## Cover
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Vendor Print Index and Schedule (VPIS)
|  | Document No. : EI027-FPA-VD-GE-VPI-001 |  | Rev.: R1 | Page 1 of 3
STYRENE PARK OFFSITE Document Title: Vendor Print Index and Schedule (VPIS)
01 | 2024-08-06 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-08-04 | IFA | S.Baitar | H.Zahiri | H.Zahiri
Rev. | Issued Date | DESCRIPTION | PREPARED | CHECKED | APPROVED

## Index
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Vendor Print Index and Schedule (VPIS)
|  |  |  | Document No. : EI027-FPA-VD-GE-VPI-001 | [8 empty] | Rev.: R1 | Page 2 of 3
Page | Revisions | [6 empty] | Page | Revisions
| R0 | R1 | R2 | R3 | R4 | R5 | R6 |  | R0 | R1 | R2 | R3 | R4 | R5 | R6
1 | [7 empty] | 41 | bar: Revisions R0 to Revisions R1
2 | [7 empty] | 42 | bar: Revisions R0 to Revisions R1
3 | [7 empty] | 43 | bar: Revisions R0 to Revisions R1
4 | [7 empty] | 44
5 | [7 empty] | 45
6 | [7 empty] | 46
7 | [7 empty] | 47
8 | [7 empty] | 48
9 | [7 empty] | 49
10 | [7 empty] | 50
11 | [7 empty] | 51
12 | [7 empty] | 52
13 | [7 empty] | 53
14 | [7 empty] | 54
15 | [7 empty] | 55
16 | [7 empty] | 56
17 | [7 empty] | 57
18 | [7 empty] | 58
19 | [7 empty] | 59
20 | [7 empty] | 60
21 | [7 empty] | 61
22 | [7 empty] | 62
23 | [7 empty] | 63
24 | [7 empty] | 64
25 | [7 empty] | 65
26 | [7 empty] | 66
27 | [7 empty] | 67
28 | [7 empty] | 68
29 | [7 empty] | 69
30 | [7 empty] | 70
31 | [7 empty] | 71
32 | [7 empty] | 72
33 | [7 empty] | 73
34 | [7 empty] | 74
35 | [7 empty] | 75
36 | [7 empty] | 76
37 | [7 empty] | 77
38 | [7 empty] | 78
39 | [7 empty] | 79
40 | [7 empty] | 80

## VPIS
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Vendor Print Index and Schedule (VPIS)
|  | Document No. : EI027-FPA-VD-GE-VPI-001 |  |  | Rev.: R1 |  | Page 3 of 3
No. | DOCUMENT NO. |  | DOCUMENT TITLE | PLANNED ISSUE DATE (DD/MM/YYYY) | P.O.I | As Built Required (Y/N?)
GENERAL
1 | E1027-FPA-VD-GE-VPI-001 |  | Vendor Print Index & Schedule (VPIS) | 2024-08-05 | IFA | N
2 | E1027-FPA-VD-GE-SVL-002 |  | Sub-Vendor List (SVL) | 2024-08-05 | IFA | N
3 | E1027-FPA-VD-GE-LST-003 |  | Final vendor Data Book Index | 2024-12-20 | IFA | N
4 | E1027-FPA-VD-GE-VDB-004 |  | Final vendor Data Book | 2024-12-28 | IFA | N
5 | E1027-FPA-VD-GE-HSE-005 |  | HSE Plan | 2024-10-06 | IFA | N
PLANNING
6 | E1027-FPA-VD-PL-WBS-001 |  | WBS | 2024-08-12 | IFA | N
7 | E1027-FPA-VD-PL-SCH-002 |  | Time Schedule | 2024-08-19 | IFA | N
8 | E1027-FPA-VD-PL-REP-003 |  | Monthly Progress Report | 2024-08-26 | IFI | N
ENGINEERING
9 | E1027-FPA-EB-ME-DWG-001 |  | As Built Drawing | 2024-12-28 | IFA | Y
QC.
10 | E1027-FPA-VD-QC-ITP-001 |  | Inspection & Test Plan (ITP) | 2024-08-05 | IFA | N
11 | E1027-FPA-VD-QC-WPS-002 |  | Welding Document (WPS & PQR) | 2024-08-20 | IFA | Y
12 | E1027-FPA-VD-QC-NDT-003 |  | Welding & NDT Map | 2024-08-24 | IFA | N
13 | E1027-FPA-VD-QC-CRT-004 |  | NDT Operator Qualification | 2024-08-29 | IFA | N
14 | E1027-FPA-VD-QC-WPQ-005 |  | Welder Performance Qualification | 2024-08-29 | IFA | N
15 | E1027-FPA-VD-QC-PRO-006 |  | NDT Procedure (RT, UT, PT, MT) | 2024-09-05 | IFA | N
16 | E1027-FPA-VD-QC-PRO-007 |  | Hydrostatic Test Procedure | 2024-09-07 | IFA | N
17 | E1027-FPA-VD-QC-PRO-008 |  | Surface Preparation & Painting Procedure | 2024-09-09 | IFA | N
18 | E1027-FPA-VD-QC-PRO-009 |  | PFHT Procedure for Head Forming and U Bend Tubes | 2024-09-11 | IFA | N