## Cover
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Work Breakdown Structure (WBS)
|  | Document No. : EI027-FPA-VD-PL-WBS-001 |  | Rev.: R0 | Page 1 of 13
STYRENE PARK OFFSITE Document Title: Work Breakdown Structure (WBS)
00 | 2024-08-11 | IFA | S.Baitar | H.Zahiri | H.Zahiri
Rev. | Issued Date | DESCRIPTION | PREPARED | CHECKED | APPROVED

## Index
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Work Breakdown Structure (WBS)
|  |  |  | Document No. : EI027-FPA-VD-PL-WBS-001 | [8 empty] | Rev.: R0 | Page 2 of 13
Page | Revisions | [6 empty] | Page | Revisions
| R0 | R1 | R2 | R3 | R4 | R5 | R6 |  | R0 | R1 | R2 | R3 | R4 | R5 | R6
1 | [7 empty] | 41 | bar: Revisions R0
2 | [7 empty] | 42 | bar: Revisions R0
3 | [7 empty] | 43 | bar: Revisions R0
4 | [7 empty] | 44 | bar: Revisions R0
5 | [7 empty] | 45 | bar: Revisions R0
6 | [7 empty] | 46 | bar: Revisions R0
7 | [7 empty] | 47 | bar: Revisions R0
8 | [7 empty] | 48 | bar: Revisions R0
9 | [7 empty] | 49 | bar: Revisions R0
10 | [7 empty] | 50 | bar: Revisions R0
11 | [7 empty] | 51 | bar: Revisions R0
12 | [7 empty] | 52
13 | [7 empty] | 53
14 | [7 empty] | 54
15 | [7 empty] | 55
16 | [7 empty] | 56
17 | [7 empty] | 57
18 | [7 empty] | 58
19 | [7 empty] | 59
20 | [7 empty] | 60
21 | [7 empty] | 61
22 | [7 empty] | 62
23 | [7 empty] | 63
24 | [7 empty] | 64
25 | [7 empty] | 65
26 | [7 empty] | 66
27 | [7 empty] | 67
28 | [7 empty] | 68
29 | [7 empty] | 69
30 | [7 empty] | 70
31 | [7 empty] | 71
32 | [7 empty] | 72
33 | [7 empty] | 73
34 | [7 empty] | 74
35 | [7 empty] | 75
36 | [7 empty] | 76
37 | [7 empty] | 77
38 | [7 empty] | 78
39 | [7 empty] | 79
40 | [7 empty] | 80

## WBS
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: Work Breakdown Structure (WBS)
[6 empty] | Document No. : EI027-FPA-VD-PL-WBS-001 |  | Rev.: R0
Work Breakdown Structure (WBS)
Level No.(*) |  |  |  |  | Description |  | Weight Factor (%)
1 | 1 | 1 | 1 | 1 | Shell & Tube Heat exchanger |  |  |  | 100
1.1 | 1.1 | 1.1 | 1.1 | 1.1 | Engineering |  | 100% |  | 10
1.1.1 | 1.1.1 | 1.1.1 | 1.1.1 | 1.1.1 | Vendor Print Index & Schedule (VPIS) |  | 3% |  | 0.3
1.1.2 | 1.1.2 | 1.1.2 | 1.1.2 | 1.1.2 | Sub-Vendor List (SVL) |  | 5% |  | 0.5
1.1.3 | 1.1.3 | 1.1.3 | 1.1.3 | 1.1.3 | Final vendor Data Book Index |  | 3% |  | 0.3
1.1.4 | 1.1.4 | 1.1.4 | 1.1.4 | 1.1.4 | Final vendor Data Book |  | 5% |  | 0.5
1.1.5 | 1.1.5 | 1.1.5 | 1.1.5 | 1.1.5 | HSE Plan |  | 4% |  | 0.4
1.1.6 | 1.1.6 | 1.1.6 | 1.1.6 | 1.1.6 | WBS for Shell & Tube Heat Exchangers |  | 5% |  | 0.5
1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | 1.1.7 | Time Schedule for Shell & Tube Heat Exchangers |  | 7% |  | 0.7
1.1.8 | 1.1.8 | 1.1.8 | 1.1.8 | 1.1.8 | Monthly Progress Report for Shell & Tube Heat Exchangers |  | 5% |  | 0.5
1.1.9 | 1.1.9 | 1.1.9 | 1.1.9 | 1.1.9 | As Built Drawing |  | 13% |  | 1.3
1.1.10 | 1.1.10 | 1.1.10 | 1.1.10 | 1.1.10 | Inspection & Test Plan (ITP) |  | 5% |  | 0.5
1.1.11 | 1.1.11 | 1.1.11 | 1.1.11 | 1.1.11 | Welding Document (WPS & PQR) |  | 8% |  | 0.8
1.1.12 | 1.1.12 | 1.1.12 | 1.1.12 | 1.1.12 | Welding & NDT Map |  | 7% |  | 0.7
1.1.13 | 1.1.13 | 1.1.13 | 1.1.13 | 1.1.13 | NDT Operator Qualification |  | 7% |  | 0.7
1.1.14 | 1.1.14 | 1.1.14 | 1.1.14 | 1.1.14 | Welder Performance Qualification |  | 5% |  | 0.5
1.1.15 | 1.1.15 | 1.1.15 | 1.1.15 | 1.1.15 | NDT Procedure (RT, UT, PT, MT) |  | 6% |  | 0.6
1.1.16 | 1.1.16 | 1.1.16 | 1.1.16 | 1.1.16 | Hydrostatic Test Procedure |  | 7% |  | 0.7
1.1.17 | 1.1.17 | 1.1.17 | 1.1.17 | 1.1.17 | Surface Preparation & Painting Procedure |  | 5% |  | 0.5
1.2 | 1.2 | 1.2 | 1.2 | 1.2 | Procurement |  | 100% |  | 40
1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | 1.2.1 | Plate |  | 23% |  | 9.2
1.2.1.1 | 1.2.1.1 | 1.2.1.1 | 1.2.1.1 | 1.2.1.1 | PO placement |  | 25% |  | 2.3
1.2.1.2 | 1.2.1.2 | 1.2.1.2 | 1.2.1.2 | 1.2.1.2 | Fabrication |  | 65% |  | 5.98
1.2.1.3 | 1.2.1.3 | 1.2.1.3 | 1.2.1.3 | 1.2.1.3 | Shipping |  | 7% |  | 0.644
1.2.1.4 | 1.2.1.4 | 1.2.1.4 | 1.2.1.4 | 1.2.1.4 | Custom clearance |  | 3% |  | 0.276
1.2.2 | 1.2.2 | 1.2.2 | 1.2.2 | 1.2.2 | Head |  | 20% |  | 8
1.2.2.1 | 1.2.2.1 | 1.2.2.1 | 1.2.2.1 | 1.2.2.1 | PO placement |  | 25% |  | 2
1.2.2.2 | 1.2.2.2 | 1.2.2.2 | 1.2.2.2 | 1.2.2.2 | Fabrication |  | 65% |  | 5.2
1.2.2.3 | 1.2.2.3 | 1.2.2.3 | 1.2.2.3 | 1.2.2.3 | Shipping |  | 7% |  | 0.56
1.2.2.4 | 1.2.2.4 | 1.2.2.4 | 1.2.2.4 | 1.2.2.4 | Custom clearance |  | 3% |  | 0.24
1.2.3 | 1.2.3 | 1.2.3 | 1.2.3 | 1.2.3 | U-Tube |  | 19% |  | 7.6
1.2.3.1 | 1.2.3.1 | 1.2.3.1 | 1.2.3.1 | 1.2.3.1 | PO placement |  | 25% |  | 1.9
1.2.3.2 | 1.2.3.2 | 1.2.3.2 | 1.2.3.2 | 1.2.3.2 | Fabrication |  | 65% |  | 4.94
1.2.3.3 | 1.2.3.3 | 1.2.3.3 | 1.2.3.3 | 1.2.3.3 | Shipping |  | 7% |  | 0.532
1.2.3.4 | 1.2.3.4 | 1.2.3.4 | 1.2.3.4 | 1.2.3.4 | Custom clearance |  | 3% |  | 0.228
1.2.4 | 1.2.4 | 1.2.4 | 1.2.4 | 1.2.4 | Tube sheet |  | 7% |  | 2.8
1.2.4.1 | 1.2.4.1 | 1.2.4.1 | 1.2.4.1 | 1.2.4.1 | PO placement |  | 25% |  | 0.7
1.2.4.2 | 1.2.4.2 | 1.2.4.2 | 1.2.4.2 | 1.2.4.2 | Fabrication |  | 65% |  | 1.82
1.2.4.3 | 1.2.4.3 | 1.2.4.3 | 1.2.4.3 | 1.2.4.3 | Shipping |  | 7% |  | 0.196
1.2.4.4 | 1.2.4.4 | 1.2.4.4 | 1.2.4.4 | 1.2.4.4 | Custom clearance |  | 3% |  | 0.084
1.2.5 | 1.2.5 | 1.2.5 | 1.2.5 | 1.2.5 | Baffle |  | 5% |  | 2
1.2.5.1 | 1.2.5.1 | 1.2.5.1 | 1.2.5.1 | 1.2.5.1 | PO placement |  | 25% |  | 0.5
1.2.5.2 | 1.2.5.2 | 1.2.5.2 | 1.2.5.2 | 1.2.5.2 | Fabrication |  | 65% |  | 1.3
1.2.5.3 | 1.2.5.3 | 1.2.5.3 | 1.2.5.3 | 1.2.5.3 | Shipping |  | 7% |  | 0.14
1.2.5.4 | 1.2.5.4 | 1.2.5.4 | 1.2.5.4 | 1.2.5.4 | Custom clearance |  | 3% |  | 0.06
1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | 1.2.6 | Elbow |  | 2% |  | 0.8
1.2.6.1 | 1.2.6.1 | 1.2.6.1 | 1.2.6.1 | 1.2.6.1 | PO placement |  | 25% |  | 0.2
1.2.6.2 | 1.2.6.2 | 1.2.6.2 | 1.2.6.2 | 1.2.6.2 | Fabrication |  | 65% |  | 0.52
1.2.6.3 | 1.2.6.3 | 1.2.6.3 | 1.2.6.3 | 1.2.6.3 | Shipping |  | 7% |  | 0.056
1.2.6.4 | 1.2.6.4 | 1.2.6.4 | 1.2.6.4 | 1.2.6.4 | Custom clearance |  | 3% |  | 0.024
1.2.7 | 1.2.7 | 1.2.7 | 1.2.7 | 1.2.7 | Pipe |  | 9% |  | 3.6
1.2.7.1 | 1.2.7.1 | 1.2.7.1 | 1.2.7.1 | 1.2.7.1 | PO placement |  | 25% |  | 0.9
1.2.7.2 | 1.2.7.2 | 1.2.7.2 | 1.2.7.2 | 1.2.7.2 | Fabrication |  | 65% |  | 2.34
1.2.7.3 | 1.2.7.3 | 1.2.7.3 | 1.2.7.3 | 1.2.7.3 | Shipping |  | 7% |  | 0.252
1.2.7.4 | 1.2.7.4 | 1.2.7.4 | 1.2.7.4 | 1.2.7.4 | Custom clearance |  | 3% |  | 0.108
1.2.8 | 1.2.8 | 1.2.8 | 1.2.8 | 1.2.8 | Flange |  | 7% |  | 2.8
1.2.8.1 | 1.2.8.1 | 1.2.8.1 | 1.2.8.1 | 1.2.8.1 | PO placement |  | 25% |  | 0.7
1.2.8.2 | 1.2.8.2 | 1.2.8.2 | 1.2.8.2 | 1.2.8.2 | Fabrication |  | 65% |  | 1.82
1.2.8.3 | 1.2.8.3 | 1.2.8.3 | 1.2.8.3 | 1.2.8.3 | Shipping |  | 7% |  | 0.196
1.2.8.4 | 1.2.8.4 | 1.2.8.4 | 1.2.8.4 | 1.2.8.4 | Custom clearance |  | 3% |  | 0.084
1.2.9 | 1.2.9 | 1.2.9 | 1.2.9 | 1.2.9 | Spacer |  | 3% |  | 1.2
1.2.9.1 | 1.2.9.1 | 1.2.9.1 | 1.2.9.1 | 1.2.9.1 | PO placement |  | 25% |  | 0.3
1.2.9.2 | 1.2.9.2 | 1.2.9.2 | 1.2.9.2 | 1.2.9.2 | Fabrication |  | 65% |  | 0.78
1.2.9.3 | 1.2.9.3 | 1.2.9.3 | 1.2.9.3 | 1.2.9.3 | Shipping |  | 7% |  | 0.084
1.2.9.4 | 1.2.9.4 | 1.2.9.4 | 1.2.9.4 | 1.2.9.4 | Custom clearance |  | 3% |  | 0.036
1.2.10 | 1.2.10 | 1.2.10 | 1.2.10 | 1.2.10 | Nut & bolt |  | 2% |  | 0.8
1.2.10.1 | 1.2.10.1 | 1.2.10.1 | 1.2.10.1 | 1.2.10.1 | PO placement |  | 25% |  | 0.2
1.2.10.2 | 1.2.10.2 | 1.2.10.2 | 1.2.10.2 | 1.2.10.2 | Fabrication |  | 65% |  | 0.52
1.2.10.3 | 1.2.10.3 | 1.2.10.3 | 1.2.10.3 | 1.2.10.3 | Shipping |  | 7% |  | 0.056
1.2.10.4 | 1.2.10.4 | 1.2.10.4 | 1.2.10.4 | 1.2.10.4 | Custom clearance |  | 3% |  | 0.024
1.2.11 | 1.2.11 | 1.2.11 | 1.2.11 | 1.2.11 | Gasket |  | 1% |  | 0.4
1.2.11.1 | 1.2.11.1 | 1.2.11.1 | 1.2.11.1 | 1.2.11.1 | PO placement |  | 25% |  | 0.1
1.2.11.2 | 1.2.11.2 | 1.2.11.2 | 1.2.11.2 | 1.2.11.2 | Fabrication |  | 65% |  | 0.26
1.2.11.3 | 1.2.11.3 | 1.2.11.3 | 1.2.11.3 | 1.2.11.3 | Shipping |  | 7% |  | 0.028
1.2.11.4 | 1.2.11.4 | 1.2.11.4 | 1.2.11.4 | 1.2.11.4 | Custom clearance |  | 3% |  | 0.012
1.2.12 | 1.2.12 | 1.2.12 | 1.2.12 | 1.2.12 | Paint |  | 1% |  | 0.4
1.2.12.1 | 1.2.12.1 | 1.2.12.1 | 1.2.12.1 | 1.2.12.1 | PO placement |  | 25% |  | 0.1
1.2.12.2 | 1.2.12.2 | 1.2.12.2 | 1.2.12.2 | 1.2.12.2 | Fabrication |  | 65% |  | 0.26
1.2.12.3 | 1.2.12.3 | 1.2.12.3 | 1.2.12.3 | 1.2.12.3 | Shipping |  | 7% |  | 0.028
1.2.12.4 | 1.2.12.4 | 1.2.12.4 | 1.2.12.4 | 1.2.12.4 | Custom clearance |  | 3% |  | 0.012
1.2.13 | 1.2.13 | 1.2.13 | 1.2.13 | 1.2.13 | Name plate |  | 1% |  | 0.4
1.2.13.1 | 1.2.13.1 | 1.2.13.1 | 1.2.13.1 | 1.2.13.1 | PO placement |  | 25% |  | 0.1
1.2.13.2 | 1.2.13.2 | 1.2.13.2 | 1.2.13.2 | 1.2.13.2 | Fabrication |  | 65% |  | 0.26
1.2.13.3 | 1.2.13.3 | 1.2.13.3 | 1.2.13.3 | 1.2.13.3 | Shipping |  | 7% |  | 0.028
1.2.13.4 | 1.2.13.4 | 1.2.13.4 | 1.2.13.4 | 1.2.13.4 | Custom clearance |  | 3% |  | 0.012
1.3 | 1.3 | 1.3 | 1.3 | 1.3 | Fabrication |  |  |  | 50
1.3.1 | 1.3.1 | 1.3.1 | 1.3.1 | 1.3.1 | RU-0001A-E-02 |  | 50% |  | 25
1.3.1.1 | 1.3.1.1 | 1.3.1.1 | 1.3.1.1 | 1.3.1.1 | Prefabrication |  | 40% |  | 10
1.3.1.1.1 | 1.3.1.1.1 | 1.3.1.1.1 | 1.3.1.1.1 | 1.3.1.1.1 | Shell |  | 35% |  | 3.5
1.3.1.1.1.1 | 1.3.1.1.1.1 | 1.3.1.1.1.1 | 1.3.1.1.1.1 | 1.3.1.1.1.1 | Cutting |  | 10% |  | 0.35
1.3.1.1.1.2 | 1.3.1.1.1.2 | 1.3.1.1.1.2 | 1.3.1.1.1.2 | 1.3.1.1.1.2 | Beveling |  | 10% |  | 0.35
1.3.1.1.1.3 | 1.3.1.1.1.3 | 1.3.1.1.1.3 | 1.3.1.1.1.3 | 1.3.1.1.1.3 | Rolling |  | 15% |  | 0.525
1.3.1.1.1.4 | 1.3.1.1.1.4 | 1.3.1.1.1.4 | 1.3.1.1.1.4 | 1.3.1.1.1.4 | Assembly (LW) |  | 25% |  | 0.875
1.3.1.1.1.5 | 1.3.1.1.1.5 | 1.3.1.1.1.5 | 1.3.1.1.1.5 | 1.3.1.1.1.5 | Welding (LW) |  | 35% |  | 1.225
1.3.1.1.1.6 | 1.3.1.1.1.6 | 1.3.1.1.1.6 | 1.3.1.1.1.6 | 1.3.1.1.1.6 | Reroll |  | 5% |  | 0.175
1.3.1.1.2 | 1.3.1.1.2 | 1.3.1.1.2 | 1.3.1.1.2 | 1.3.1.1.2 | Channel |  | 15% |  | 1.5
1.3.1.1.2.1 | 1.3.1.1.2.1 | 1.3.1.1.2.1 | 1.3.1.1.2.1 | 1.3.1.1.2.1 | Cutting |  | 10% |  | 0.15
1.3.1.1.2.2 | 1.3.1.1.2.2 | 1.3.1.1.2.2 | 1.3.1.1.2.2 | 1.3.1.1.2.2 | Beveling |  | 10% |  | 0.15
1.3.1.1.2.3 | 1.3.1.1.2.3 | 1.3.1.1.2.3 | 1.3.1.1.2.3 | 1.3.1.1.2.3 | Rolling |  | 15% |  | 0.225
1.3.1.1.2.4 | 1.3.1.1.2.4 | 1.3.1.1.2.4 | 1.3.1.1.2.4 | 1.3.1.1.2.4 | Assembly (LW) |  | 25% |  | 0.375
1.3.1.1.2.5 | 1.3.1.1.2.5 | 1.3.1.1.2.5 | 1.3.1.1.2.5 | 1.3.1.1.2.5 | Welding (LW) |  | 35% |  | 0.525
1.3.1.1.2.6 | 1.3.1.1.2.6 | 1.3.1.1.2.6 | 1.3.1.1.2.6 | 1.3.1.1.2.6 | Reroll |  | 5% |  | 0.075
1.3.1.1.3 | 1.3.1.1.3 | 1.3.1.1.3 | 1.3.1.1.3 | 1.3.1.1.3 | Cone |  | 20% |  | 2
1.3.1.1.3.1 | 1.3.1.1.3.1 | 1.3.1.1.3.1 | 1.3.1.1.3.1 | 1.3.1.1.3.1 | Cutting |  | 10% |  | 0.2
1.3.1.1.3.2 | 1.3.1.1.3.2 | 1.3.1.1.3.2 | 1.3.1.1.3.2 | 1.3.1.1.3.2 | Beveling |  | 10% |  | 0.2
1.3.1.1.3.3 | 1.3.1.1.3.3 | 1.3.1.1.3.3 | 1.3.1.1.3.3 | 1.3.1.1.3.3 | Rolling |  | 15% |  | 0.3
1.3.1.1.3.4 | 1.3.1.1.3.4 | 1.3.1.1.3.4 | 1.3.1.1.3.4 | 1.3.1.1.3.4 | Assembly (LW) |  | 25% |  | 0.5
1.3.1.1.3.5 | 1.3.1.1.3.5 | 1.3.1.1.3.5 | 1.3.1.1.3.5 | 1.3.1.1.3.5 | Welding (LW) |  | 35% |  | 0.7
1.3.1.1.3.6 | 1.3.1.1.3.6 | 1.3.1.1.3.6 | 1.3.1.1.3.6 | 1.3.1.1.3.6 | Reroll |  | 5% |  | 0.1
1.3.1.1.4 | 1.3.1.1.4 | 1.3.1.1.4 | 1.3.1.1.4 | 1.3.1.1.4 | Saddle fabrication |  | 10% |  | 1
1.3.1.1.4.1 | 1.3.1.1.4.1 | 1.3.1.1.4.1 | 1.3.1.1.4.1 | 1.3.1.1.4.1 | Cutting |  | 10% |  | 0.1
1.3.1.1.4.2 | 1.3.1.1.4.2 | 1.3.1.1.4.2 | 1.3.1.1.4.2 | 1.3.1.1.4.2 | Beveling |  | 10% |  | 0.1
1.3.1.1.4.3 | 1.3.1.1.4.3 | 1.3.1.1.4.3 | 1.3.1.1.4.3 | 1.3.1.1.4.3 | Rolling |  | 15% |  | 0.15
1.3.1.1.4.4 | 1.3.1.1.4.4 | 1.3.1.1.4.4 | 1.3.1.1.4.4 | 1.3.1.1.4.4 | Assembly (LW) |  | 25% |  | 0.25
1.3.1.1.4.5 | 1.3.1.1.4.5 | 1.3.1.1.4.5 | 1.3.1.1.4.5 | 1.3.1.1.4.5 | Welding (LW) |  | 35% |  | 0.35
1.3.1.1.4.6 | 1.3.1.1.4.6 | 1.3.1.1.4.6 | 1.3.1.1.4.6 | 1.3.1.1.4.6 | Reroll |  | 5% |  | 0.05
1.3.1.1.5 | 1.3.1.1.5 | 1.3.1.1.5 | 1.3.1.1.5 | 1.3.1.1.5 | Nozzle fabrication (part 1) |  | 8% |  | 0.8
1.3.1.1.5.1 | 1.3.1.1.5.1 | 1.3.1.1.5.1 | 1.3.1.1.5.1 | 1.3.1.1.5.1 | Pipe cutting |  | 15% |  | 0.12
1.3.1.1.5.2 | 1.3.1.1.5.2 | 1.3.1.1.5.2 | 1.3.1.1.5.2 | 1.3.1.1.5.2 | Pipe beveling |  | 15% |  | 0.12
1.3.1.1.5.3 | 1.3.1.1.5.3 | 1.3.1.1.5.3 | 1.3.1.1.5.3 | 1.3.1.1.5.3 | Assembly pipe to flange |  | 25% |  | 0.2
1.3.1.1.5.4 | 1.3.1.1.5.4 | 1.3.1.1.5.4 | 1.3.1.1.5.4 | 1.3.1.1.5.4 | Welding pipe to flange |  | 45% |  | 0.36
1.3.1.1.6 | 1.3.1.1.6 | 1.3.1.1.6 | 1.3.1.1.6 | 1.3.1.1.6 | Nozzle fabrication (part 2) |  | 12% |  | 1.2
1.3.1.1.6.1 | 1.3.1.1.6.1 | 1.3.1.1.6.1 | 1.3.1.1.6.1 | 1.3.1.1.6.1 | Pipe cutting |  | 5% |  | 0.06
1.3.1.1.6.2 | 1.3.1.1.6.2 | 1.3.1.1.6.2 | 1.3.1.1.6.2 | 1.3.1.1.6.2 | Pipe beveling |  | 5% |  | 0.06
1.3.1.1.6.3 | 1.3.1.1.6.3 | 1.3.1.1.6.3 | 1.3.1.1.6.3 | 1.3.1.1.6.3 | Assembly pipe to flange |  | 15% |  | 0.18
1.3.1.1.6.4 | 1.3.1.1.6.4 | 1.3.1.1.6.4 | 1.3.1.1.6.4 | 1.3.1.1.6.4 | Welding pipe to flange |  | 35% |  | 0.42
1.3.1.1.6.5 | 1.3.1.1.6.5 | 1.3.1.1.6.5 | 1.3.1.1.6.5 | 1.3.1.1.6.5 | Assembly elbow to pipe |  | 10% |  | 0.12
1.3.1.1.6.6 | 1.3.1.1.6.6 | 1.3.1.1.6.6 | 1.3.1.1.6.6 | 1.3.1.1.6.6 | Welding elbow to pipe |  | 30% |  | 0.36
1.3.1.2 | 1.3.1.2 | 1.3.1.2 | 1.3.1.2 | 1.3.1.2 | Final assembly |  | 50% |  | 12.5
1.3.1.2.1 | 1.3.1.2.1 | 1.3.1.2.1 | 1.3.1.2.1 | 1.3.1.2.1 | Shell |  | 40% |  | 5
1.3.1.2.1.1 | 1.3.1.2.1.1 | 1.3.1.2.1.1 | 1.3.1.2.1.1 | 1.3.1.2.1.1 | Assembly shell segments (CW) |  | 12% |  | 0.6
1.3.1.2.1.2 | 1.3.1.2.1.2 | 1.3.1.2.1.2 | 1.3.1.2.1.2 | 1.3.1.2.1.2 | Welding shell segments (CW) |  | 27% |  | 1.35
1.3.1.2.1.3 | 1.3.1.2.1.3 | 1.3.1.2.1.3 | 1.3.1.2.1.3 | 1.3.1.2.1.3 | Opening for nozzle assembly |  | 5% |  | 0.25
1.3.1.2.1.4 | 1.3.1.2.1.4 | 1.3.1.2.1.4 | 1.3.1.2.1.4 | 1.3.1.2.1.4 | Nozzle assembly to shell |  | 5% |  | 0.25
1.3.1.2.1.5 | 1.3.1.2.1.5 | 1.3.1.2.1.5 | 1.3.1.2.1.5 | 1.3.1.2.1.5 | Nozzle welding to shell |  | 10% |  | 0.5
1.3.1.2.1.6 | 1.3.1.2.1.6 | 1.3.1.2.1.6 | 1.3.1.2.1.6 | 1.3.1.2.1.6 | Assembly head to shell |  | 3% |  | 0.15
1.3.1.2.1.7 | 1.3.1.2.1.7 | 1.3.1.2.1.7 | 1.3.1.2.1.7 | 1.3.1.2.1.7 | Welding head to shell |  | 7% |  | 0.35
1.3.1.2.1.8 | 1.3.1.2.1.8 | 1.3.1.2.1.8 | 1.3.1.2.1.8 | 1.3.1.2.1.8 | Assembly cone to shell |  | 3% |  | 0.15
1.3.1.2.1.9 | 1.3.1.2.1.9 | 1.3.1.2.1.9 | 1.3.1.2.1.9 | 1.3.1.2.1.9 | Welding cone to shell |  | 7% |  | 0.35
1.3.1.2.1.10 | 1.3.1.2.1.10 | 1.3.1.2.1.10 | 1.3.1.2.1.10 | 1.3.1.2.1.10 | Assembly segment shell to cone |  | 3% |  | 0.15
1.3.1.2.1.11 | 1.3.1.2.1.11 | 1.3.1.2.1.11 | 1.3.1.2.1.11 | 1.3.1.2.1.11 | Welding segment shell to cone |  | 8% |  | 0.4
1.3.1.2.1.12 | 1.3.1.2.1.12 | 1.3.1.2.1.12 | 1.3.1.2.1.12 | 1.3.1.2.1.12 | Assembly body flange to shell |  | 3% |  | 0.15
1.3.1.2.1.13 | 1.3.1.2.1.13 | 1.3.1.2.1.13 | 1.3.1.2.1.13 | 1.3.1.2.1.13 | Welding body flange to shell |  | 7% |  | 0.35
1.3.1.2.2 | 1.3.1.2.2 | 1.3.1.2.2 | 1.3.1.2.2 | 1.3.1.2.2 | Channel |  | 15% |  | 1.875
1.3.1.2.2.1 | 1.3.1.2.2.1 | 1.3.1.2.2.1 | 1.3.1.2.2.1 | 1.3.1.2.2.1 | Assembly head to channel |  | 10% |  | 0.1875
1.3.1.2.2.2 | 1.3.1.2.2.2 | 1.3.1.2.2.2 | 1.3.1.2.2.2 | 1.3.1.2.2.2 | Welding head to channel |  | 20% |  | 0.375
1.3.1.2.2.3 | 1.3.1.2.2.3 | 1.3.1.2.2.3 | 1.3.1.2.2.3 | 1.3.1.2.2.3 | Assembly body flange to channel |  | 10% |  | 0.1875
1.3.1.2.2.4 | 1.3.1.2.2.4 | 1.3.1.2.2.4 | 1.3.1.2.2.4 | 1.3.1.2.2.4 | Welding body flange to channel |  | 20% |  | 0.375
1.3.1.2.2.5 | 1.3.1.2.2.5 | 1.3.1.2.2.5 | 1.3.1.2.2.5 | 1.3.1.2.2.5 | Opening for nozzle assembly |  | 10% |  | 0.1875
1.3.1.2.2.6 | 1.3.1.2.2.6 | 1.3.1.2.2.6 | 1.3.1.2.2.6 | 1.3.1.2.2.6 | Assembly nozzle to channel |  | 10% |  | 0.1875
1.3.1.2.2.7 | 1.3.1.2.2.7 | 1.3.1.2.2.7 | 1.3.1.2.2.7 | 1.3.1.2.2.7 | Welding nozzle to channel |  | 20% |  | 0.375
1.3.1.2.3 | 1.3.1.2.3 | 1.3.1.2.3 | 1.3.1.2.3 | 1.3.1.2.3 | Bundle structure |  | 45% |  | 5.625
1.3.1.2.3.1 | 1.3.1.2.3.1 | 1.3.1.2.3.1 | 1.3.1.2.3.1 | 1.3.1.2.3.1 | Assembly bundle structure |  | 15% |  | 0.84375
1.3.1.2.3.2 | 1.3.1.2.3.2 | 1.3.1.2.3.2 | 1.3.1.2.3.2 | 1.3.1.2.3.2 | Insert tube to bundle structure |  | 10% |  | 0.5625
1.3.1.2.3.3 | 1.3.1.2.3.3 | 1.3.1.2.3.3 | 1.3.1.2.3.3 | 1.3.1.2.3.3 | Tube to tube sheet welding |  | 30% |  | 1.6875
1.3.1.2.3.4 | 1.3.1.2.3.4 | 1.3.1.2.3.4 | 1.3.1.2.3.4 | 1.3.1.2.3.4 | Expanding |  | 5% |  | 0.28125
1.3.1.2.3.5 | 1.3.1.2.3.5 | 1.3.1.2.3.5 | 1.3.1.2.3.5 | 1.3.1.2.3.5 | Insert bundle to shell |  | 2% |  | 0.1125
1.3.1.2.3.6 | 1.3.1.2.3.6 | 1.3.1.2.3.6 | 1.3.1.2.3.6 | 1.3.1.2.3.6 | Assembly tube sheet to shell |  | 5% |  | 0.28125
1.3.1.2.3.7 | 1.3.1.2.3.7 | 1.3.1.2.3.7 | 1.3.1.2.3.7 | 1.3.1.2.3.7 | Welding tube sheet to shell |  | 10% |  | 0.5625
1.3.1.2.3.8 | 1.3.1.2.3.8 | 1.3.1.2.3.8 | 1.3.1.2.3.8 | 1.3.1.2.3.8 | Assembly saddle to shell |  | 5% |  | 0.28125
1.3.1.2.3.9 | 1.3.1.2.3.9 | 1.3.1.2.3.9 | 1.3.1.2.3.9 | 1.3.1.2.3.9 | Welding saddle to shell |  | 10% |  | 0.5625
1.3.1.2.3.10 | 1.3.1.2.3.10 | 1.3.1.2.3.10 | 1.3.1.2.3.10 | 1.3.1.2.3.10 | Assembly external part to shell& channel |  | 2% |  | 0.1125
1.3.1.2.3.11 | 1.3.1.2.3.11 | 1.3.1.2.3.11 | 1.3.1.2.3.11 | 1.3.1.2.3.11 | Welding external part to shell& channel |  | 4% |  | 0.225
1.3.1.2.3.12 | 1.3.1.2.3.12 | 1.3.1.2.3.12 | 1.3.1.2.3.12 | 1.3.1.2.3.12 | Final NDT |  | 2% |  | 0.1125
1.3.1.3 | 1.3.1.3 | 1.3.1.3 | 1.3.1.3 | 1.3.1.3 | Test |  | 5% |  | 1.25
1.3.1.3.1 | 1.3.1.3.1 | 1.3.1.3.1 | 1.3.1.3.1 | 1.3.1.3.1 | Hydrostatic Test |  | 100% |  | 1.25
1.3.1.4 | 1.3.1.4 | 1.3.1.4 | 1.3.1.4 | 1.3.1.4 | Sandblast & paint |  | 5% |  | 1.25
1.3.1.4.1 | 1.3.1.4.1 | 1.3.1.4.1 | 1.3.1.4.1 | 1.3.1.4.1 | Sandblast |  | 50% |  | 0.625
1.3.1.4.2 | 1.3.1.4.2 | 1.3.1.4.2 | 1.3.1.4.2 | 1.3.1.4.2 | Painting |  | 50% |  | 0.625
1.3.2 | 1.3.2 | 1.3.2 | 1.3.2 | 1.3.2 | RU-0001A-E-02 |  | 50% |  | 25
1.3.2.1 | 1.3.2.1 | 1.3.2.1 | 1.3.2.1 | 1.3.2.1 | Prefabrication |  | 40% |  | 10
1.3.2.1.1 | 1.3.2.1.1 | 1.3.2.1.1 | 1.3.2.1.1 | 1.3.2.1.1 | Shell |  | 35% |  | 3.5
1.3.2.1.1.1 | 1.3.2.1.1.1 | 1.3.2.1.1.1 | 1.3.2.1.1.1 | 1.3.2.1.1.1 | Cutting |  | 10% |  | 0.35
1.3.2.1.1.2 | 1.3.2.1.1.2 | 1.3.2.1.1.2 | 1.3.2.1.1.2 | 1.3.2.1.1.2 | Beveling |  | 10% |  | 0.35
1.3.2.1.1.3 | 1.3.2.1.1.3 | 1.3.2.1.1.3 | 1.3.2.1.1.3 | 1.3.2.1.1.3 | Rolling |  | 15% |  | 0.525
1.3.2.1.1.4 | 1.3.2.1.1.4 | 1.3.2.1.1.4 | 1.3.2.1.1.4 | 1.3.2.1.1.4 | Assembly (LW) |  | 25% |  | 0.875
1.3.2.1.1.5 | 1.3.2.1.1.5 | 1.3.2.1.1.5 | 1.3.2.1.1.5 | 1.3.2.1.1.5 | Welding (LW) |  | 35% |  | 1.225
1.3.2.1.1.6 | 1.3.2.1.1.6 | 1.3.2.1.1.6 | 1.3.2.1.1.6 | 1.3.2.1.1.6 | Reroll |  | 5% |  | 0.175
1.3.2.1.2 | 1.3.2.1.2 | 1.3.2.1.2 | 1.3.2.1.2 | 1.3.2.1.2 | Channel |  | 15% |  | 1.5
1.3.2.1.2.1 | 1.3.2.1.2.1 | 1.3.2.1.2.1 | 1.3.2.1.2.1 | 1.3.2.1.2.1 | Cutting |  | 10% |  | 0.15
1.3.2.1.2.2 | 1.3.2.1.2.2 | 1.3.2.1.2.2 | 1.3.2.1.2.2 | 1.3.2.1.2.2 | Beveling |  | 10% |  | 0.15
1.3.2.1.2.3 | 1.3.2.1.2.3 | 1.3.2.1.2.3 | 1.3.2.1.2.3 | 1.3.2.1.2.3 | Rolling |  | 15% |  | 0.225
1.3.2.1.2.4 | 1.3.2.1.2.4 | 1.3.2.1.2.4 | 1.3.2.1.2.4 | 1.3.2.1.2.4 | Assembly (LW) |  | 25% |  | 0.375
1.3.2.1.2.5 | 1.3.2.1.2.5 | 1.3.2.1.2.5 | 1.3.2.1.2.5 | 1.3.2.1.2.5 | Welding (LW) |  | 35% |  | 0.525
1.3.2.1.2.6 | 1.3.2.1.2.6 | 1.3.2.1.2.6 | 1.3.2.1.2.6 | 1.3.2.1.2.6 | Reroll |  | 5% |  | 0.075
1.3.2.1.3 | 1.3.2.1.3 | 1.3.2.1.3 | 1.3.2.1.3 | 1.3.2.1.3 | Cone |  | 20% |  | 2
1.3.2.1.3.1 | 1.3.2.1.3.1 | 1.3.2.1.3.1 | 1.3.2.1.3.1 | 1.3.2.1.3.1 | Cutting |  | 10% |  | 0.2
1.3.2.1.3.2 | 1.3.2.1.3.2 | 1.3.2.1.3.2 | 1.3.2.1.3.2 | 1.3.2.1.3.2 | Beveling |  | 10% |  | 0.2
1.3.2.1.3.3 | 1.3.2.1.3.3 | 1.3.2.1.3.3 | 1.3.2.1.3.3 | 1.3.2.1.3.3 | Rolling |  | 15% |  | 0.3
1.3.2.1.3.4 | 1.3.2.1.3.4 | 1.3.2.1.3.4 | 1.3.2.1.3.4 | 1.3.2.1.3.4 | Assembly (LW) |  | 25% |  | 0.5
1.3.2.1.3.5 | 1.3.2.1.3.5 | 1.3.2.1.3.5 | 1.3.2.1.3.5 | 1.3.2.1.3.5 | Welding (LW) |  | 35% |  | 0.7
1.3.2.1.3.6 | 1.3.2.1.3.6 | 1.3.2.1.3.6 | 1.3.2.1.3.6 | 1.3.2.1.3.6 | Reroll |  | 5% |  | 0.1
1.3.2.1.4 | 1.3.2.1.4 | 1.3.2.1.4 | 1.3.2.1.4 | 1.3.2.1.4 | Saddle fabrication |  | 10% |  | 1
1.3.2.1.4.1 | 1.3.2.1.4.1 | 1.3.2.1.4.1 | 1.3.2.1.4.1 | 1.3.2.1.4.1 | Cutting |  | 10% |  | 0.1
1.3.2.1.4.2 | 1.3.2.1.4.2 | 1.3.2.1.4.2 | 1.3.2.1.4.2 | 1.3.2.1.4.2 | Beveling |  | 10% |  | 0.1
1.3.2.1.4.3 | 1.3.2.1.4.3 | 1.3.2.1.4.3 | 1.3.2.1.4.3 | 1.3.2.1.4.3 | Rolling |  | 15% |  | 0.15
1.3.2.1.4.4 | 1.3.2.1.4.4 | 1.3.2.1.4.4 | 1.3.2.1.4.4 | 1.3.2.1.4.4 | Assembly (LW) |  | 25% |  | 0.25
1.3.2.1.4.5 | 1.3.2.1.4.5 | 1.3.2.1.4.5 | 1.3.2.1.4.5 | 1.3.2.1.4.5 | Welding (LW) |  | 35% |  | 0.35
1.3.2.1.4.6 | 1.3.2.1.4.6 | 1.3.2.1.4.6 | 1.3.2.1.4.6 | 1.3.2.1.4.6 | Reroll |  | 5% |  | 0.05
1.3.2.1.5 | 1.3.2.1.5 | 1.3.2.1.5 | 1.3.2.1.5 | 1.3.2.1.5 | Nozzle fabrication (part 1) |  | 8% |  | 0.8
1.3.2.1.5.1 | 1.3.2.1.5.1 | 1.3.2.1.5.1 | 1.3.2.1.5.1 | 1.3.2.1.5.1 | Pipe cutting |  | 15% |  | 0.12
1.3.2.1.5.2 | 1.3.2.1.5.2 | 1.3.2.1.5.2 | 1.3.2.1.5.2 | 1.3.2.1.5.2 | Pipe beveling |  | 15% |  | 0.12
1.3.2.1.5.3 | 1.3.2.1.5.3 | 1.3.2.1.5.3 | 1.3.2.1.5.3 | 1.3.2.1.5.3 | Assembly pipe to flange |  | 25% |  | 0.2
1.3.2.1.5.4 | 1.3.2.1.5.4 | 1.3.2.1.5.4 | 1.3.2.1.5.4 | 1.3.2.1.5.4 | Welding pipe to flange |  | 45% |  | 0.36
1.3.2.1.6 | 1.3.2.1.6 | 1.3.2.1.6 | 1.3.2.1.6 | 1.3.2.1.6 | Nozzle fabrication (part 2) |  | 12% |  | 1.2
1.3.2.1.6.1 | 1.3.2.1.6.1 | 1.3.2.1.6.1 | 1.3.2.1.6.1 | 1.3.2.1.6.1 | Pipe cutting |  | 5% |  | 0.06
1.3.2.1.6.2 | 1.3.2.1.6.2 | 1.3.2.1.6.2 | 1.3.2.1.6.2 | 1.3.2.1.6.2 | Pipe beveling |  | 5% |  | 0.06
1.3.2.1.6.3 | 1.3.2.1.6.3 | 1.3.2.1.6.3 | 1.3.2.1.6.3 | 1.3.2.1.6.3 | Assembly pipe to flange |  | 15% |  | 0.18
1.3.2.1.6.4 | 1.3.2.1.6.4 | 1.3.2.1.6.4 | 1.3.2.1.6.4 | 1.3.2.1.6.4 | Welding pipe to flange |  | 35% |  | 0.42
1.3.2.1.6.5 | 1.3.2.1.6.5 | 1.3.2.1.6.5 | 1.3.2.1.6.5 | 1.3.2.1.6.5 | Assembly elbow to pipe |  | 10% |  | 0.12
1.3.2.1.6.6 | 1.3.2.1.6.6 | 1.3.2.1.6.6 | 1.3.2.1.6.6 | 1.3.2.1.6.6 | Welding elbow to pipe |  | 30% |  | 0.36
1.3.2.2 | 1.3.2.2 | 1.3.2.2 | 1.3.2.2 | 1.3.2.2 | Final assembly |  | 50% |  | 12.5
1.3.2.2.1 | 1.3.2.2.1 | 1.3.2.2.1 | 1.3.2.2.1 | 1.3.2.2.1 | Shell |  | 40% |  | 5
1.3.2.2.1.1 | 1.3.2.2.1.1 | 1.3.2.2.1.1 | 1.3.2.2.1.1 | 1.3.2.2.1.1 | Assembly shell segments (CW) |  | 12% |  | 0.6
1.3.2.2.1.2 | 1.3.2.2.1.2 | 1.3.2.2.1.2 | 1.3.2.2.1.2 | 1.3.2.2.1.2 | Welding shell segments (CW) |  | 27% |  | 1.35
1.3.2.2.1.3 | 1.3.2.2.1.3 | 1.3.2.2.1.3 | 1.3.2.2.1.3 | 1.3.2.2.1.3 | Opening for nozzle assembly |  | 5% |  | 0.25
1.3.2.2.1.4 | 1.3.2.2.1.4 | 1.3.2.2.1.4 | 1.3.2.2.1.4 | 1.3.2.2.1.4 | Nozzle assembly to shell |  | 5% |  | 0.25
1.3.2.2.1.5 | 1.3.2.2.1.5 | 1.3.2.2.1.5 | 1.3.2.2.1.5 | 1.3.2.2.1.5 | Nozzle welding to shell |  | 10% |  | 0.5
1.3.2.2.1.6 | 1.3.2.2.1.6 | 1.3.2.2.1.6 | 1.3.2.2.1.6 | 1.3.2.2.1.6 | Assembly head to shell |  | 3% |  | 0.15
1.3.2.2.1.7 | 1.3.2.2.1.7 | 1.3.2.2.1.7 | 1.3.2.2.1.7 | 1.3.2.2.1.7 | Welding head to shell |  | 7% |  | 0.35
1.3.2.2.1.8 | 1.3.2.2.1.8 | 1.3.2.2.1.8 | 1.3.2.2.1.8 | 1.3.2.2.1.8 | Assembly cone to shell |  | 3% |  | 0.15
1.3.2.2.1.9 | 1.3.2.2.1.9 | 1.3.2.2.1.9 | 1.3.2.2.1.9 | 1.3.2.2.1.9 | Welding cone to shell |  | 7% |  | 0.35
1.3.2.2.1.10 | 1.3.2.2.1.10 | 1.3.2.2.1.10 | 1.3.2.2.1.10 | 1.3.2.2.1.10 | Assembly segment shell to cone |  | 3% |  | 0.15
1.3.2.2.1.11 | 1.3.2.2.1.11 | 1.3.2.2.1.11 | 1.3.2.2.1.11 | 1.3.2.2.1.11 | Welding segment shell to cone |  | 8% |  | 0.4
1.3.2.2.1.12 | 1.3.2.2.1.12 | 1.3.2.2.1.12 | 1.3.2.2.1.12 | 1.3.2.2.1.12 | Assembly body flange to shell |  | 3% |  | 0.15
1.3.2.2.1.13 | 1.3.2.2.1.13 | 1.3.2.2.1.13 | 1.3.2.2.1.13 | 1.3.2.2.1.13 | Welding body flange to shell |  | 7% |  | 0.35
1.3.2.2.2 | 1.3.2.2.2 | 1.3.2.2.2 | 1.3.2.2.2 | 1.3.2.2.2 | Channel |  | 15% |  | 1.875
1.3.2.2.2.1 | 1.3.2.2.2.1 | 1.3.2.2.2.1 | 1.3.2.2.2.1 | 1.3.2.2.2.1 | Assembly head to channel |  | 10% |  | 0.1875
1.3.2.2.2.2 | 1.3.2.2.2.2 | 1.3.2.2.2.2 | 1.3.2.2.2.2 | 1.3.2.2.2.2 | Welding head to channel |  | 20% |  | 0.375
1.3.2.2.2.3 | 1.3.2.2.2.3 | 1.3.2.2.2.3 | 1.3.2.2.2.3 | 1.3.2.2.2.3 | Assembly body flange to channel |  | 10% |  | 0.1875
1.3.2.2.2.4 | 1.3.2.2.2.4 | 1.3.2.2.2.4 | 1.3.2.2.2.4 | 1.3.2.2.2.4 | Welding body flange to channel |  | 20% |  | 0.375
1.3.2.2.2.5 | 1.3.2.2.2.5 | 1.3.2.2.2.5 | 1.3.2.2.2.5 | 1.3.2.2.2.5 | Opening for nozzle assembly |  | 10% |  | 0.1875
1.3.2.2.2.6 | 1.3.2.2.2.6 | 1.3.2.2.2.6 | 1.3.2.2.2.6 | 1.3.2.2.2.6 | Assembly nozzle to channel |  | 10% |  | 0.1875
1.3.2.2.2.7 | 1.3.2.2.2.7 | 1.3.2.2.2.7 | 1.3.2.2.2.7 | 1.3.2.2.2.7 | Welding nozzle to channel |  | 20% |  | 0.375
1.3.2.2.3 | 1.3.2.2.3 | 1.3.2.2.3 | 1.3.2.2.3 | 1.3.2.2.3 | Bundle structure |  | 45% |  | 5.625
1.3.2.2.3.1 | 1.3.2.2.3.1 | 1.3.2.2.3.1 | 1.3.2.2.3.1 | 1.3.2.2.3.1 | Assembly bundle structure |  | 15% |  | 0.84375
1.3.2.2.3.2 | 1.3.2.2.3.2 | 1.3.2.2.3.2 | 1.3.2.2.3.2 | 1.3.2.2.3.2 | Insert tube to bundle structure |  | 10% |  | 0.5625
1.3.2.2.3.3 | 1.3.2.2.3.3 | 1.3.2.2.3.3 | 1.3.2.2.3.3 | 1.3.2.2.3.3 | Tube to tube sheet welding |  | 30% |  | 1.6875
1.3.2.2.3.4 | 1.3.2.2.3.4 | 1.3.2.2.3.4 | 1.3.2.2.3.4 | 1.3.2.2.3.4 | Expanding |  | 5% |  | 0.28125
1.3.2.2.3.5 | 1.3.2.2.3.5 | 1.3.2.2.3.5 | 1.3.2.2.3.5 | 1.3.2.2.3.5 | Insert bundle to shell |  | 2% |  | 0.1125
1.3.2.2.3.6 | 1.3.2.2.3.6 | 1.3.2.2.3.6 | 1.3.2.2.3.6 | 1.3.2.2.3.6 | Assembly tube sheet to shell |  | 5% |  | 0.28125
1.3.2.2.3.7 | 1.3.2.2.3.7 | 1.3.2.2.3.7 | 1.3.2.2.3.7 | 1.3.2.2.3.7 | Welding tube sheet to shell |  | 10% |  | 0.5625
1.3.2.2.3.8 | 1.3.2.2.3.8 | 1.3.2.2.3.8 | 1.3.2.2.3.8 | 1.3.2.2.3.8 | Assembly saddle to shell |  | 5% |  | 0.28125
1.3.2.2.3.9 | 1.3.2.2.3.9 | 1.3.2.2.3.9 | 1.3.2.2.3.9 | 1.3.2.2.3.9 | Welding saddle to shell |  | 10% |  | 0.5625
1.3.2.2.3.10 | 1.3.2.2.3.10 | 1.3.2.2.3.10 | 1.3.2.2.3.10 | 1.3.2.2.3.10 | Assembly external part to shell& channel |  | 2% |  | 0.1125
1.3.2.2.3.11 | 1.3.2.2.3.11 | 1.3.2.2.3.11 | 1.3.2.2.3.11 | 1.3.2.2.3.11 | Welding external part to shell& channel |  | 4% |  | 0.225
1.3.2.2.3.12 | 1.3.2.2.3.12 | 1.3.2.2.3.12 | 1.3.2.2.3.12 | 1.3.2.2.3.12 | Final NDT |  | 2% |  | 0.1125
1.3.2.3 | 1.3.2.3 | 1.3.2.3 | 1.3.2.3 | 1.3.2.3 | Test |  | 5% |  | 1.25
1.3.2.3.1 | 1.3.2.3.1 | 1.3.2.3.1 | 1.3.2.3.1 | 1.3.2.3.1 | Hydrostatic Test |  | 100% |  | 1.25
1.3.2.4 | 1.3.2.4 | 1.3.2.4 | 1.3.2.4 | 1.3.2.4 | Sandblast & paint |  | 5% |  | 1.25
1.3.2.4.1 | 1.3.2.4.1 | 1.3.2.4.1 | 1.3.2.4.1 | 1.3.2.4.1 | Sandblast |  | 50% |  | 0.625
1.3.2.4.2 | 1.3.2.4.2 | 1.3.2.4.2 | 1.3.2.4.2 | 1.3.2.4.2 | Painting |  | 50% |  | 0.625