## Cover
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: PROGRESS REPORT NO.04
|  |  |  | Rev.: R0 | Page 1 of 13
STYRENE PARK OFFSITE Document Title: PROGRESS REPORT NO.04
00 | 2024-11-09 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-10-26 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-10-01 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-09-14 | IFA | S.Baitar | H.Zahiri | H.Zahiri
Rev. | Issued Date | DESCRIPTION | PREPARED | CHECKED | APPROVED

## Drop Down List (hidden)
Methanol Production Plant 1100
Methanol Production Plant 1200
Methanol Production Plant 1100 & 1200
Air Separation Unit 1
Air Separation Unit 2
Air Separation Unit 3
Air Separation Unit 1 & 2
Air Separation Unit 1~3
Utilities
Olefin Via Methanol Plant 2100
Olefin Via Methanol Plant 2200
Olefin Via Methanol Plant 2100 & 2200
HDPE Production Plant 3100
HDPE Production Plant 3200
HDPE Production Plant 3100 & 3200
Polypropylene Production Plant 4100
Polypropylene Production Plant 4200
Polypropylene Production Plant 4100 & 4200
Non-Industrial Buildings

## PMS
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.04
WBS Level | WBS ID | WBS Level Description | Weight Factor | Weight Value | Cumulative
[5 empty] | Plan | Actual | Variance
1 | 1 | Shell & Tube Heat exchanger |  | 100 | 43.13% | 42.1% | -1.028%
2 | 1.1 | Engineering | 100% | 10 | 92% | 73.3% | -18.7%
3 | 1.1.1 | Vendor Print Index & Schedule (VPIS) | 3% | 0.3 | 100% | 100% | 0%
3 | 1.1.2 | Sub-Vendor List (SVL) | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.3 | Final vendor Data Book Index | 3% | 0.3 | 0% |  | 0%
3 | 1.1.4 | Final vendor Data Book | 5% | 0.5 | 0% |  | 0%
3 | 1.1.5 | HSE Plan | 4% | 0.4 | 100% | 100% | 0%
3 | 1.1.6 | WBS for Shell & Tube Heat Exchangers | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.7 | Time Schedule for Shell & Tube Heat Exchangers | 7% | 0.7 | 100% | 90% | -10%
3 | 1.1.8 | Monthly Progress Report for Shell & Tube Heat Exchangers | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.9 | As Built Drawing | 13% | 1.3 | 100% |  | -100%
3 | 1.1.10 | Inspection & Test Plan (ITP) | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.11 | Welding Document (WPS & PQR) | 8% | 0.8 | 100% | 100% | 0%
3 | 1.1.12 | Welding & NDT Map | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.13 | NDT Operator Qualification | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.14 | Welder Performance Qualification | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.15 | NDT Procedure (RT, UT, PT, MT) | 6% | 0.6 | 100% | 100% | 0%
3 | 1.1.16 | Hydrostatic Test Procedure | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.17 | Surface Preparation & Painting Procedure | 5% | 0.5 | 100% |  | -100%
2 | 1.2 | Procurement | 100% | 40 | 84.82% | 86.93% | 2.106%
3 | 1.2.1 | Plate | 23% | 9.2 | 88.7% | 88.7% | 0%
4 | 1.2.1.1 | PO placement | 25% | 2.3 | 100% | 100% | 0%
4 | 1.2.1.2 | Fabrication | 65% | 5.98 | 98% | 98% | 0%
4 | 1.2.1.3 | Shipping | 7% | 0.644 |  |  | 0%
4 | 1.2.1.4 | Custom clearance | 3% | 0.276 |  |  | 0%
3 | 1.2.2 | Head | 20% | 8 | 88.7% | 88.7% | 0%
4 | 1.2.2.1 | PO placement | 25% | 2 | 100% | 100% | 0%
4 | 1.2.2.2 | Fabrication | 65% | 5.2 | 98% | 98% | 0%
4 | 1.2.2.3 | Shipping | 7% | 0.56 |  |  | 0%
4 | 1.2.2.4 | Custom clearance | 3% | 0.24 |  |  | 0%
3 | 1.2.3 | U-Tube | 19% | 7.6 | 88.7% | 88.7% | 0%
4 | 1.2.3.1 | PO placement | 25% | 1.9 | 100% | 100% | 0%
4 | 1.2.3.2 | Fabrication | 65% | 4.94 | 98% | 98% | 0%
4 | 1.2.3.3 | Shipping | 7% | 0.532 |  |  | 0%
4 | 1.2.3.4 | Custom clearance | 3% | 0.228 |  |  | 0%
3 | 1.2.4 | Tube sheet | 7% | 2.8 | 77% | 88.7% | 11.7%
4 | 1.2.4.1 | PO placement | 25% | 0.7 | 100% | 100% | 0%
4 | 1.2.4.2 | Fabrication | 65% | 1.82 | 80% | 98% | 18%
4 | 1.2.4.3 | Shipping | 7% | 0.196 |  |  | 0%
4 | 1.2.4.4 | Custom clearance | 3% | 0.084 |  |  | 0%
3 | 1.2.5 | Baffle | 5% | 2 | 77% | 88.7% | 11.7%
4 | 1.2.5.1 | PO placement | 25% | 0.5 | 100% | 100% | 0%
4 | 1.2.5.2 | Fabrication | 65% | 1.3 | 80% | 98% | 18%
4 | 1.2.5.3 | Shipping | 7% | 0.14 |  |  | 0%
4 | 1.2.5.4 | Custom clearance | 3% | 0.06 |  |  | 0%
3 | 1.2.6 | Elbow | 2% | 0.8 | 88.7% | 88.7% | 0%
4 | 1.2.6.1 | PO placement | 25% | 0.2 | 100% | 100% | 0%
4 | 1.2.6.2 | Fabrication | 65% | 0.52 | 98% | 98% | 0%
4 | 1.2.6.3 | Shipping | 7% | 0.056 |  |  | 0%
4 | 1.2.6.4 | Custom clearance | 3% | 0.024 |  |  | 0%
3 | 1.2.7 | Pipe | 9% | 3.6 | 88.7% | 88.7% | 0%
4 | 1.2.7.1 | PO placement | 25% | 0.9 | 100% | 100% | 0%
4 | 1.2.7.2 | Fabrication | 65% | 2.34 | 98% | 98% | 0%
4 | 1.2.7.3 | Shipping | 7% | 0.252 |  |  | 0%
4 | 1.2.7.4 | Custom clearance | 3% | 0.108 |  |  | 0%
3 | 1.2.8 | Flange | 7% | 2.8 | 88.7% | 88.7% | 0%
4 | 1.2.8.1 | PO placement | 25% | 0.7 | 100% | 100% | 0%
4 | 1.2.8.2 | Fabrication | 65% | 1.82 | 98% | 98% | 0%
4 | 1.2.8.3 | Shipping | 7% | 0.196 |  |  | 0%
4 | 1.2.8.4 | Custom clearance | 3% | 0.084 |  |  | 0%
3 | 1.2.9 | Spacer | 3% | 1.2 | 77% | 88.7% | 11.7%
4 | 1.2.9.1 | PO placement | 25% | 0.3 | 100% | 100% | 0%
4 | 1.2.9.2 | Fabrication | 65% | 0.78 | 80% | 98% | 18%
4 | 1.2.9.3 | Shipping | 7% | 0.084 |  |  | 0%
4 | 1.2.9.4 | Custom clearance | 3% | 0.036 |  |  | 0%
3 | 1.2.10 | Nut & bolt | 2% | 0.8 | 77% | 88.7% | 11.7%
4 | 1.2.10.1 | PO placement | 25% | 0.2 | 100% | 100% | 0%
4 | 1.2.10.2 | Fabrication | 65% | 0.52 | 80% | 98% | 18%
4 | 1.2.10.3 | Shipping | 7% | 0.056 |  |  | 0%
4 | 1.2.10.4 | Custom clearance | 3% | 0.024 |  |  | 0%
3 | 1.2.11 | Gasket | 1% | 0.4 | 77% | 88.7% | 11.7%
4 | 1.2.11.1 | PO placement | 25% | 0.1 | 100% | 100% | 0%
4 | 1.2.11.2 | Fabrication | 65% | 0.26 | 80% | 98% | 18%
4 | 1.2.11.3 | Shipping | 7% | 0.028 |  |  | 0%
4 | 1.2.11.4 | Custom clearance | 3% | 0.012 |  |  | 0%
3 | 1.2.12 | Paint | 1% | 0.4 | 0% | 0% | 0%
4 | 1.2.12.1 | PO placement | 25% | 0.1 |  |  | 0%
4 | 1.2.12.2 | Fabrication | 65% | 0.26 |  |  | 0%
4 | 1.2.12.3 | Shipping | 7% | 0.028 |  |  | 0%
4 | 1.2.12.4 | Custom clearance | 3% | 0.012 |  |  | 0%
3 | 1.2.13 | Name plate | 1% | 0.4 | 0% | 0% | 0%
4 | 1.2.13.1 | PO placement | 25% | 0.1 |  |  | 0%
4 | 1.2.13.2 | Fabrication | 65% | 0.26 |  |  | 0%
4 | 1.2.13.3 | Shipping | 7% | 0.028 |  |  | 0%
4 | 1.2.13.4 | Custom clearance | 3% | 0.012 |  |  | 0%
2 | 1.3 | Fabrication | 100% | 50 |  |  | 0%
3 | 1.3.1 | RU-0001A-E-02 | 50% | 25 |  |  | 0%
4 | 1.3.1.1 | Prefabrication | 40% | 10 |  |  | 0%
5 | 1.3.1.1.1 | Shell | 35% | 3.5 |  |  | 0%
6 | 1.3.1.1.1.1 | Cutting | 10% | 0.35 |  |  | 0%
6 | 1.3.1.1.1.2 | Beveling | 10% | 0.35 |  |  | 0%
6 | 1.3.1.1.1.3 | Rolling | 15% | 0.525 |  |  | 0%
6 | 1.3.1.1.1.4 | Assembly (LW) | 25% | 0.875 |  |  | 0%
6 | 1.3.1.1.1.5 | Welding (LW) | 35% | 1.225 |  |  | 0%
6 | 1.3.1.1.1.6 | Reroll | 5% | 0.175 |  |  | 0%
5 | 1.3.1.1.2 | Channel | 15% | 1.5 |  |  | 0%
6 | 1.3.1.1.2.1 | Cutting | 10% | 0.15 |  |  | 0%
6 | 1.3.1.1.2.2 | Beveling | 10% | 0.15 |  |  | 0%
6 | 1.3.1.1.2.3 | Rolling | 15% | 0.225 |  |  | 0%
6 | 1.3.1.1.2.4 | Assembly (LW) | 25% | 0.375 |  |  | 0%
6 | 1.3.1.1.2.5 | Welding (LW) | 35% | 0.525 |  |  | 0%
6 | 1.3.1.1.2.6 | Reroll | 5% | 0.075 |  |  | 0%
5 | 1.3.1.1.3 | Cone | 20% | 2 |  |  | 0%
6 | 1.3.1.1.3.1 | Cutting | 10% | 0.2 |  |  | 0%
6 | 1.3.1.1.3.2 | Beveling | 10% | 0.2 |  |  | 0%
6 | 1.3.1.1.3.3 | Rolling | 15% | 0.3 |  |  | 0%
6 | 1.3.1.1.3.4 | Assembly (LW) | 25% | 0.5 |  |  | 0%
6 | 1.3.1.1.3.5 | Welding (LW) | 35% | 0.7 |  |  | 0%
6 | 1.3.1.1.3.6 | Reroll | 5% | 0.1 |  |  | 0%
5 | 1.3.1.1.4 | Saddle fabrication | 10% | 1 |  |  | 0%
6 | 1.3.1.1.4.1 | Cutting | 10% | 0.1 |  |  | 0%
6 | 1.3.1.1.4.2 | Beveling | 10% | 0.1 |  |  | 0%
6 | 1.3.1.1.4.3 | Rolling | 15% | 0.15 |  |  | 0%
6 | 1.3.1.1.4.4 | Assembly (LW) | 25% | 0.25 |  |  | 0%
6 | 1.3.1.1.4.5 | Welding (LW) | 35% | 0.35 |  |  | 0%
6 | 1.3.1.1.4.6 | Reroll | 5% | 0.05 |  |  | 0%
5 | 1.3.1.1.5 | Nozzle fabrication (part 1) | 8% | 0.8 |  |  | 0%
6 | 1.3.1.1.5.1 | Pipe cutting | 15% | 0.12 |  |  | 0%
6 | 1.3.1.1.5.2 | Pipe beveling | 15% | 0.12 |  |  | 0%
6 | 1.3.1.1.5.3 | Assembly pipe to flange | 25% | 0.2 |  |  | 0%
6 | 1.3.1.1.5.4 | Welding pipe to flange | 45% | 0.36 |  |  | 0%
5 | 1.3.1.1.6 | Nozzle fabrication (part 2) | 12% | 1.2 |  |  | 0%
6 | 1.3.1.1.6.1 | Pipe cutting | 5% | 0.06 |  |  | 0%
6 | 1.3.1.1.6.2 | Pipe beveling | 5% | 0.06 |  |  | 0%
6 | 1.3.1.1.6.3 | Assembly pipe to flange | 15% | 0.18 |  |  | 0%
6 | 1.3.1.1.6.4 | Welding pipe to flange | 35% | 0.42 |  |  | 0%
6 | 1.3.1.1.6.5 | Assembly elbow to pipe | 10% | 0.12 |  |  | 0%
6 | 1.3.1.1.6.6 | Welding elbow to pipe | 30% | 0.36 |  |  | 0%
4 | 1.3.1.2 | Final assembly | 50% | 12.5 |  |  | 0%
5 | 1.3.1.2.1 | Shell | 40% | 5 |  |  | 0%
6 | 1.3.1.2.1.1 | Assembly shell segments (CW) | 12% | 0.6 |  |  | 0%
6 | 1.3.1.2.1.2 | Welding shell segments (CW) | 27% | 1.35 |  |  | 0%
6 | 1.3.1.2.1.3 | Opening for nozzle assembly | 5% | 0.25 |  |  | 0%
6 | 1.3.1.2.1.4 | Nozzle assembly to shell | 5% | 0.25 |  |  | 0%
6 | 1.3.1.2.1.5 | Nozzle welding to shell | 10% | 0.5 |  |  | 0%
6 | 1.3.1.2.1.6 | Assembly head to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.7 | Welding head to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.1.2.1.8 | Assembly cone to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.9 | Welding cone to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.1.2.1.10 | Assembly segment shell to cone | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.11 | Welding segment shell to cone | 8% | 0.4 |  |  | 0%
6 | 1.3.1.2.1.12 | Assembly body flange to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.13 | Welding body flange to shell | 7% | 0.35 |  |  | 0%
5 | 1.3.1.2.2 | Channel | 15% | 1.875 |  |  | 0%
6 | 1.3.1.2.2.1 | Assembly head to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.2 | Welding head to channel | 20% | 0.375 |  |  | 0%
6 | 1.3.1.2.2.3 | Assembly body flange to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.4 | Welding body flange to channel | 20% | 0.375 |  |  | 0%
6 | 1.3.1.2.2.5 | Opening for nozzle assembly | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.6 | Assembly nozzle to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.7 | Welding nozzle to channel | 20% | 0.375 |  |  | 0%
5 | 1.3.1.2.3 | Bundle structure | 45% | 5.625 |  |  | 0%
6 | 1.3.1.2.3.1 | Assembly bundle structure | 15% | 0.84375 |  |  | 0%
6 | 1.3.1.2.3.2 | Insert tube to bundle structure | 10% | 0.5625 |  |  | 0%
6 | 1.3.1.2.3.3 | Tube to tube sheet welding | 30% | 1.6875 |  |  | 0%
6 | 1.3.1.2.3.4 | Expanding | 5% | 0.28125 |  |  | 0%
6 | 1.3.1.2.3.5 | Insert bundle to shell | 2% | 0.1125 |  |  | 0%
6 | 1.3.1.2.3.6 | Assembly tube sheet to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.1.2.3.7 | Welding tube sheet to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.1.2.3.8 | Assembly saddle to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.1.2.3.9 | Welding saddle to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.1.2.3.10 | Assembly external part to shell& channel | 2% | 0.1125 |  |  | 0%
6 | 1.3.1.2.3.11 | Welding external part to shell& channel | 4% | 0.225 |  |  | 0%
6 | 1.3.1.2.3.12 | Final NDT | 2% | 0.1125 |  |  | 0%
4 | 1.3.1.3 | Test | 5% | 1.25 |  |  | 0%
5 | 1.3.1.3.1 | Hydrostatic Test | 100% | 1.25 |  |  | 0%
4 | 1.3.1.4 | Sandblast & paint | 5% | 1.25 |  |  | 0%
5 | 1.3.1.4.1 | Sandblast | 50% | 0.625 |  |  | 0%
5 | 1.3.1.4.2 | Painting | 50% | 0.625 |  |  | 0%
3 | 1.3.2 | RU-0001A-E-02 | 50% | 25 |  |  | 0%
4 | 1.3.2.1 | Prefabrication | 40% | 10 |  |  | 0%
5 | 1.3.2.1.1 | Shell | 35% | 3.5 |  |  | 0%
6 | 1.3.2.1.1.1 | Cutting | 10% | 0.35 |  |  | 0%
6 | 1.3.2.1.1.2 | Beveling | 10% | 0.35 |  |  | 0%
6 | 1.3.2.1.1.3 | Rolling | 15% | 0.525 |  |  | 0%
6 | 1.3.2.1.1.4 | Assembly (LW) | 25% | 0.875 |  |  | 0%
6 | 1.3.2.1.1.5 | Welding (LW) | 35% | 1.225 |  |  | 0%
6 | 1.3.2.1.1.6 | Reroll | 5% | 0.175 |  |  | 0%
5 | 1.3.2.1.2 | Channel | 15% | 1.5 |  |  | 0%
6 | 1.3.2.1.2.1 | Cutting | 10% | 0.15 |  |  | 0%
6 | 1.3.2.1.2.2 | Beveling | 10% | 0.15 |  |  | 0%
6 | 1.3.2.1.2.3 | Rolling | 15% | 0.225 |  |  | 0%
6 | 1.3.2.1.2.4 | Assembly (LW) | 25% | 0.375 |  |  | 0%
6 | 1.3.2.1.2.5 | Welding (LW) | 35% | 0.525 |  |  | 0%
6 | 1.3.2.1.2.6 | Reroll | 5% | 0.075 |  |  | 0%
5 | 1.3.2.1.3 | Cone | 20% | 2 |  |  | 0%
6 | 1.3.2.1.3.1 | Cutting | 10% | 0.2 |  |  | 0%
6 | 1.3.2.1.3.2 | Beveling | 10% | 0.2 |  |  | 0%
6 | 1.3.2.1.3.3 | Rolling | 15% | 0.3 |  |  | 0%
6 | 1.3.2.1.3.4 | Assembly (LW) | 25% | 0.5 |  |  | 0%
6 | 1.3.2.1.3.5 | Welding (LW) | 35% | 0.7 |  |  | 0%
6 | 1.3.2.1.3.6 | Reroll | 5% | 0.1 |  |  | 0%
5 | 1.3.2.1.4 | Saddle fabrication | 10% | 1 |  |  | 0%
6 | 1.3.2.1.4.1 | Cutting | 10% | 0.1 |  |  | 0%
6 | 1.3.2.1.4.2 | Beveling | 10% | 0.1 |  |  | 0%
6 | 1.3.2.1.4.3 | Rolling | 15% | 0.15 |  |  | 0%
6 | 1.3.2.1.4.4 | Assembly (LW) | 25% | 0.25 |  |  | 0%
6 | 1.3.2.1.4.5 | Welding (LW) | 35% | 0.35 |  |  | 0%
6 | 1.3.2.1.4.6 | Reroll | 5% | 0.05 |  |  | 0%
5 | 1.3.2.1.5 | Nozzle fabrication (part 1) | 8% | 0.8 |  |  | 0%
6 | 1.3.2.1.5.1 | Pipe cutting | 15% | 0.12 |  |  | 0%
6 | 1.3.2.1.5.2 | Pipe beveling | 15% | 0.12 |  |  | 0%
6 | 1.3.2.1.5.3 | Assembly pipe to flange | 25% | 0.2 |  |  | 0%
6 | 1.3.2.1.5.4 | Welding pipe to flange | 45% | 0.36 |  |  | 0%
5 | 1.3.2.1.6 | Nozzle fabrication (part 2) | 12% | 1.2 |  |  | 0%
6 | 1.3.2.1.6.1 | Pipe cutting | 5% | 0.06 |  |  | 0%
6 | 1.3.2.1.6.2 | Pipe beveling | 5% | 0.06 |  |  | 0%
6 | 1.3.2.1.6.3 | Assembly pipe to flange | 15% | 0.18 |  |  | 0%
6 | 1.3.2.1.6.4 | Welding pipe to flange | 35% | 0.42 |  |  | 0%
6 | 1.3.2.1.6.5 | Assembly elbow to pipe | 10% | 0.12 |  |  | 0%
6 | 1.3.2.1.6.6 | Welding elbow to pipe | 30% | 0.36 |  |  | 0%
4 | 1.3.2.2 | Final assembly | 50% | 12.5 |  |  | 0%
5 | 1.3.2.2.1 | Shell | 40% | 5 |  |  | 0%
6 | 1.3.2.2.1.1 | Assembly shell segments (CW) | 12% | 0.6 |  |  | 0%
6 | 1.3.2.2.1.2 | Welding shell segments (CW) | 27% | 1.35 |  |  | 0%
6 | 1.3.2.2.1.3 | Opening for nozzle assembly | 5% | 0.25 |  |  | 0%
6 | 1.3.2.2.1.4 | Nozzle assembly to shell | 5% | 0.25 |  |  | 0%
6 | 1.3.2.2.1.5 | Nozzle welding to shell | 10% | 0.5 |  |  | 0%
6 | 1.3.2.2.1.6 | Assembly head to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.7 | Welding head to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.2.2.1.8 | Assembly cone to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.9 | Welding cone to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.2.2.1.10 | Assembly segment shell to cone | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.11 | Welding segment shell to cone | 8% | 0.4 |  |  | 0%
6 | 1.3.2.2.1.12 | Assembly body flange to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.13 | Welding body flange to shell | 7% | 0.35 |  |  | 0%
5 | 1.3.2.2.2 | Channel | 15% | 1.875 |  |  | 0%
6 | 1.3.2.2.2.1 | Assembly head to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.2 | Welding head to channel | 20% | 0.375 |  |  | 0%
6 | 1.3.2.2.2.3 | Assembly body flange to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.4 | Welding body flange to channel | 20% | 0.375 |  |  | 0%
6 | 1.3.2.2.2.5 | Opening for nozzle assembly | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.6 | Assembly nozzle to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.7 | Welding nozzle to channel | 20% | 0.375 |  |  | 0%
5 | 1.3.2.2.3 | Bundle structure | 45% | 5.625 |  |  | 0%
6 | 1.3.2.2.3.1 | Assembly bundle structure | 15% | 0.84375 |  |  | 0%
6 | 1.3.2.2.3.2 | Insert tube to bundle structure | 10% | 0.5625 |  |  | 0%
6 | 1.3.2.2.3.3 | Tube to tube sheet welding | 30% | 1.6875 |  |  | 0%
6 | 1.3.2.2.3.4 | Expanding | 5% | 0.28125 |  |  | 0%
6 | 1.3.2.2.3.5 | Insert bundle to shell | 2% | 0.1125 |  |  | 0%
6 | 1.3.2.2.3.6 | Assembly tube sheet to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.2.2.3.7 | Welding tube sheet to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.2.2.3.8 | Assembly saddle to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.2.2.3.9 | Welding saddle to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.2.2.3.10 | Assembly external part to shell& channel | 2% | 0.1125 |  |  | 0%
6 | 1.3.2.2.3.11 | Welding external part to shell& channel | 4% | 0.225 |  |  | 0%
6 | 1.3.2.2.3.12 | Final NDT | 2% | 0.1125 |  |  | 0%
4 | 1.3.2.3 | Test | 5% | 1.25 |  |  | 0%
5 | 1.3.2.3.1 | Hydrostatic Test | 100% | 1.25 |  |  | 0%
4 | 1.3.2.4 | Sandblast & paint | 5% | 1.25 |  |  | 0%
5 | 1.3.2.4.1 | Sandblast | 50% | 0.625 |  |  | 0%
5 | 1.3.2.4.2 | Painting | 50% | 0.625 |  |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Contractual Info.
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.04
This Period Highlights: |  |  | Fabrication process for all materials have been finished and ready for inspection. Notice for inspection in Korea will be issued as soon as possible.
Forcasted activities for the next report period: |  | Sending for Surface Preparation & Painting Procedure will be issued.
Overall Progress Table
Phase |  | Weight Factor | Cumulative up to Last Period |  | This Period |  | Cumulative up to End of This Period
|  |  | Plan | Actual | Plan | Actual | Plan | Actual | Variance
Engineering |  | 10% | 92% | 71.6% | 0% | 1.7% | 92% | 73.3% | -18.7%
Material Supply |  | 40% | 75.62% | 75.71% | 9.204% | 11.21% | 84.82% | 86.93% | 2.106%
Manufacturing |  | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total |  | 100% | 39.45% | 37.45% | 3.682% | 4.655% | 43.13% | 42.1% | -1.028%

## S-Curve
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.04
S-Curve
Interval | 2024-07-15 | 2024-07-31 | 2024-08-15 | 2024-08-31 | 2024-09-14 | 2024-10-01 | 2024-10-26 | 2024-11-15 | 2024-11-30 | 2024-12-15 | 2024-12-31 | 2025-01-15 | 2025-01-31 | 2025-02-15 | 2025-01-31
Cumulative Plan | 0.003167% | 6.67% | 15.4% | 20.92% | 26% | 32% | 39% | 43.13% | 46.5% | 54.46% | 67.66% | 77.17% | 85.94% | 93.61% | 100%
Periodic Plan | 0.003167% | 6.667% | 8.73% | 5.52% | 5.08% | 6% | 7% | 4.13% | 3.37% | 7.96% | 13.2% | 9.51% | 8.77% | 7.67% | 6.39%
Cumulative Actual | 0.5% | 2% | 5% | 12% | 16.4% | 23.5% | 37.4% | 42.1%
Periodic Actual | 0.5% | 1.5% | 3% | 7% | 4.4% | 7.1% | 13.9% | 4.7% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Pictures
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.04
P.O. Number:
P.O. Description:
Raw Material / Fabrication Pictures