## Cover
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title: PROGRESS REPORT NO.06
|  |  |  | Rev.: R0 | Page 1 of 9
STYRENE PARK OFFSITE Document Title: PROGRESS REPORT NO.06
00 | 2025-01-25 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-12-16 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-11-09 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-10-26 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-10-01 | IFA | S.Baitar | H.Zahiri | H.Zahiri
00 | 2024-09-14 | IFA | S.Baitar | H.Zahiri | H.Zahiri
Rev. | Issued Date | DESCRIPTION | PREPARED | CHECKED | APPROVED

## Drop Down List (hidden)
Methanol Production Plant 1100
Methanol Production Plant 1200
Methanol Production Plant 1100 & 1200
Air Separation Unit 1
Air Separation Unit 2
Air Separation Unit 3
Air Separation Unit 1 & 2
Air Separation Unit 1~3
Utilities
Olefin Via Methanol Plant 2100
Olefin Via Methanol Plant 2200
Olefin Via Methanol Plant 2100 & 2200
HDPE Production Plant 3100
HDPE Production Plant 3200
HDPE Production Plant 3100 & 3200
Polypropylene Production Plant 4100
Polypropylene Production Plant 4200
Polypropylene Production Plant 4100 & 4200
Non-Industrial Buildings

## PMS
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.06
WBS Level | WBS ID | WBS Level Description | Weight Factor | Weight Value | Cumulative
[5 empty] | Plan | Actual | Variance
1 | 1 | Shell & Tube Heat exchanger |  | 100 | 76.64% | 45.29% | -31.35%
2 | 1.1 | Engineering | 100% | 10 | 100% | 74% | -26%
3 | 1.1.1 | Vendor Print Index & Schedule (VPIS) | 3% | 0.3 | 100% | 100% | 0%
3 | 1.1.2 | Sub-Vendor List (SVL) | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.3 | Final vendor Data Book Index | 3% | 0.3 | 100% |  | -100%
3 | 1.1.4 | Final vendor Data Book | 5% | 0.5 | 100% |  | -100%
3 | 1.1.5 | HSE Plan | 4% | 0.4 | 100% | 100% | 0%
3 | 1.1.6 | WBS for Shell & Tube Heat Exchangers | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.7 | Time Schedule for Shell & Tube Heat Exchangers | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.8 | Monthly Progress Report for Shell & Tube Heat Exchangers | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.9 | As Built Drawing | 13% | 1.3 | 100% |  | -100%
3 | 1.1.10 | Inspection & Test Plan (ITP) | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.11 | Welding Document (WPS & PQR) | 8% | 0.8 | 100% | 100% | 0%
3 | 1.1.12 | Welding & NDT Map | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.13 | NDT Operator Qualification | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.14 | Welder Performance Qualification | 5% | 0.5 | 100% | 100% | 0%
3 | 1.1.15 | NDT Procedure (RT, UT, PT, MT) | 6% | 0.6 | 100% | 100% | 0%
3 | 1.1.16 | Hydrostatic Test Procedure | 7% | 0.7 | 100% | 100% | 0%
3 | 1.1.17 | Surface Preparation & Painting Procedure | 5% | 0.5 | 100% |  | -100%
2 | 1.2 | Procurement | 100% | 40 | 100% | 94.72% | -5.283%
3 | 1.2.1 | Plate | 23% | 9.2 | 100% | 96.65% | -3.35%
4 | 1.2.1.1 | PO placement | 25% | 2.3 | 100% | 100% | 0%
4 | 1.2.1.2 | Fabrication | 65% | 5.98 | 100% | 100% | 0%
4 | 1.2.1.3 | Shipping | 7% | 0.644 | 100% | 95% | -5%
4 | 1.2.1.4 | Custom clearance | 3% | 0.276 | 100% |  | -100%
3 | 1.2.2 | Head | 20% | 8 | 100% | 96.65% | -3.35%
4 | 1.2.2.1 | PO placement | 25% | 2 | 100% | 100% | 0%
4 | 1.2.2.2 | Fabrication | 65% | 5.2 | 100% | 100% | 0%
4 | 1.2.2.3 | Shipping | 7% | 0.56 | 100% | 95% | -5%
4 | 1.2.2.4 | Custom clearance | 3% | 0.24 | 100% |  | -100%
3 | 1.2.3 | U-Tube | 19% | 7.6 | 100% | 96.65% | -3.35%
4 | 1.2.3.1 | PO placement | 25% | 1.9 | 100% | 100% | 0%
4 | 1.2.3.2 | Fabrication | 65% | 4.94 | 100% | 100% | 0%
4 | 1.2.3.3 | Shipping | 7% | 0.532 | 100% | 95% | -5%
4 | 1.2.3.4 | Custom clearance | 3% | 0.228 | 100% |  | -100%
3 | 1.2.4 | Tube sheet | 7% | 2.8 | 100% | 96.65% | -3.35%
4 | 1.2.4.1 | PO placement | 25% | 0.7 | 100% | 100% | 0%
4 | 1.2.4.2 | Fabrication | 65% | 1.82 | 100% | 100% | 0%
4 | 1.2.4.3 | Shipping | 7% | 0.196 | 100% | 95% | -5%
4 | 1.2.4.4 | Custom clearance | 3% | 0.084 | 100% |  | -100%
3 | 1.2.5 | Baffle | 5% | 2 | 100% | 96.65% | -3.35%
4 | 1.2.5.1 | PO placement | 25% | 0.5 | 100% | 100% | 0%
4 | 1.2.5.2 | Fabrication | 65% | 1.3 | 100% | 100% | 0%
4 | 1.2.5.3 | Shipping | 7% | 0.14 | 100% | 95% | -5%
4 | 1.2.5.4 | Custom clearance | 3% | 0.06 | 100% |  | -100%
3 | 1.2.6 | Elbow | 2% | 0.8 | 100% | 96.65% | -3.35%
4 | 1.2.6.1 | PO placement | 25% | 0.2 | 100% | 100% | 0%
4 | 1.2.6.2 | Fabrication | 65% | 0.52 | 100% | 100% | 0%
4 | 1.2.6.3 | Shipping | 7% | 0.056 | 100% | 95% | -5%
4 | 1.2.6.4 | Custom clearance | 3% | 0.024 | 100% |  | -100%
3 | 1.2.7 | Pipe | 9% | 3.6 | 100% | 96.65% | -3.35%
4 | 1.2.7.1 | PO placement | 25% | 0.9 | 100% | 100% | 0%
4 | 1.2.7.2 | Fabrication | 65% | 2.34 | 100% | 100% | 0%
4 | 1.2.7.3 | Shipping | 7% | 0.252 | 100% | 95% | -5%
4 | 1.2.7.4 | Custom clearance | 3% | 0.108 | 100% |  | -100%
3 | 1.2.8 | Flange | 7% | 2.8 | 100% | 96.65% | -3.35%
4 | 1.2.8.1 | PO placement | 25% | 0.7 | 100% | 100% | 0%
4 | 1.2.8.2 | Fabrication | 65% | 1.82 | 100% | 100% | 0%
4 | 1.2.8.3 | Shipping | 7% | 0.196 | 100% | 95% | -5%
4 | 1.2.8.4 | Custom clearance | 3% | 0.084 | 100% |  | -100%
3 | 1.2.9 | Spacer | 3% | 1.2 | 100% | 96.65% | -3.35%
4 | 1.2.9.1 | PO placement | 25% | 0.3 | 100% | 100% | 0%
4 | 1.2.9.2 | Fabrication | 65% | 0.78 | 100% | 100% | 0%
4 | 1.2.9.3 | Shipping | 7% | 0.084 | 100% | 95% | -5%
4 | 1.2.9.4 | Custom clearance | 3% | 0.036 | 100% |  | -100%
3 | 1.2.10 | Nut & bolt | 2% | 0.8 | 100% | 96.65% | -3.35%
4 | 1.2.10.1 | PO placement | 25% | 0.2 | 100% | 100% | 0%
4 | 1.2.10.2 | Fabrication | 65% | 0.52 | 100% | 100% | 0%
4 | 1.2.10.3 | Shipping | 7% | 0.056 | 100% | 95% | -5%
4 | 1.2.10.4 | Custom clearance | 3% | 0.024 | 100% |  | -100%
3 | 1.2.11 | Gasket | 1% | 0.4 | 100% | 96.65% | -3.35%
4 | 1.2.11.1 | PO placement | 25% | 0.1 | 100% | 100% | 0%
4 | 1.2.11.2 | Fabrication | 65% | 0.26 | 100% | 100% | 0%
4 | 1.2.11.3 | Shipping | 7% | 0.028 | 100% | 95% | -5%
4 | 1.2.11.4 | Custom clearance | 3% | 0.012 | 100% |  | -100%
3 | 1.2.12 | Paint | 1% | 0.4 | 100% | 0% | -100%
4 | 1.2.12.1 | PO placement | 25% | 0.1 | 100% |  | -100%
4 | 1.2.12.2 | Fabrication | 65% | 0.26 | 100% |  | -100%
4 | 1.2.12.3 | Shipping | 7% | 0.028 | 100% |  | -100%
4 | 1.2.12.4 | Custom clearance | 3% | 0.012 | 100% |  | -100%
3 | 1.2.13 | Name plate | 1% | 0.4 | 100% | 0% | -100%
4 | 1.2.13.1 | PO placement | 25% | 0.1 | 100% |  | -100%
4 | 1.2.13.2 | Fabrication | 65% | 0.26 | 100% |  | -100%
4 | 1.2.13.3 | Shipping | 7% | 0.028 | 100% |  | -100%
4 | 1.2.13.4 | Custom clearance | 3% | 0.012 | 100% |  | -100%
2 | 1.3 | Fabrication | 100% | 50 | 53.28% |  | -53.28%
3 | 1.3.1 | RU-0001A-E-02 | 50% | 25 | 53.63% |  | -53.63%
4 | 1.3.1.1 | Prefabrication | 40% | 10 | 73% |  | -73%
5 | 1.3.1.1.1 | Shell | 35% | 3.5 | 100% |  | -100%
6 | 1.3.1.1.1.1 | Cutting | 10% | 0.35 | 100% |  | -100%
6 | 1.3.1.1.1.2 | Beveling | 10% | 0.35 | 100% |  | -100%
6 | 1.3.1.1.1.3 | Rolling | 15% | 0.525 | 100% |  | -100%
6 | 1.3.1.1.1.4 | Assembly (LW) | 25% | 0.875 | 100% |  | -100%
6 | 1.3.1.1.1.5 | Welding (LW) | 35% | 1.225 | 100% |  | -100%
6 | 1.3.1.1.1.6 | Reroll | 5% | 0.175 | 100% |  | -100%
5 | 1.3.1.1.2 | Channel | 15% | 1.5 | 60% |  | -60%
6 | 1.3.1.1.2.1 | Cutting | 10% | 0.15 | 100% |  | -100%
6 | 1.3.1.1.2.2 | Beveling | 10% | 0.15 | 100% |  | -100%
6 | 1.3.1.1.2.3 | Rolling | 15% | 0.225 | 100% |  | -100%
6 | 1.3.1.1.2.4 | Assembly (LW) | 25% | 0.375 | 100% |  | -100%
6 | 1.3.1.1.2.5 | Welding (LW) | 35% | 0.525 |  |  | 0%
6 | 1.3.1.1.2.6 | Reroll | 5% | 0.075 |  |  | 0%
5 | 1.3.1.1.3 | Cone | 20% | 2 | 35% |  | -35%
6 | 1.3.1.1.3.1 | Cutting | 10% | 0.2 | 100% |  | -100%
6 | 1.3.1.1.3.2 | Beveling | 10% | 0.2 | 100% |  | -100%
6 | 1.3.1.1.3.3 | Rolling | 15% | 0.3 | 100% |  | -100%
6 | 1.3.1.1.3.4 | Assembly (LW) | 25% | 0.5 |  |  | 0%
6 | 1.3.1.1.3.5 | Welding (LW) | 35% | 0.7 |  |  | 0%
6 | 1.3.1.1.3.6 | Reroll | 5% | 0.1 |  |  | 0%
5 | 1.3.1.1.4 | Saddle fabrication | 10% | 1 | 20% |  | -20%
6 | 1.3.1.1.4.1 | Cutting | 10% | 0.1 | 100% |  | -100%
6 | 1.3.1.1.4.2 | Beveling | 10% | 0.1 | 100% |  | -100%
6 | 1.3.1.1.4.3 | Rolling | 15% | 0.15 |  |  | 0%
6 | 1.3.1.1.4.4 | Assembly (LW) | 25% | 0.25 |  |  | 0%
6 | 1.3.1.1.4.5 | Welding (LW) | 35% | 0.35 |  |  | 0%
6 | 1.3.1.1.4.6 | Reroll | 5% | 0.05 |  |  | 0%
5 | 1.3.1.1.5 | Nozzle fabrication (part 1) | 8% | 0.8 | 100% |  | -100%
6 | 1.3.1.1.5.1 | Pipe cutting | 15% | 0.12 | 100% |  | -100%
6 | 1.3.1.1.5.2 | Pipe beveling | 15% | 0.12 | 100% |  | -100%
6 | 1.3.1.1.5.3 | Assembly pipe to flange | 25% | 0.2 | 100% |  | -100%
6 | 1.3.1.1.5.4 | Welding pipe to flange | 45% | 0.36 | 100% |  | -100%
5 | 1.3.1.1.6 | Nozzle fabrication (part 2) | 12% | 1.2 | 100% |  | -100%
6 | 1.3.1.1.6.1 | Pipe cutting | 5% | 0.06 | 100% |  | -100%
6 | 1.3.1.1.6.2 | Pipe beveling | 5% | 0.06 | 100% |  | -100%
6 | 1.3.1.1.6.3 | Assembly pipe to flange | 15% | 0.18 | 100% |  | -100%
6 | 1.3.1.1.6.4 | Welding pipe to flange | 35% | 0.42 | 100% |  | -100%
6 | 1.3.1.1.6.5 | Assembly elbow to pipe | 10% | 0.12 | 100% |  | -100%
6 | 1.3.1.1.6.6 | Welding elbow to pipe | 30% | 0.36 | 100% |  | -100%
4 | 1.3.1.2 | Final assembly | 50% | 12.5 | 48.85% |  | -48.85%
5 | 1.3.1.2.1 | Shell | 40% | 5 | 49% |  | -49%
6 | 1.3.1.2.1.1 | Assembly shell segments (CW) | 12% | 0.6 | 100% |  | -100%
6 | 1.3.1.2.1.2 | Welding shell segments (CW) | 27% | 1.35 | 100% |  | -100%
6 | 1.3.1.2.1.3 | Opening for nozzle assembly | 5% | 0.25 | 100% |  | -100%
6 | 1.3.1.2.1.4 | Nozzle assembly to shell | 5% | 0.25 | 100% |  | -100%
6 | 1.3.1.2.1.5 | Nozzle welding to shell | 10% | 0.5 |  |  | 0%
6 | 1.3.1.2.1.6 | Assembly head to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.7 | Welding head to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.1.2.1.8 | Assembly cone to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.9 | Welding cone to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.1.2.1.10 | Assembly segment shell to cone | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.11 | Welding segment shell to cone | 8% | 0.4 |  |  | 0%
6 | 1.3.1.2.1.12 | Assembly body flange to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.1.2.1.13 | Welding body flange to shell | 7% | 0.35 |  |  | 0%
5 | 1.3.1.2.2 | Channel | 15% | 1.875 | 30% |  | -30%
6 | 1.3.1.2.2.1 | Assembly head to channel | 10% | 0.1875 | 100% |  | -100%
6 | 1.3.1.2.2.2 | Welding head to channel | 20% | 0.375 | 100% |  | -100%
6 | 1.3.1.2.2.3 | Assembly body flange to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.4 | Welding body flange to channel | 20% | 0.375 |  |  | 0%
6 | 1.3.1.2.2.5 | Opening for nozzle assembly | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.6 | Assembly nozzle to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.1.2.2.7 | Welding nozzle to channel | 20% | 0.375 |  |  | 0%
5 | 1.3.1.2.3 | Bundle structure | 45% | 5.625 | 55% |  | -55%
6 | 1.3.1.2.3.1 | Assembly bundle structure | 15% | 0.84375 | 100% |  | -100%
6 | 1.3.1.2.3.2 | Insert tube to bundle structure | 10% | 0.5625 | 100% |  | -100%
6 | 1.3.1.2.3.3 | Tube to tube sheet welding | 30% | 1.6875 | 100% |  | -100%
6 | 1.3.1.2.3.4 | Expanding | 5% | 0.28125 |  |  | 0%
6 | 1.3.1.2.3.5 | Insert bundle to shell | 2% | 0.1125 |  |  | 0%
6 | 1.3.1.2.3.6 | Assembly tube sheet to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.1.2.3.7 | Welding tube sheet to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.1.2.3.8 | Assembly saddle to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.1.2.3.9 | Welding saddle to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.1.2.3.10 | Assembly external part to shell& channel | 2% | 0.1125 |  |  | 0%
6 | 1.3.1.2.3.11 | Welding external part to shell& channel | 4% | 0.225 |  |  | 0%
6 | 1.3.1.2.3.12 | Final NDT | 2% | 0.1125 |  |  | 0%
4 | 1.3.1.3 | Test | 5% | 1.25 |  |  | 0%
5 | 1.3.1.3.1 | Hydrostatic Test | 100% | 1.25 |  |  | 0%
4 | 1.3.1.4 | Sandblast & paint | 5% | 1.25 |  |  | 0%
5 | 1.3.1.4.1 | Sandblast | 50% | 0.625 |  |  | 0%
5 | 1.3.1.4.2 | Painting | 50% | 0.625 |  |  | 0%
3 | 1.3.2 | RU-0001A-E-02 | 50% | 25 | 52.93% |  | -52.93%
4 | 1.3.2.1 | Prefabrication | 40% | 10 | 66.25% |  | -66.25%
5 | 1.3.2.1.1 | Shell | 35% | 3.5 | 100% |  | -100%
6 | 1.3.2.1.1.1 | Cutting | 10% | 0.35 | 100% |  | -100%
6 | 1.3.2.1.1.2 | Beveling | 10% | 0.35 | 100% |  | -100%
6 | 1.3.2.1.1.3 | Rolling | 15% | 0.525 | 100% |  | -100%
6 | 1.3.2.1.1.4 | Assembly (LW) | 25% | 0.875 | 100% |  | -100%
6 | 1.3.2.1.1.5 | Welding (LW) | 35% | 1.225 | 100% |  | -100%
6 | 1.3.2.1.1.6 | Reroll | 5% | 0.175 | 100% |  | -100%
5 | 1.3.2.1.2 | Channel | 15% | 1.5 | 35% |  | -35%
6 | 1.3.2.1.2.1 | Cutting | 10% | 0.15 | 100% |  | -100%
6 | 1.3.2.1.2.2 | Beveling | 10% | 0.15 | 100% |  | -100%
6 | 1.3.2.1.2.3 | Rolling | 15% | 0.225 | 100% |  | -100%
6 | 1.3.2.1.2.4 | Assembly (LW) | 25% | 0.375 |  |  | 0%
6 | 1.3.2.1.2.5 | Welding (LW) | 35% | 0.525 |  |  | 0%
6 | 1.3.2.1.2.6 | Reroll | 5% | 0.075 |  |  | 0%
5 | 1.3.2.1.3 | Cone | 20% | 2 | 20% |  | -20%
6 | 1.3.2.1.3.1 | Cutting | 10% | 0.2 | 100% |  | -100%
6 | 1.3.2.1.3.2 | Beveling | 10% | 0.2 | 100% |  | -100%
6 | 1.3.2.1.3.3 | Rolling | 15% | 0.3 |  |  | 0%
6 | 1.3.2.1.3.4 | Assembly (LW) | 25% | 0.5 |  |  | 0%
6 | 1.3.2.1.3.5 | Welding (LW) | 35% | 0.7 |  |  | 0%
6 | 1.3.2.1.3.6 | Reroll | 5% | 0.1 |  |  | 0%
5 | 1.3.2.1.4 | Saddle fabrication | 10% | 1 | 20% |  | -20%
6 | 1.3.2.1.4.1 | Cutting | 10% | 0.1 | 100% |  | -100%
6 | 1.3.2.1.4.2 | Beveling | 10% | 0.1 | 100% |  | -100%
6 | 1.3.2.1.4.3 | Rolling | 15% | 0.15 |  |  | 0%
6 | 1.3.2.1.4.4 | Assembly (LW) | 25% | 0.25 |  |  | 0%
6 | 1.3.2.1.4.5 | Welding (LW) | 35% | 0.35 |  |  | 0%
6 | 1.3.2.1.4.6 | Reroll | 5% | 0.05 |  |  | 0%
5 | 1.3.2.1.5 | Nozzle fabrication (part 1) | 8% | 0.8 | 100% |  | -100%
6 | 1.3.2.1.5.1 | Pipe cutting | 15% | 0.12 | 100% |  | -100%
6 | 1.3.2.1.5.2 | Pipe beveling | 15% | 0.12 | 100% |  | -100%
6 | 1.3.2.1.5.3 | Assembly pipe to flange | 25% | 0.2 | 100% |  | -100%
6 | 1.3.2.1.5.4 | Welding pipe to flange | 45% | 0.36 | 100% |  | -100%
5 | 1.3.2.1.6 | Nozzle fabrication (part 2) | 12% | 1.2 | 100% |  | -100%
6 | 1.3.2.1.6.1 | Pipe cutting | 5% | 0.06 | 100% |  | -100%
6 | 1.3.2.1.6.2 | Pipe beveling | 5% | 0.06 | 100% |  | -100%
6 | 1.3.2.1.6.3 | Assembly pipe to flange | 15% | 0.18 | 100% |  | -100%
6 | 1.3.2.1.6.4 | Welding pipe to flange | 35% | 0.42 | 100% |  | -100%
6 | 1.3.2.1.6.5 | Assembly elbow to pipe | 10% | 0.12 | 100% |  | -100%
6 | 1.3.2.1.6.6 | Welding elbow to pipe | 30% | 0.36 | 100% |  | -100%
4 | 1.3.2.2 | Final assembly | 50% | 12.5 | 52.85% |  | -52.85%
5 | 1.3.2.2.1 | Shell | 40% | 5 | 59% |  | -59%
6 | 1.3.2.2.1.1 | Assembly shell segments (CW) | 12% | 0.6 | 100% |  | -100%
6 | 1.3.2.2.1.2 | Welding shell segments (CW) | 27% | 1.35 | 100% |  | -100%
6 | 1.3.2.2.1.3 | Opening for nozzle assembly | 5% | 0.25 | 100% |  | -100%
6 | 1.3.2.2.1.4 | Nozzle assembly to shell | 5% | 0.25 | 100% |  | -100%
6 | 1.3.2.2.1.5 | Nozzle welding to shell | 10% | 0.5 | 100% |  | -100%
6 | 1.3.2.2.1.6 | Assembly head to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.7 | Welding head to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.2.2.1.8 | Assembly cone to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.9 | Welding cone to shell | 7% | 0.35 |  |  | 0%
6 | 1.3.2.2.1.10 | Assembly segment shell to cone | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.11 | Welding segment shell to cone | 8% | 0.4 |  |  | 0%
6 | 1.3.2.2.1.12 | Assembly body flange to shell | 3% | 0.15 |  |  | 0%
6 | 1.3.2.2.1.13 | Welding body flange to shell | 7% | 0.35 |  |  | 0%
5 | 1.3.2.2.2 | Channel | 15% | 1.875 | 30% |  | -30%
6 | 1.3.2.2.2.1 | Assembly head to channel | 10% | 0.1875 | 100% |  | -100%
6 | 1.3.2.2.2.2 | Welding head to channel | 20% | 0.375 | 100% |  | -100%
6 | 1.3.2.2.2.3 | Assembly body flange to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.4 | Welding body flange to channel | 20% | 0.375 |  |  | 0%
6 | 1.3.2.2.2.5 | Opening for nozzle assembly | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.6 | Assembly nozzle to channel | 10% | 0.1875 |  |  | 0%
6 | 1.3.2.2.2.7 | Welding nozzle to channel | 20% | 0.375 |  |  | 0%
5 | 1.3.2.2.3 | Bundle structure | 45% | 5.625 | 55% |  | -55%
6 | 1.3.2.2.3.1 | Assembly bundle structure | 15% | 0.84375 | 100% |  | -100%
6 | 1.3.2.2.3.2 | Insert tube to bundle structure | 10% | 0.5625 | 100% |  | -100%
6 | 1.3.2.2.3.3 | Tube to tube sheet welding | 30% | 1.6875 | 100% |  | -100%
6 | 1.3.2.2.3.4 | Expanding | 5% | 0.28125 |  |  | 0%
6 | 1.3.2.2.3.5 | Insert bundle to shell | 2% | 0.1125 |  |  | 0%
6 | 1.3.2.2.3.6 | Assembly tube sheet to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.2.2.3.7 | Welding tube sheet to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.2.2.3.8 | Assembly saddle to shell | 5% | 0.28125 |  |  | 0%
6 | 1.3.2.2.3.9 | Welding saddle to shell | 10% | 0.5625 |  |  | 0%
6 | 1.3.2.2.3.10 | Assembly external part to shell& channel | 2% | 0.1125 |  |  | 0%
6 | 1.3.2.2.3.11 | Welding external part to shell& channel | 4% | 0.225 |  |  | 0%
6 | 1.3.2.2.3.12 | Final NDT | 2% | 0.1125 |  |  | 0%
4 | 1.3.2.3 | Test | 5% | 1.25 |  |  | 0%
5 | 1.3.2.3.1 | Hydrostatic Test | 100% | 1.25 |  |  | 0%
4 | 1.3.2.4 | Sandblast & paint | 5% | 1.25 |  |  | 0%
5 | 1.3.2.4.1 | Sandblast | 50% | 0.625 |  |  | 0%
5 | 1.3.2.4.2 | Painting | 50% | 0.625 |  |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Contractual Info.
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.06
This Period Highlights: |  |  | Material for tube, tube sheet, girth flange, baffle, plate, head, STD flange, fitting, SMS pipe, tie rod, gasket & nut & bolt have been delivered from Korea to Iran. The material received date to the customs will be forecast until end of january.
Forcasted activities for the next report period:
Overall Progress Table
Phase |  | Weight Factor | Cumulative up to Last Period |  | This Period |  | Cumulative up to End of This Period
|  |  | Plan | Actual | Plan | Actual | Plan | Actual | Variance
Engineering |  | 10% | 92% | 73.3% | 8% | 0.7% | 100% | 74% | -26%
Material Supply |  | 40% | 92.6% | 89.23% | 7.4% | 5.488% | 100% | 94.72% | -5.283%
Manufacturing |  | 50% | 11.22% | 0% | 42.06% | 0% | 53.28% | 0% | -53.28%
Total |  | 100% | 51.85% | 43.02% | 24.79% | 2.265% | 76.64% | 45.29% | -31.35%

## S-Curve
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.06
S-Curve
Interval | 2024-07-15 | 2024-07-31 | 2024-08-15 | 2024-08-31 | 2024-09-14 | 2024-10-01 | 2024-10-26 | 2024-11-15 | 2024-12-16 | 2025-01-25 | 2025-02-15 | 2025-02-28 | 2025-03-15 | 2025-03-30
Cumulative Plan | 0.003167% | 6.67% | 15.4% | 20.92% | 26% | 32% | 39% | 43.13% | 51.85% | 70% | 93% | 100% | 100% | 100%
Periodic Plan | 0.003167% | 6.667% | 8.73% | 5.52% | 5.08% | 6% | 7% | 4.13% | 8.72% | 18.15% | 23% | 7% | 0% | 0%
Cumulative Actual | 0.5% | 2% | 5% | 12% | 16.4% | 23.5% | 37.4% | 42.1% | 43.02% | 45.3%
Periodic Actual | 0.5% | 1.5% | 3% | 7% | 4.4% | 7.1% | 13.9% | 4.7% | 0.92% | 2.28% | 0% | 0% | 0% | 0%

## Pictures
Toase-ehe Park Sanati Gohar Ofogh Petrochemical Co. CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Document Title:
Document Title: PROGRESS REPORT NO.06
P.O. Number:
P.O. Description:
Raw Material / Fabrication Pictures