## WBS
WBS NAME |  | Management & Milestones | Weight Factor%
1 | Overal project |  | 100%
1.1 | Milestones |  | 0%
1.1.1 | LOI Date |  | 0%
1.1.2 | Effective Date |  | 0%
1.1.3 | K.O.M |  | 0%
1.1.4 | Bank Garanty Payment Date |  | 0%
1.1.5 | Advanced Payment Date |  | 0%
1.2 | Engineering |  | 5%
1.2.1 | GENERAL DOCUMENT |  | 0.5%
1.2.1.1 | Vendor Print Index & Schedule (VPIS) |  | 0.2%
1.2.1.2 | WBS |  | 0.1%
1.2.1.3 | Time Schedule |  | 0.05%
1.2.1.4 | Project Monthly Report for Refrigeration Packages |  | 0.05%
1.2.1.5 | Sub Vendor List |  | 0.1%
1.2.2 | ENGINEERING DOCUMENT |  | 3.9%
1.2.2.1 | Vendor Final Book Index |  | 0.08%
1.2.2.2 | Piping and Instrument Diagram (PID) |  | 0.08%
1.2.2.3 | General Arrangement Drawing Including Loads, Displacement, and Maintenace Info |  | 0.3%
1.2.2.4 | Mechanical Calculation of Heat Exchangers and Pressure Vessles |  | 0.3%
1.2.2.5 | Utility Consumption List |  | 0.04%
1.2.2.6 | Instrument Index List (Including Alarm & Trip Points) |  | 0.04%
1.2.2.7 | Junction Box Connection Diagrams (Including Wire Schematic to Instruments) |  | 0.04%
1.2.2.8 | Package PLC Wiring Diagrams (Including Wire Schematic to Instruments) |  | 0.04%
1.2.2.9 | Control Narrative (Sequence Description) |  | 0.04%
1.2.2.10 | Spare Parts List for Commissioning & Start-up |  | 0.04%
1.2.2.11 | Spare Parts List for 2-Year Operation |  | 0.04%
1.2.2.12 | IOM(including start up, shut down, precommissioning, commissioning procedure) |  | 0.04%
1.2.2.13 | I/O List |  | 0.05%
1.2.2.14 | Logic Diagram (Print out PLC Program) |  | 0.05%
1.2.2.15 | Compressor Drawing |  | 0.08%
1.2.2.16 | Oil Filter Drawing and Data Sheet |  | 0.08%
1.2.2.17 | Main Motor Data Sheet and Curve |  | 0.08%
1.2.2.18 | PLC Wiring Diagrams |  | 0.08%
1.2.2.19 | Process Flow Diagram (PFD) |  | 0.08%
1.2.2.20 | Main Motor Drawing |  | 0.08%
1.2.2.21 | Oil Cooler Drawing and Data Sheet |  | 0.08%
1.2.2.22 | Oil Pump Drawing and Data Sheet |  | 0.08%
1.2.2.23 | Oil Separator Drawing and Data Sheet |  | 0.08%
1.2.2.24 | Condensor Drawing and Data Sheet |  | 0.08%
1.2.2.25 | Liquid Receiver Drawing and Data Sheet |  | 0.08%
1.2.2.26 | K/O Drum Drawing and Data Sheet |  | 0.08%
1.2.2.27 | Economizer Drawing and Data Sheet |  | 0.08%
1.2.2.28 | Oil Pump Motor Drawing and Data Sheet |  | 0.08%
1.2.2.29 | Instrument Cable List |  | 0.07%
1.2.2.30 | Instrument Data Sheets |  | 0.08%
1.2.2.31 | Cause and Effect Diagram |  | 0.05%
1.2.2.32 | Operating Manual (Including Start up, Shut Down, Pre-Commissioning, Commissioning Procedure) |  | 0.05%
1.2.2.33 | Operating / Control Philosophy |  | 0.05%
1.2.2.34 | Compressor Data Sheet |  | 0.08%
1.2.2.35 | Equipment List |  | 0.08%
1.2.2.36 | Process Description |  | 0.06%
1.2.2.37 | Outline Dimensional Drawings (Cabinets Arrangement) |  | 0.08%
1.2.2.38 | Instrument Calculations (Safety Relief Valves, Control Valves, Flow Meters, Restriction Orifices, …) |  | 0.08%
1.2.2.39 | Instrument Hook up Drawings |  | 0.08%
1.2.2.40 | Noise Data Sheet |  | 0.08%
1.2.2.41 | Filter Dryer Drawing and Data Sheet |  | 0.08%
1.2.2.42 | 3D Model |  | 0.05%
1.2.2.43 | Line List |  | 0.05%
1.2.2.44 | PMS for Compressor Package |  | 0.05%
1.2.2.45 | Isometrci Drawing for Interconnecting Piping |  | 0.08%
1.2.2.46 | MTO of Insulation |  | 0.08%
1.2.2.47 | Thermal Calculation for Heat Exchangers |  | 0.25%
1.2.2.48 | Name Plate Drawing |  | 0.04%
1.2.2.49 | Capital Spare Part |  | 0.04%
1.2.2.50 | Special Tools List |  | 0.04%
1.2.3 | QC DOCUMENT |  | 0.6%
1.2.3.1 | Inspection & Test Plan (ITP) (for Whole Package) |  | 0.1%
1.2.3.2 | Welding Book (WPS, PQR and Welding / NDE Map) |  | 0.06%
1.2.3.3 | Painting Procedure |  | 0.04%
1.2.3.4 | Packing, Marking and Shipping Procedure |  | 0.04%
1.2.3.5 | Fat Procedure for Control System |  | 0.04%
1.2.3.6 | NDE Procedure |  | 0.04%
1.2.3.7 | PMI Procedure |  | 0.04%
1.2.3.8 | Inspection and Test Procedure for Compressor |  | 0.04%
1.2.3.9 | Inspection and Test Procedure for Vessle Skids |  | 0.04%
1.2.3.10 | Preservation Procedure |  | 0.04%
1.2.3.11 | Hydrostatic Test Procedure |  | 0.04%
1.2.3.12 | Lifting Procedure |  | 0.04%
1.2.3.13 | Certificates |  | 0.04%
1.3 | Supply of Material |  | 35%
1.3.1 | Domestic Supply |  | 10%
1.3.1.1 | Pipe |  | 1.11%
1.3.1.1.1 | PO placement |  | 0.12%
1.3.1.1.2 | EX Work |  | 0.44%
1.3.1.1.3 | Delivery to shop |  | 0.55%
1.3.1.2 | Plate |  | 1.11%
1.3.1.2.1 | PO placement |  | 0.12%
1.3.1.2.2 | EX Work |  | 0.44%
1.3.1.2.3 | Delivery to shop |  | 0.55%
1.3.1.3 | Flange & Fitting |  | 1.11%
1.3.1.3.1 | PO placement |  | 0.12%
1.3.1.3.2 | EX Work |  | 0.44%
1.3.1.3.3 | Delivery to shop |  | 0.55%
1.3.1.4 | Gasket |  | 1.11%
1.3.1.4.1 | PO placement |  | 0.12%
1.3.1.4.2 | EX Work |  | 0.44%
1.3.1.4.3 | Delivery to shop |  | 0.55%
1.3.1.5 | Bolt & Nut |  | 1.11%
1.3.1.5.1 | PO placement |  | 0.12%
1.3.1.5.2 | EX Work |  | 0.44%
1.3.1.5.3 | Delivery to shop |  | 0.55%
1.3.1.6 | Electrical |  | 1.11%
1.3.1.6.1 | PO placement |  | 0.12%
1.3.1.6.2 | EX Work |  | 0.44%
1.3.1.6.3 | Delivery to shop |  | 0.55%
1.3.1.7 | Manual valves |  | 1.12%
1.3.1.7.1 | PO placement |  | 0.13%
1.3.1.7.2 | EX Work |  | 0.44%
1.3.1.7.3 | Delivery to shop |  | 0.55%
1.3.1.8 | Instrument |  | 1.11%
1.3.1.8.1 | PO placement |  | 0.12%
1.3.1.8.2 | EX Work |  | 0.44%
1.3.1.8.3 | Delivery to shop |  | 0.55%
1.3.1.9 | PLC |  | 1.11%
1.3.1.9.1 | PO placement |  | 0.12%
1.3.1.9.2 | EX Work |  | 0.44%
1.3.1.9.3 | Delivery to shop |  | 0.55%
1.3.2 | ForeignSupply |  | 25%
1.3.2.1 | Other Valves |  | 1.87%
1.3.2.1.1 | PO placement |  | 0.19%
1.3.2.1.2 | EX Work |  | 0.75%
1.3.2.1.3 | Custom clearance |  | 0.56%
1.3.2.1.4 | Delivery to shop |  | 0.37%
1.3.2.2 | Instrument |  | 1.87%
1.3.2.2.1 | PO placement |  | 0.19%
1.3.2.2.2 | EX Work |  | 0.75%
1.3.2.2.3 | Custom clearance |  | 0.56%
1.3.2.2.4 | Delivery to shop |  | 0.37%
1.3.2.3 | Electrical (Electro motor) |  | 5%
1.3.2.3.1 | PO placement |  | 0.5%
1.3.2.3.2 | EX Work |  | 2%
1.3.2.3.3 | Custom clearance |  | 1.5%
1.3.2.3.4 | Delivery to shop |  | 1%
1.3.2.4 | Filter |  | 1.88%
1.3.2.4.1 | PO placement |  | 0.2%
1.3.2.4.2 | EX Work |  | 0.75%
1.3.2.4.3 | Custom clearance |  | 0.56%
1.3.2.4.4 | Delivery to shop |  | 0.37%
1.3.2.5 | Oil pump & Oil separator |  | 1.88%
1.3.2.5.1 | PO placement |  | 0.2%
1.3.2.5.2 | EX Work |  | 0.75%
1.3.2.5.3 | Custom clearance |  | 0.56%
1.3.2.5.4 | Delivery to shop |  | 0.37%
1.3.2.6 | Compressor |  | 12.5%
1.3.2.6.1 | PO placement |  | 1.25%
1.3.2.6.2 | EX Work |  | 5%
1.3.2.6.3 | Custom clearance |  | 3.75%
1.3.2.6.4 | Delivery to shop |  | 2.5%
1.4 | Fabrication |  | 45%
1.4.1 | Fabrication For Compressor unit |  | 6.6%
1.4.1.1 | Part Fabrication-(cutting,rolling,casting) |  | 3.31%
1.4.1.2 | Part Assembly |  | 1.65%
1.4.1.3 | Part Welding |  | 0.82%
1.4.1.4 | NDT |  | 0.82%
1.4.2 | Fabrication For Condensor |  | 6.6%
1.4.2.1 | Part Fabrication-(cutting,rolling,casting) |  | 3.31%
1.4.2.2 | Part Assembly |  | 1.65%
1.4.2.3 | Part Welding |  | 0.82%
1.4.2.4 | NDT |  | 0.82%
1.4.3 | Fabrication For Hexane chiller |  | 6.6%
1.4.3.1 | Part Fabrication-(cutting,rolling,casting) |  | 3.31%
1.4.3.2 | Part Assembly |  | 1.65%
1.4.3.3 | Part Welding |  | 0.82%
1.4.3.4 | NDT |  | 0.82%
1.4.4 | Fabrication For Skid |  | 6.6%
1.4.4.1 | Part Fabrication-(cutting,rolling,casting) |  | 3.31%
1.4.4.2 | Part Assembly |  | 1.65%
1.4.4.3 | Part Welding |  | 0.82%
1.4.4.4 | NDT |  | 0.82%
1.4.5 | Assembly of packages on skid |  | 6.6%
1.4.5.1 | Inter connecting piping |  | 3.31%
1.4.5.2 | Part Assembly |  | 1.65%
1.4.5.3 | Part Welding |  | 0.82%
1.4.5.4 | NDT |  | 0.82%
1.4.6 | Visual & DIM. Inspection |  | 4%
1.4.7 | Surface Preparation |  | 2.5%
1.4.8 | Painting |  | 2.5%
1.4.9 | Final Check |  | 3%
1.5 | FINAL INSPECTION TEST and RELEASE NOTE for Ex-Work |  | 10%
1.5.1 | FINAL INSPECTION TEST and RELEASE NOTE for Ex-Work |  | 10%
1.6 | Final Data Book |  | 5%
1.7.1 | VENDOR FINAL DATA BOOK |  | 5%