## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | GAD | N-278-VD-6019-PR-GAD-0003-01 (17735-04)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | 0 |  | foundation loading data is not complete. loading data should be completed (seismic&wind) | Following diviation is approved by Nargan during sales phase (item 11); Airpack 23-Aug-2021: Considering the very small size of offered package, these loads are negligible and will therefore not be considered. We confirm package design is suitable to withstand such load cases. TCL H2: Skid foundation drawing (showing skid dimensions, anchor bolt locations, etc.) will be provided by Airpack. Concrete or steel foundation at site (on which the package will be installed) shall be designed by others locally. Therefor foundation layout on the GA drawing is sufficient.
2 |  | 0 |  | Plant North | Noted, and adjusted
3 |  | 0 |  | The below comment has been already confirmed on TCL by vendor so please consider it and implement it as a note or prepare reply sheet. - With considering this area has been considered as fire potential zone all fireproofing requirement shall be considered for equipment support, structures,valves, actuators, junction boxes and associated cable trays according to JOB SPECIFICATION FOR PASSIVE FIRE PROTECTION [N-278-000-HS-JSD-1740-00. and also the valve body shall be fire safe. also please note according to IEC-60331, actuators, junction box and glands shall be considered as explosion proof and cables shall be supplied as fire resistant | Fire safe: TCL G3, Fire safe design is not considered. Only for ball valve, Fire Safe according to API 607 is required. Comment is made on the valve datasheet. No need to put this on the GAD. Explosion proof: TCL E12 is closed, b. IP-65 is confirmed. Area classification is not applicable considering package is installed in safe area.
4 |  | 0 |  | Please specify Tie-in Tag No. and Nozzle dimension at this view. -Pipe support of lines at the edge of package where located in vendor area is by vendor | Noted
5 |  | 0 |  | Instrument Comment: - Instrument Nozzle details table, Cable Tray .... to be indicated on this document, otherwise, this document cannot be reviewed by instrument Dept. | Not considered for the GA drawing. Information is already shown in document 17735-38 Hook-up drawing. And also mentioned in the instrument datasheet 17735-12. Cable tray details is mentioned in the wiring 17735-05.
6 |  | 0 |  | Please also mark item 13 (fan motor) in this viwe and please clarify this fan will cool which device. (what is the application of this fan?) | Noted, and adjusted
7 |  | 0 |  | It seems instruments are not displayed in GAD | Will be updated when the instruments are ordered so we can put the exact model in the drawing. |  |  |  | Open
8 |  | 0 |  | Please add a section for reference documents and please refer to compressor datasheet, P&ID and other major docs | Noted, and adjusted |  |  |  | Closed
9 |  | 0 |  | As per latest comment PID document, tag name should be revised. | Noted, and adjusted
10 |  | 0 |  | What do these dimensions refer to? (Are they related to COG?) | Yes correct please find symbol explanation on drawing
11 |  | 0 |  | Please clarify if this oil pump has any PSV. (positive displacement pumps require PSV for protection.) | Please mention this on leading P&ID document
12 |  | 0 |  | to be clarified.There is V-belt. | Noted, and adjusted
13 |  | 0 |  | Please also add weight of compressor, dampers, and coolers as well. | Noted, and adjusted
14 |  | 0 |  | According to vendor reply on VPIS, Sketch of lifting/transport arrangement will be provided as additional page on GA, | COG and lifting points are mentioned on the GA drawing. Lifting drawing is made before transportation. As mentioned in the VPIS CRS this is provided in the databook.
15 |  | 0 |  | Please display oil drain of sump on GAD | Noted, and adjusted
16 |  | 0 |  | Please mention/mark the port for filling the oil sump | Noted, and adjusted
17 |  | 0 |  | Please correct the name (there is no Nitrogen) | Noted, and adjusted
18 |  | 0 |  | Please mention "maximum maintenance weight" | Noted, and adjusted
19
20