## Resolution Sheet
|  |  |  | PROJECT: | Integrated methanol and ammonia plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Equipment datasheet | 17735-11A
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  |  |  | Please confirmed pressure drop from package BL to compressor nozzle is considered in reported pressure. These pressure are exactly the same as pressure at package BL | The pressure drop from the package inlet to the 1st stage compressor inlet is negligible, as it only is a small distance.
2 |  |  |  | Since there is no coupling. This is NA | Changed
3 |  |  |  | Please add a note that this is required/rated capacity with no negative tolerance | If the inlet flow has no negative tolerance, the outlet flow should not have negative tolerance either.
4 |  |  |  | Please remove from datasheet. It shall be reported in GAD and it will be discussed in that document | Removed
5 |  |  |  | Discrepancy with motor datasheet | Updated
6 |  |  |  | Discrepancy with motor datasheet. Driver power same as compressor power in this datasheet, is not the same according to motor datasheet | Updated
7 |  |  |  | max 46 degrees C | Updated |  |  |  | Open
8 |  |  |  | 0 | Updated |  |  |  | Closed
9 |  |  |  | 0 barg is 1.01 bara | As every other value in the document is in bar(g), we will keep this value in bar(g) as well
10 |  |  |  | cooling water supply = 4.5 barg, return is 2.5 barg | Updated
11 |  |  |  | please add below note: including driver at full load condition from each noisy part and whole package. | The noise test will be done according to the FAT procedure, (N-278-VD-6019-GN-PRC-0015-01)
12 |  |  |  | Please add a note that 39barg is related to both stage casings. Otherwise, the value for first stage shall be reported | Added
13 |  |  |  | Please change this to MAWP. This is normally used in rotating equipment. | MAWP is not the same as design pressure, therefore we keep it the same.
14 |  |  |  | Please add hydrotest pressure values for compressor cylinders | 1.5x design pressure. Refer to 17735-17 hydrotest procedure (N278-VD-6019-GN-PRC-0018-04)
15 |  |  |  | add references to control valve and psv datasheets | Added
16 |  |  |  | please mention for both stages (In P&ID, discharge of first stage design is 175 degC) | Added
17 |  |  |  | Please mention the model | Data not available
18 |  |  |  | This shall be clarified since the compressor is on/off type | The PCV mentioned here is the capacity control for the compressor (320PCV-8201). This valve recycles part of the instrument air to make sure that the outlet pressure of the package is as close as possible to the desired value, even when the inlet pressure fluctuates.
19 |  |  |  | Please add data for both stages of compressor casing. (please note that the rating shall be compatible with MAWP/design pressure) | Added data as much as possible.
20 |  |  |  | Data of oil pump shall be added material of parts, sealing, coupling) | No data available, as the oil pump is in the compressor itself and the package is small.
21 |  |  |  | Data of oil heater shall be added(material of parts, immersed length, element temperature, etc) | No data available, as the oil pump is in the compressor itself and the package is small.
22 |  |  |  | Below data of compressor shall be added: -No. Of cylinders, existence of unloader, volumetric efficiency, Material of all parts for both stages, combined rod loads, maximum allowable rod loads, acoustic simulation analysis, Data related to V-belt, cylinders/packing cooling (water/air), barring device (required or not) cylinder bore, stroke, piston speed, liner thickness, valves type and quantity and velocity and lift and rod diameter. piston rod hardness and coating hardness, Insulation/ personal protection | All data which is available is filled in to the datasheet. Not all data is available as this is asmall compressor package.
23 |  |  |  | Since there is inter&after cooler datasheet, please remove this section | Removed
24 |  |  |  | For all dampers, please add design pressure/temperature to this table | Added for all pulsation dampers
25 |  |  |  | Please mention ASTM No. And grade for material (not just CS) | Mentioned as CS here because the pulsation dampers have different grades and ASTM numbers in them. For more details, refer to 17735-23B Detail drawings for pulsation dampers (N-278-VD-6019-ME-DWG-0025-01)
26 |  |  |  | Please remove any paint data from this datasheet. | removed
27
28
29
30