## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Inter- en aftercooler datasheet | 17735-11B
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | 2 |  | Discrepancy with PID to be removed | Discrepancy will be filled in the PID. The values in these datsheet are correct
2 |  | 2 |  | ASTM No. And grade of all materials to be mentioned | Added material grades according to latest revision of cooler drawings
3
4
5
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20