## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Inter- en aftercooler datasheet | 17735-11B
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | 2 |  | Discrepancy with PID to be removed | Discrepancy will be filled in the PID. The values in these datsheet are correct | Noted, utility consumption to be revised | noted
2 |  | 2 |  | ASTM No. And grade of all materials to be mentioned | Added material grades according to latest revision of cooler drawings | Check comments on data sheet. | noted
3 |  | 3 |  | 1- For design pressures please write from -1 bar(g) or vacum to ... bar(g). For design temperature also mention the lower bound. 2- All discrepancy with approved drawing to be revised. 3- add volume and hydrostatic test pressure of shell and tube side. | We keep our documents with the same data. We use the design pressure / temperature defined in the P&ID for this project. This is also commented from your side. For example 30 * 1.3 = 39 bar design pressure. So design data will stay the same as defined. actual or tested can be higher, but never lower.
4 |  | 3 |  | -1 to 39 bar(g) as per approved drawing. For de3sign temperature -10/175 C. | noted
5 |  | 3 |  | -1 to 10 bar(g) as per approved drawing. for design temperature -10/100 C. | noted
6 |  | 3 |  | please recheck by approved drawing and revise. material seems to be SA-240. | The main material (Shell and tube) is SA-312 as indicated on the latest drawing.
7 |  | 3 |  | Add operating weight as well. | Updated |  |  |  | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20