## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | 17735-14-FAT Procedure | N-278-VD-6019-GN-PRC-0015-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page9 | 2 |  | This should be clarified. please provide the related calculation in this doc. | The calculation is provided in attachment 6 | Noted. | Closed
2 | Page 9 | 2 |  | Is this applicable to all measuring points? | Only the motor and the compressor measure points (attachment 5). | 1- our question was "Is this applicable to all measuring point? (e.g. cylinders, frame, motor, etc.)?. 2-(Please clarify. Why is the sketch displaying the measuring point removed? Please add. | It is applicable to all measuring points. Schematicis added and table is made more clear.
3 | att. 3 | 2 |  | please recheck this. in P&ID, set pressure for LLA is 1 barg. | It is changed to 1,5 bar (g) | Noted. | Closed
4 | att. 4 | 2 |  | please clarify | This is deleted as it should be filled in during FAT |  | Closed
5 | att. 4 | 2 |  | There is a discrepancy between noise estimated for points and the noise average measured which is reported as 75 dB(A). Please clarify | Yes the 75 is updated to 85 |  | Closed
6 | att. 5 | 2 |  | Please clarify about the H1-H3 and V1,V2. On cylinders vibration should be measured (usually there is 3 component) | To clarify the vibration test there is no more schematic picture only a table. | Please add a schematic same as previous revision showing the measuring point. | Schematic added |  | Open
7 | att. 5 | 2 |  | This shall be clarified. Is there any gear between motor and compressor? As far as vendor informed us motor is connected to compressor by V-Belt. | Correct there is no gear only V-Belt | Noted. | Closed
8 | att. 5 | 2 |  | Please clarify about other applicable points. According to ISO 10816-8 Fig. 2. (attached) other points (e.g. each frame corner point, each frame location between cylinders, pulsation vessels) are required. | There will be 4 measurements on the compressor frame and 2 measurement points at the motor. All 6 points will be tested in vertical horizontal and axial. The corner frames won't be tested because there is no use as there is no dampers beneath the vessels and the piping can't vibrate more then the motor/compressor. | 1-Please add a schematic same as previous revision showing the measuring point. 2-Measuring vibrations for corner frames is applicable not only when we have dampers beneath. It is required to recheck that frame vibration will not be above acceptable criteria. 3-Please clarify. We have 2 cylinders, and 4 dampers. It means if vendor wants to measure on compressor, cylinders and dampers, at least we have 7 points. This shall be clarified. | Schematic added
9 | Page 1 | 3 |  | As we informed vendor with PCIM system before, comments attached from client shall be reviewed/replied by vendor. | Noted | Not replied.
10 | Page 6 | 3 |  | Plz add following items for instrument - Degree of Ingress Protection (IP) Certificate - Performance Tests For Valves are required the following Items too - Hydrostatic/NDE Test - Blowdown/Set Pressure Test | Of course all certificates can be checked before shipment. This procedure is only the tests during FAT (factory acceptance test) | Noted.
11 | Page 6 | 3 |  | should be added "and material certificate" | Not incorporated. Why do you want a material certificate of the test instruments as a multimeter ? These are temporarily used during FAT. | Noted.
12 | Page 9 | 3 |  | as stated before , all electrical eq. shall be 400 V | Comment is not applicable for this document. This document is the test procedue.
13 | Page 9 | 3 |  | Is this applicable to all measuring point? (e.g. cylinders, frame, motor, etc.)? | Yes. We measure on compressor frame and motor frame. | Noted.
14 | Att. 4 | 3 |  | What are these marks? | Removed in the next revision | Noted.
15 | Att. 4 | 3 |  | Please add a schematic same as previous revision showing the measuring point. | Added to the attachment | Noted.
16 | Att. 4 | 3 |  | 1-Please clarify. We have 2 cylinders, and 4 dampers. It means if vendor wants to measure on compressor, cylinders and dampers, at least we have 7 points. This shall be clarified. 2-Measuring points shall be clear. Please add a schematic. | Measuring points are made more clear and schematic added | Noted.
17 | Att. 5 | 3 |  | Please clarify. will actual volume in test condition be measured/calculated and compared with actual flow at site condition? | From the actual flow at site this sheet is calculated by the compressor manufacturer. Since we are running on atmosperic pressure during FAT the outlet flow and pressure is less than at site. If the noted values are reached the compressor can handle the side conditions. | Noted.
18 | Att. 5 | 3 |  | Please remove this. (test duration is specified in age 9) | This means that the compressor can be tested maximum for 24 running hours with atmospheric pressure. The actual running test will be 4h as described in page 9 | Noted.
19 | Page 1 | 4 |  | As we informed vendor with PCIM system before, comments attached from client shall be reviewed/replied by vendor. | Noted
20 | Att. 4 | 4 |  | Please recheck and clarify why on each pulsation damper is not considered. Please also measure vibration at each pulsation damper if possible. | Vibrations are coming from the machinery. Vibrations measured at the motor and compressor are the highest. Because it is small piping to and from the pulsation dampeners the piping absorbed most vibrations. Also the pulsation dampeners are fixed to the main frame. Therefor we measure at the machinery and other equipment on the package can be checked visually during FAT.
21 | 6 | 5 |  | Add: clamp meter, HART communicator, laser thermometer gun, Electronic bearing stethoscope | These will not be needed as the temperature check on electric motor, bearing temp and bearing noise check will not be done during FAT. A noise check of the entire package will be done however.
22 | 11 | 5 |  | availability valid calibration certificated for all instrument devices | All instruments that are available will have a calibration certificate that is valid during the time of the FAT.
23 | 12 | 5 |  | Electric motor surface temp check, Electric motor ampere check, transmitter parameters check by HART communicator, Electric motor bearing temp and sound check, Interlock check IP 920. 922. 923 | Interlocks cannot be checked during FAT as we are not at site and this package is controlled by the DCS of the plant. This has to be checked during SAT. Transmitter parameters will be checked at random (10%). We will not check the ampere, surface temp, bearing temp or sound during the FAT. These things have been tested by the manufacturer of the electric motor.
24 |  |  |  | Client reply: According to N278-000-EL-JSS-1691-001-02 document section 6, it is mandatory to perform the required tests. | Please specify the tests. Motor is Safe area, very small and routine test certificate is available in the databook. All tests are according the approved ITP and accordign the order