## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Hydrotest procedure | N-278-VD-6019-GN-PRC-0018-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 02 |  | Final checking of below design and test pressures will be done after issuance of drawings for below mentioned equipment by vendor. | noted
2 | 3 | 02 |  | Duration as per ASME VIII, Div.1, shall be one hour as minimum. | Incorporated to 1 hour
3 | 3 | 02 |  | 150 | Incorporated | Usually maximum allowable content for hydrotest in standards is 50ppm (e.g. API 618). So you are kindly requested to consider 50ppm. Sorry for our previous comment in this regard.
4 | 3 | 02 |  | Design pressure of cooling water is 7 barg according to design basis | Incorporated | Noted.
5 | 4 | 02 |  | Vendor shall submit a sketch to demonstrate different stages of tests for shell and tube sides. | There will be a drawing of the cooler
6 | 4 | 02 |  | As per ASME Sec. VIII, Div.1, test pressure shall be 1.3 of design pressure. | Incorporated
7 | 4 | 02 |  | this shall be checked and clarified by vendor. (for case of tube rupture what measure is considered?) this comment will be discussed in coolers datasheet/drawing. | noted | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) |  |  | Open
8 |  | 02 |  | If design pressure of every item changed, this doc shall be revised accordingly. | noted | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.)
9 |  | 02
10 |  | 02
11 |  | 02
12 |  | 02
13 |  | 02
14 |  | 02
15 |  | 02
16 |  | 02
17 |  | 02
18 |  | 02
19 |  | 02
20 |  | 02
21 |  | 02
22 |  | 02
23 |  | 02
24 |  | 02
25 |  | 02
26 |  | 02
27 |  | 02
28 |  | 02
29 |  | 02
30 |  | 02
31 |  | 02
32 |  | 02