## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Hydrotest procedure | N-278-VD-6019-GN-PRC-0018-01 (17735-17)
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 01 |  | Final checking of below design and test pressures will be done after issuance of drawings for below mentioned equipment by vendor. | noted
2 | 3 | 01 |  | Duration as per ASME VIII, Div.1, shall be one hour as minimum. | Incorporated to 1 hour | Noted.
3 | 3 | 01 |  | 150 | Incorporated | Usually maximum allowable content for hydrotest in standards is 50ppm (e.g. API 618). So you are kindly requested to consider 50ppm. Sorry for our previous comment in this regard. | Updated accordingly in the next revision
4 | 3 | 01 |  | Design pressure of cooling water is 7 barg according to design basis | Incorporated | Noted.
5 | 4 | 01 |  | Vendor shall submit a sketch to demonstrate different stages of tests for shell and tube sides. | There will be a drawing of the cooler | Noted.
6 | 4 | 01 |  | As per ASME Sec. VIII, Div.1, test pressure shall be 1.3 of design pressure. | Incorporated | noted.
7 | 4 | 01 |  | this shall be checked and clarified by vendor. (for case of tube rupture what measure is considered?) this comment will be discussed in coolers datasheet/drawing. | noted | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID | 1-there exist comments regarding design pressure (e.g. design pressure of cooling water side in coolers are not specified in P&ID and case of tube rupture shall be clarified.) 2-Hydrotest pressure is 1.3 of MAWP. (please recheck the values). 3-MAWP of inter-coolers and supppressors will be specified in related drawings and this doc will be approved after finalizing MAWP in those docs. | Open
8 | 4 | 01 |  | If design pressure of every item changed, this doc shall be revised accordingly. | noted | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID | 1-there exist comments regarding design pressure (e.g. design pressure of cooling water side in coolers are not specified in P&ID and case of tube rupture shall be clarified.) 2-Hydrotest pressure is 1.3 of MAWP. (please recheck the values). 3-MAWP of inter-coolers and supppressors will be specified in related drawings and this doc will be approved after finalizing MAWP in those docs.
9 | 3 | 02 |  | Usually maximum allowable content for hydrotest in standards is 50ppm (e.g. API 618). So you are kindly requested to consider 50ppm. Sorry for our previous comment in this regard. | Updated accordingly in the next revision
10 | 4 | 02 |  | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID
11 | 4 | 02 |  | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID
12 | 4 | 03 |  | of Pulsation damper | This is main process piping, not pulsation dampener. As per 17735-03 P&ID, from the package inlet till the 1st stage suction of the compressor is meant.
13 | 4 | 03 |  | Please check Nargan comments on pulsation damper second suction on Doc. No. N-278-VD-6019-PR-PID-0002-01 (17735-03). | Please find reply in the below comment
14 | 4 | 03 |  | 1-there exist comments regarding design pressure (e.g. design pressure of cooling water side in coolers are not specified in P&ID and case of tube rupture shall be clarified.) 2-Hydrotest pressure is 1.3 of MAWP. (please recheck the values). 3-MAWP of inter-coolers and supppressors will be specified in related drawings and this doc will be reviwed/approved after finalizing MAWP in those docs. | 1. There is a PSV on the cool water piping, set @7 bar. This is also the design pressure of the tube side of the inter- aftercooler. At the in and outlet of the cooling water the operating (OP) and design pressure (DP) is shown. 2. Incorporated in the next revision. 3. Noted.
15 |  | 04 |  | Thesr data shll be checked after approval of following document: N-278-VD-6019-PR-PID-0002-01 (17735-03). | Noted
16 |  | 04 |  | Design pressure of tubeside on drawing of cooler is 10bar. | Design pressure of the cooling water system is 7barg. Which makes hydrotest pressure 9,1 barg. Airpack makes sure all the equipment will be resistant to 9,1 barg or more as the cooler (10barg). The tested pressure for the hydrotest is 9,1 barg, as this is 1,3 times the design pressure, which is based on the operating pressure
17 |  | 04 |  | As per latest P&ID, design pressure of 2nd stage suction dampener is 39barg | Updated
18 |  | 04 |  | Hdtrotest of compressor pressure parts to be 1.5 of MAWP | Design pressure is equal to MAWP in this project, so changed to 1,5 times design pressure
19 |  |  |  | See DWG No. N-278-VD-6019-ME-DWG-0024-01 (17735-23A) Detail drawings for coolers. | according to the spec it is 1.3x design pressure. These pressures are noted. The supplier used a higher pressure so it is tested to a better safety. Still the pressures noted are the specified pressures. It is updated to min. hydrotest pressure in the procedure.
20 |  |  |  | See DWG No. N-278-VD-6019-ME-DWG-0025-01 (17735-23B) Detail Drawings for Pulsation Damper. | see above.
21 |  |  |  | is 45.75 related to first stage and 58.5 related to second stage cylinder? The matter will be approved after specifying first stage MAWP in datasheet. | Working pressure is on the P&ID,.
22
23
24
25
26
27
28
29
30
31
32