## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Pulsation study CRS | 17735-24
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 6 | 01 |  | these values will be checked with datasheet | Noted
2 | Page 6 | 01 |  | please report this value for suction/discharge of both stages (4 values are required as used in page 9/9) | Input data is added
3 | Page 6 | 01 |  | to be clarified. | Note is refering to the input data table to see the calculation.
4 | Page 6 | 01 |  | Please recheck this. | Updated
5 | Page 6 | 01 |  | please clarify why rod section area is subtracted. (vendor stated it is single act and it seems cylinder section area should be multiplied by stroke( | One stroke is subtracted and then multiplied by the stroke. oIn this case the formula is for single acting
6 | Page 8 | 01 |  | therefore please mention the final volume are queal to 0.03m3 | Updated
7 | Page 8 | 01 |  | please clarify how it can be concluded that maximum allowable pulsation level at the compressor cylinder flange is below the calculated values (or 7%). (How it can be concluded that 7.9.4.2.5.2 is followed?) | Conclusion is added in the next revision |  |  |  | Open
8 | Page 8 | 01 |  | please clarify how it can be concluded that maximum pressure drop at the inlet of the device is below of 0.25? (How it can be concluded that 7.9.4.2.5.3.1 is followed?) | Conclusion is added in the next revision |  |  |  | Closed
9 | Page 9 | 01 |  | please clarify how it can be concluded that pulsation level at the line side of the pulsation device is below the calculated values. (How it can be concluded that 7.9.4.2.5.2.2.1 is followed?) | Design approch one is to calculate the peak-to-peak pulsation levels determined by the equation. Deasign approaches 2 and 3 calculates this further.
10 | Page 9 | 01 |  | please recheck this value (operating pressure in P&ID is 23.3 for first stage discharge) | This is not the operating pressure, but this is the average mean absolute line pressure.
11 | Page 9 | 01 |  | please recheck this value (operating pressure in P&ID is 30barg for second stage discharge) | This is not the operating pressure, but this is the average mean absolute line pressure.
12
13
14
15
16
17
18
19
20