## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | WPS PQR | N-278-VD-6019-GN-WS-0027-01 (17735-25)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 1 | 1 |  | vendor shall submit welding/NDE map for fabrication of skid, CS and SS pipings. | Noted, please find weld map drawings attached. NDE drawings will be seperate drawings please note that NDE drawings are not part of this document | Noted. We have not seen any document in VPIS regarding NDE drawing. Vendor shall specify this matter. | Closed, New document number is requested NDE drawings will be provided as separate document.
2 | Page 6, 8, 10, 12, 15, 17, 19, 24 and 26 | 1 |  | Please submit joint design as per AWS D1.1 here. | As per applicable welding codes joint details can be addressed on separate documents is this case joint details can be found in weld map | Noted. | Closed
3 | 45 | 2 |  | Test specimen for PQR is not pipe and it is flanges. | Noted and closed, Airpack is qualified for piping material and flange material which will be welded to pipe
4
5
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20