## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Control and shut down Logic Block Diagram | N-278-VD-6019-IN-DIA-0049 (17735-32)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 01 |  | This document will be reviewed again after finalizing control philosophy interlock description document. | Please put the comment in the correct document. For interlock information please refer to Control Philosophy and Cause & Effect chart. | please be informed reference document for this document is "Cause and effect chart" and "Control philosophy and Interlock Description". Compatibility with reference document and other vendor documents is vendor responsibility and scope and next comments are just for hint. Please issue next revision after finalizing "Control philosophy and Interlock Description" document. | There is no need to wait after finalizing the control philosophy since it is our responsibility to keep the documents updated with each other. We will submit the last revision when the order is ready for shipment. | Noted.
2 | 12 | 01 |  | HS-8204 | Noted. Tag number will be updated. | Noted.
3 | 12 | 01 |  | should be described in control philosophy document too | It is described in the control philosophy in the common alarm and common trip chapter. Accept from DCS will be updated as Acknowledge. | Noted.
4 | 1 | 02 |  | Reference document should be mentioned. - PID Document - Cause and effect chart - Control philosophy and Interlock Description - IO List | Noted. Reference documents will be mentioned. | Noted.
5 | 2 | 02 |  | Alarm acknowledge | Noted. It will be incorporated. | Noted.
6 | 12 | 03 |  | Start pushbutton HS-8201 is not sending the signal to the PLC. this signal is only sending to the MCC. please recheck | Acoording to per control philosophy, when the start pushbutton HS-8201 is pressed, start signal is send to PLC in DCS. And the PLC in DCS is sending a start signal to MCC to start the fan motor, then the MCC is returning a running signal to start the main motor. |  |  |  | Open
7 | 16 | 03 |  | should be added to legend | Noted. It will be added. |  |  |  | Closed
8 | 19 | 03 |  | Positioner feedback signal (PZT-8201) should be implemented in this page. | Positioner feedback signal will be added.
9 | 19 | 03 |  | whereas positioner feedback signal is an Analog signal, tag name PZLC-8201 (PZLC is used for limit switch and digital signal) should be modified to PZT-8201 in PID and relevant document. PZT-8201 is correct for analog input signal. | As per P&ID and approved IO list, the tag number will be PZLC-8201.
10 | 13 | 04 |  | As per comment on C&E document from Process dept, The fault lamp related to the LPS will be on when a fault occurs in the MCC. This fault will be indicated on the fault lamp through the DCS. | From rev.05 of the P&ID an attachment is send from your side with a request to have the following lights; - running - fault - operational - emergency trip In the meeting after we agreed to use the alarms for the fault signal. Therefor the fault is also shown 'amber' and not red as the trip light. For motor fault please refer to SH8 in the diagram. | Should be Updated As per latest C&F document comments from process dept. | Noted. It will be updated accordingly.
11 | 1 | 06 |  | Should be Updated As per latest C&F document.(Rev.07) (As per latest C&F document revision, "320-PAHH-8191, 320-PALL-8191, 320PAH-8191" should be implemented in logic block diagram.) | Noted. External signals will be included.
12
13
14
15
16
17
18