## Resolution Sheet
|  |  |  | PROJECT: | LIDCO, Pars SEE Zone, Assaluyeh, Integrated Methanol and Ammonia Plant 3000 MTPD MeOH / 900 MTPD NH3 PROJECT
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | (Pre-) Commisioning procedure | 17735-33
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | 1 |  | Outlet pressure higher than inlet pressure is impossible, discrepancy between P&ID and this Document to be removed | Fixed value, No more discrepancy between P&ID and this document.
2 |  | 1 |  | please consider below comments: Safety level based on IEC 61508 | Rules of site have to be followed as a minimum before commisioning and testing.
3 |  | 1 |  | Rules & conduct in case of fire (alarm, evacuation and other measures) | Rules of site have to be followed as a minimum before commisioning and testing.
4 |  | 1 |  | Please clarify about acceptance criteria of performance test | Acceptance criteria of the performanceRefer to FAT procedure 17735-14 (N-278-VD-6019-GN-PRC-0015-01))
5 |  | 1 |  | As per below sentence extracted from scope of supply, performance test at factory shall be done. Please also clarify about guarantee of normal flow per hour of compressor reported in data sheet. | Performance test at factory will be done before performance test at site. Refer to FAT procedure 17735-14 (N-278-VD-6019-GN-PRC-0015-01))
6 |  | 1 |  | Please clarify about measurement of vibration and record of value | Refer to FAT procedure 17735-14 (N-278-VD-6019-GN-PRC-0015-01))
7 |  | 1 |  | there is no separate power supply in the LPS, only 24 VDC is issued from DCS. | Updated |  |  |  | Open
8 |  | 1 |  | Please clarify which panels should be powered up, the LPS only includes lamp signals and switches. | Updated |  |  |  | Closed
9 |  | 1 |  | Please clarify Nitrogen generator | Updated
10
11
12
13
14
15
16
17
18
19
20