## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | 17735-35 Instrument index | N-278-VD-6019-IN-LIS-0033-01
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | 1 |  | This data is not required in this document | Proces connection, instrument connection, B&B and Type B&B will stay | Noted.
2 |  | 1 | Closed | unit of measurement shall be specified (e.g. "barg") | Unit of measurement is specified | closed
3 |  | 1 | Closed | Has discrepancy with PID Set point HH=34barg | Discrepancy fixed | closed
4 |  | 1 |  | thermowell tag should be mentioned. | Thermowell tags added | Noted.
6 |  | 1 | Closed | -Discrepancy with PID Document -All set point should be same in Instrument list PID and IO list document. Compliance of documents is one of the vendors responsibilities. | Set points the same as in P&ID | Noted.
7 |  | 1 |  | General Comments : - Final Approval of P&ID document is the prerequisite for checking the I/O List Document. Therefore, Plz the next revision of this document should be sent after the Approval of PID documents. - Instrument Type , PID No.,Data sheet No.,Hook up No., Line/Equipment No., EX Certificate, System(DCS/ESD), Unit , Cal. range, Oper. Range,service, IO Type column should be added the list. | Instrument type, P&ID No., Line/Equipment No., IO type Added. Data sheet & Hook up no. added at bottom of list. | Noted. |  |  | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20