## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Instrument Hook-up Drawing | N-278-VD-6019-IN-DWG-0035-01 (17735-38)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 02 |  | Instrument General Comment: 1- Instrument and piping Battery limit scope of work to be specified. 2- revision No. of reference document to be removed. It's clear latest revision to be followed by vendor. 3- Tubing length to be specified. 4- Mounting type to be specified in document for each pages. | 1. Noted. Battery limit will be indicated. 2. Noted. 3. Tubing length is according to actual engineering. It will not be indicated. 4. Noted. It will be added in the note.
2 | 3 | 02 |  | - as per vendor data sheet these tags are panel mounted, please add it in note part. - tube length to be specified. | - Note will be added - Tubing length is according to actual engineering. It will not be indicated.
3 | 3 | 02 |  | As per latest VPIS, "01" is removed from all document No. | It will be updated accordingly.
4 | 4 | 02 |  | all tags are locally mounted, so this description is not correct. | Description will be updated accordingly.
5 | 5 | 02 |  | - TG tag names have discrepancy with the related data sheet. - as per this drawing it seems TGs are head mounted. But in data sheet some TGs are panel mounted. Please clarify. | - TG tag numbers are as per P&ID and instrument datasheet. - It will be updated accordingly.
6 | 6 | 02 |  | - as per vendor data sheet mounting bracket to be supplied for these tags, please add it in note part. - Tube length to be specified. | - Note will be added. - Tubing length is according to actual engineering. It will not be indicated.
7 | 7 | 02 |  | - as per vendor data sheet mounting bracket to be supplied for these tags, please add it in note part. | Note will be added. |  |  |  | Open
8 | 8 | 02 |  | - as per vendor data sheet mounting bracket to be supplied for these tags, please add it in note part. | Note will be added. |  |  |  | Closed
9
10
11
12
13
14
15
16
17
18
19
20