## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Sub-Supplier List | N-278-VD-6019-GN-EQL-0038-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 2 | 01 | Open | Local panel to be mentioned. | Not part of agreed sub-vendor list in salesphase. | Shall be determined details device and to be mentioned in Sub-vendor list Document .
2 | 2 | 01 | Open | Please mention oil pump bearing compressor valves electric heater V-Belt | Not part of agreed sub-vendor list in salesphase. | Mehrer is mentioned for the compressor. Closed.
3 | 2 | 01 | Closed | WEG(Brazile) is not accepted | Updated to WEG Germany as per agreed sub-vendor list | Noted.
Open
Closed