## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | PSV sizing calculations | 17735-47
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 1 | 1 |  | - Compatibility of all related data between PSV sizing calculations and PSV data sheet is vendor scope. | Noted. The first revision was the preliminary calculation done by Airpack. The current revision is done by the subsupplier.
2 | Page 3 | 1 |  | As per data sheet should be SS316 | Noted.
3 | Page 3 | 1 |  | "Body/bonnet"Shall be specified , | It is now specified in the calculation.
4 | Page 3 | 1 |  | As default of leser software template, Bonnet type,Order code and other relevant specification will be indicated as report, please specify | The first revision was only for preliminary calculations, the current revision is from the subsupplier.
5 | Page 9/10 | 1 |  | As per Data sheet comment, thermal expansion shall be 3/4x1NPT | Noted
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20