## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Lubrication List | N-278-VD-6019-PR-LIS-0043-01 (17735-51)
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 02 |  | to be specified. | Incorporated
2 | 3 | 02 |  | Please recheck. Is it pre lubed? | Yes it is pre lubed.
3 | 3 | 02 |  | Please recheck. Is it equipment factory sealed and requires no field lubrication? | Correct. | Please clarify about this item. If "No field lubrication" is required, what the announced values in column E is. If vendor announced "quantity to fill" and "period between changes" Then, it requires field lubrication. (after a period.) | Updated in the next revision
Open