## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Sub-Supplier List | N-278-VD-6019-IN-LIS-0048-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 2 | 2 |  | below items shall be added to line list: 1. paint code 2. NDT 3. test pressure 4. test media | According to the painting precedure (17735-18) there is system 1 and 3 added to the line list. NDT has its own procedure (document 17735-08 ITP) Test pressure you can see in the Hydro test (17735-17) Test media you can see in the Hydro test (17735-17) | Piping Reply:Its obviosly that mentioned items shall be specified in line list fo each line
2 | 2 | 2 |  | Operating & Design condition shall be revised. this line is at the discharge of 1st stage compressor | Incorporated to same values as Pulsation damper 1st stage discharge.
3 | 2 | 2 |  | 116 °C (maximum operating temperature of exchanger upstream shall be considered as design temperature of down stream section). | N/A after the aftercooler the temperature in the piping is 75°C. otherwise you can't get the desired Air outlet. | Closed
4 | 2 | 2 |  | Requirement of hot insulation shall be clarified | Protected for safety so you can't accidently touch a hot pipe line. | if personnel protection is required please use relevant legend.
5 | 2 | 2 |  | According to the vendor PID TP-8202 is related to this line ,please check. | Corrected
6 | 2 | 2 |  | 75°C (minimum design temperature shall be considered as 75 °C) | Incorporated | closed
7 | 2 | 2 | [6 empty] | Open
8 | 2 | 2 | [6 empty] | Closed
9 | 2 | 2
10 | 2 | 2
11 | 2 | 2
12 | 2 | 2
13 | 2 | 2