## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Hydrotest procedure | N-278-VD-6019-GN-PRC-0018-01 (17735-17)
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 02 |  | Final checking of below design and test pressures will be done after issuance of drawings for below mentioned equipment by vendor. | noted | Noted.
2 | 3 | 02 |  | Duration as per ASME VIII, Div.1, shall be one hour as minimum. | Incorporated to 1 hour | Noted.
3 | 3 | 02 |  | 150 | Incorporated | Usually maximum allowable content for hydrotest in standards is 50ppm (e.g. API 618). So you are kindly requested to consider 50ppm. Sorry for our previous comment in this regard. | Updated accordingly in the next revision | Noted.
4 | 3 | 02 |  | Design pressure of cooling water is 7 barg according to design basis | Incorporated | Noted.
5 | 4 | 02 |  | Vendor shall submit a sketch to demonstrate different stages of tests for shell and tube sides. | There will be a drawing of the cooler | We did not find any shematic drawing in procedure. For your information, we want to know how many steps of hydrostatic test for heat exchangers need to be done by vendor based on type of heat exchangers and pressure of shell and tube sides.
6 | 4 | 02 |  | As per ASME Sec. VIII, Div.1, test pressure shall be 1.3 of design pressure. | Incorporated
7 | 4 | 02 |  | this shall be checked and clarified by vendor. (for case of tube rupture what measure is considered?) this comment will be discussed in coolers datasheet/drawing. | noted | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID | Noted. | Open
8 | 4 | 02 |  | If design pressure of every item changed, this doc shall be revised accordingly. | noted | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID | Noted.
9 | 3 | 03 |  | Usually maximum allowable content for hydrotest in standards is 50ppm (e.g. API 618). So you are kindly requested to consider 50ppm. Sorry for our previous comment in this regard. | Updated accordingly in the next revision | Noted.
10 | 4 | 03 |  | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID | Noted.
11 | 4 | 03 |  | since we have comments on design pressures. this document will be checked after finalizing related docs (e.g. drawings, datasheets, P&ID, etc.) | Updated according to the P&ID | Noted.
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32