## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Noise datasheet | N-278-VD-6019-IN-DS-0042-01 17735-49
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  |  |  | Noise data sheet shall be in accordance with the project template which is attached here and all data shall be specified there. | Project template is not shared with the project. This is a new comment. This template from Airpack is shared before and no comment was made. Test is signed and approved during FAT | Not accepted.please note the noise data sheet has been sent on PCIM. recheck it.The previous data sheet was the first one and safety comments have been sent you before.
2 |  |  |  | SPL shall be calculated at 1 meter distance from each noisy part and whole package. | No comment was made during testing this about this. There is also only one noice part and that is the compressor + motor, which is the whole package. Its very small. | please note that this comment is related to noise data sheet and it has been sent you so do not ignore it and add our comment ''SPL shall be calculated at 1 meter distance from each noisy part and whole package.'' to guarantee our concern.
3 |  |  |  | Please clarify your calculation for estimation and measured noise | As per ISO2151 standard | Noted.
4 |  |  |  | According the Noise level of 85 dB(A) at 1 meter distance from each noisy part and whole package, please note that positive tolerance is not acceptable. | noted | closed.