## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Vendor Data Book | N-278-VD-6019-GN-MNL-0045-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2 | AirPack's Reply #3
4 |  |  |  | VDB cover sheets as per attached format shall be considered for each part. | VDB is made as per approved document N-278-VD-6019-GN-LIS-0020-01 Index of Vendor Data Book . Changes in de index and layout after approved document can be made against extra cost. | Cover sheet of binder is only two pages (external cover sheet and spine) and it shall be added to hard copy of binders.
8 |  |  |  | All test reports and certificates shall be signed and stamped by TPI inspector. | You should have told this to your TPI when he was here. You can now only arrange TPI again to do this. The cost for that are for you. | Please send inspection notification for document review (including stamping and signing) of VDB by TPI inspector. |  |  |  | Closed
10 |  |  |  | Above mentioned certificates shall be submitted by vendor. | These certificates are not part of the approved VDS. Will not be sent, they can be checked in the VDB. | With refer to item 2.2 of approved ITP, review of material certificates (as per EN 10204-3.1) for compressor items shall be done by TPI inspector during FAT test. Therefore, vendor shall submit them.
18 |  |  |  | VDB index list shall be considered in beginning of this part, too. VDB cover sheets as per attached format shall be considered for each part. | Index can be found in part 1. VDB is made as per approved document N-278-VD-6019-GN-LIS-0020-01 Index of Vendor Data Book . Changes in de index and layout after approved document can be made against extra cost. | Vendor shall add VDB index list in beginning of each part. Cover sheet of binder is only two pages (external cover sheet and spine) and it shall be added to hard copy of binders.
19 |  |  |  | Release note and packing list shall be submitted by vendor. | Both documents are not part of the approved VDS. Will not be sent, they can be checked in the VDB. | VPIS ( as you said VDS) contains drawings, data sheets, calculations, procedures and so on. All inspection reports, test certificates, packing list and inspection release note have not been considered on VPIS. Therefore, vendor shall submit them in VDB and he confirmed them in VDB index list.
29
30
31
32
33
34
35