## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 14/Oct/2021 | Rev.: 01
|  | Comment Sheet Ref.No.: | Doc Description: AFTER COOLER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00033 | Doc. No.: BU-20-VD-303-ME-DSH-0017
|  | Transmittal Date: 14/10/2021 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Discrepancy with PID. In PID 180 oC |  |  | Noted will be updated in next revision CES REPLY: We are waiting to recive new revision of document Airpack Reply : Waiting for CRS reply from your Side
2 | Nitrogen or Instrument air compressor, which one is correct? |  |  | Instrument air compressor CES REPLY: Document title shall be revised. Airpack Reply : Noted will be revised CES REPLY (Oct.18,2021): Closed.
3 | As per clause 6.14.2.3 of API 618, minimum tube O.D shall be 16 mm. |  |  | This is not correct, API 618 6th edition does not specify this in this chapter CES REPLY: Compressor shall be designed as per API618 5th edition. This clause is related to API618 5th edition. Please send 6th edition of API618. Airpack reply : I have checked the 5th Edition and this is for specified for oil cooler only CES REPLY (Oct.18,2021): Closed. Please check the thickness and diameter again with API614 chapter 1.
4 | As per clause 6.14.2.3 of API 618, minimum tube thickness shall be 1.2mm. |  |  | This is not correct, API 618 6th edition does not specify this in this chapter CES REPLY: Compressor shall be designed as per API618 5th edition. This clause is related to API618 5th edition. Please send 6th edition of API618. Airpack reply : I have checked the 5th Edition and this is for specified for oil cooler only CES REPLY (Oct.18,2021): Closed. Please check the thickness and diameter again with API614 chapter 1.
5 | 1- TEMA type shall be specified (For example BEM, AES and etc.). 2- TEMA sheet shall be sent. 3- As per clause 6.14.2.3 of API 618, tube sheets shall be brass; and tubes shall be of a copper/zinc/tin non-ferrous material such as UNS C44300. 4- In next revision, calculation of heat exchanger shall be sent officially. |  |  | 1. Noted CES REPLY: We are waiting to recive new revision of document Airpack Reply: Next revision CES REPLY (Oct.18,2021): Closed. 2. will not be submitted CES REPLY: TEMA sheet shall be submitted. Airpack Reply: It is not specified anywhere in the specification that this is required, so it won't be submitted CES REPLY (Oct.18,2021): With reference to material requisition of compressor (ITEM C-1002 & C-7080) (BU-20-D-000-MA-MRQ-303-03) page 22 of 62, TEMA data sheet shall be submitted by AIRPACK. Please see attached file. 3. This is not correct, API 618 6th edition does not specify this in this chapter CES REPLY: Compressor shall be designed as per API618 5th edition. This clause is related to API618 5th edition. Please send 6th edition of API618. Airpack reply : I have checked the 5th Edition and this is for specified for oil cooler only CES REPLY (Oct.18,2021): Water analysis is attached to reply sheet. Please be noted that SS material for service with 50ppm chloride in is not suitable and following material shall be selected: tube sheets shall be brass; and tubes shall be of a copper/zinc/tin non-ferrous material such as UNS C44300. 4.calculation is a different document CES REPLY: Calculation shall be submitted for checking with data sheet. Only after approval of datasheet we will send the calculation CES REPLY (Oct.18,2021): Please be noted that in case of having conflict between both documents, airpack is in charge to eliminate any conflict.
6 | TBC |  |  | will be confirmed after order has been placed CES REPLY: We are waiting to recive new revision of document Airpack Reply : Noted will be revised CES REPLY (Oct.18,2021): Closed.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48