## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 12/Nov/2021 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: NDE PROCEDURE
|  | Transmittal No.: APCES-V-00050 | Doc. No.: BU-20-VD-303-QC-PRC-0007
|  | Transmittal Date: 12/Nov/2021 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply:
1 | General Comment: 1. RT and UT procedures shall be added. 2. NDT map shall be added. 3. For this procedure and UT and RT procedure shall be considered all ASME SEC. V requirement so this standard shall be added in reference sections. 4. All NDT format reports shall be added. |  |  | 1. RT procedure added 2. NDT map will not be provided for approval, it will be available in the Databook if required together with the reports 3. RT for piping as Per AMSE B31.3. MT for skid as per AWS D1.1 4. NDT format reports has been added |  |  | 1. where is UT?? 2. In order to determine which parts of the equipment need what nondestructive test, must be added. Also, according to the ITP approved, this document must be sent along with the NDT Map. 3. Ok. 4. Ok.
2