## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 28/Apr/2022 | Rev.:04
|  | Comment Sheet Ref.No.: | Doc Description: MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00126 | Doc. No.: BU-20-VD-303-ME-DSH-0022
|  | Transmittal Date: 28/Apr/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | LEVELING SCREWS, SUB SOLE PLATES, CHOKE BLOCKS and shims are required. |  |  | Not required for mounting on a foundation, this will be mounted with anchor bolts, levelling is not required. CES REPLY (Dec.18,2021): It is in AIRPACK responsibility to consider all required facilities for safe and reliable installation of compressor. Noted and closed
2 | With reference to clause 6.1.7 of API618 5th edition, allowable pressure drop along heat exchanger shall not exceed 1bar. Also with reference to clause 4.3.6 of BU-20-D-000-PR-SPC-101-06 pressure unit is bara. |  |  | pressure drop accros the cooler is as per pressure drop stated in the the information from client, additional pressure drop is created by a globe valve in the cooling water line to the cooler. Unit is bar(g) as per P&ID CES REPLY (Dec.18,2021): Closed.
3 | 1- ASTM material equivalent shall be added. |  |  | will not be added, as this are the materials used CES REPLY (Dec.18,2021): Closed. But base material of mentioned component shall be specified.
4 | All remaining data to be completed |  |  | After completion of pulsation study, currently waiting for customer piping details CES REPLY (Dec.18,2021): We are waiting to receive new data. Added
5 | All Notes shall be revised as per attached file. |  |  | This is what was provided in this format CES REPLY (Dec.18,2021): Notes in page 20 of BU-20-VD-303-ME-DSH-0022 are related to instrument air compressor. Therefor, notes shall be revised as per attached file. See TCL Clause M33.Added
6 | Compressor is V-BELT |  |  | updated CES reply (Mar. 16,2022): Closed.
7 | How it is possible to provide liner with 48 mm thickness for cylinder with 160mm??????? |  |  | because compressor is suitable for much larger piston CES reply (Mar. 16,2022): Closed.
8 | Size shall be added. 1'', 2'', 3''..... |  |  | updated CES reply (Mar. 16,2022): Closed.
9 | Please check it again |  |  | checked and confirmed CES reply (Mar. 16,2022): Closed.
10 | These notes shall be revised as per attached file. |  |  | updated CES reply (Mar. 16,2022): Closed.
1. | One row for compressor stage shall be inserted after row 15 (See annex A of API 618 5th edition). |  |  | updated 1st and 2nd stage CES reply: Closed.
2. | 2. Please be noted that it is the temperature of the first stage. Final temperature must be reported. |  |  | Noted and updated CES reply: Closed.
3. | 1.Discrepancy with PID. in PID 14.5 bara |  |  | P&ID mentioned 15.5 bar(a) = 14.5 bar(g) CES reply: Closed.
4. | Pulsation dampener data shall be updated considering comments on pulsation dampener data sheet and drawing. |  |  | it has been updated as per this datasheet, if there is any mistake please give specific comment. CES reply: Closed.
5. | With reference to clause 7.9.3.2 of API 618 5th , Vd= 1.6x (Vs/r1/k). Therefor, discharge pulsation dampener capacity shall not be less than 105 liter considering 96 liter inlet pulsation dampener capacity. |  |  | This is not true, it is based on the calculation, we use 6th edition of API for the calculation, which is newer. CES reply: Closed.
6. | With reference to clause 7.9.3.2 of API 618 5th , Vd= 1.6x (Vs/r1/k). Therefor, discharge pulsation dampener capacity shall not be less than 105 liter considering 96 liter inlet pulsation dampener capacity. |  |  | This is not true, it is based on the calculation, we use 6th edition of API for the calculation, which is newer. CES reply: Closed.
7. | 85 |  |  | Noted and updated CES reply: Closed.
8. | 210 |  |  | Noted and updated CES reply: Closed.
9. | Shall not be less than 85 C. See clause 4.5 of BU-20-D-000-PR-SPC-101 (ESS FOR AMBIENT, SITE CONDITION & UTILITY DATA), design temperature shall be at least 85C. |  |  | Noted and updated CES reply: Since TAHH (10155) is 140 C, design temperature shall not be less than 140 C.
10.