## Resolution Sheet
|  |  |  | PROJECT: | 17811-COM
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Inspection Test Plan (ITP) | 17811-08
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2 | AirPack's Reply #2
1 | page 1 | 0 | Open | Inspection and Test Plan (ITP) for Reciprocating Compressor-MEG-303 | common for both compressos, we will split them after approval of 1 document.
2 | page 1 | 0 | Open | ? | This is your format
3 | page 1 | 0 | Open | MEG | Noted will be updated
4 | Page 2 | 0 | Open | LOGO VENDOR | Noted will be updated
5 | Page 2 | 0 | Open | ?? | Noted will be updated
6 | Page 6 | 0 | Open | 20% | SW is 10% as per your formati, will not be changed
7 | Page 9 | 0 | Open | Documents Review Procedures according to VPIS H RA R R | Noted will be updated |  |  |  |  | Open
8 | Page 9 | 0 | Open | H/R/H | Noted will be updated |  |  |  |  | Closed
9 | Page 10 | 0 | Open | mention procedures needed for each steps and other necessary references. this goes for Acceptance criteria | Noted will be updated
10 | Page 10 | 0 | Open | there are no "Q" in this project. Vendor is "H" in every steps | Noted will be updated
11 | Page 10 | 0 | Open | Why all actions are "R". Submit your ITP as min requirements of SOI | Not everything is R, however only Items that do not require witness are W. If any item you want to W please indicate with proper reference to specifcation instead of general comment
12 | Page 11 | 0 | Open | R | Noted will be updated
13 | Page 16 | 0 | Open | R | Noted will be updated
14 | Page 17 | 0 | Open | R | Noted will be updated
15 | Page 18 | 0 | Open | R | Noted will be updated
16 | Page 19 | 0 | Open | H/W/W/R | Noted will be updated
17 | Page 20 | 0 | Open | H/H/H/R | Noted will be updated
18 | Page 20 | 0 | Open | Final Data Book >>>>> index as reference and acceptance criteria with H/RA/RA/R actions | Noted will be updated
19
20