## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Time Shedule | 17811-73
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | July 7 | Open | In this summary task the required documents for PIM or Inspection summary task e.g. ITP, Sub-vendor list, VPIS, GA shall be defined. | Will be added in the next
2 |  | July 7 | Open | - Plan should be presented as below weighted for level 1 of WBS as below: Key Milestones 0% (Containing: Start/ Down-payment/ KOM/ PIM) Engineering 10% (Containing: any Engineering documents mandatory for the PIM, e.g. ITP, Sub-vendor List, VPIS,...) Procurement 65% Fabrication 20% Final Inspection 2% Shipment 2% FDB 1% -The weight factors of other levels below level 1 shall be set accordingly. | Mircosoft project doesn't have the possibility. In the MPR progress can be found based on the EALIER provided weight factors.
3 |  | July 7 | Open | Predecessor and Successor relation shall be defined for every task and activity. | In the GANT BAR relation are showed
4 |  | July 7 | Open | Weight factor column (numbers as per level.1 WBS) shall be defined and calculated. | Microsoft Projects doesn't have this possibilitie. Progress percentage can be found in the MPR.
5 |  | July 7 | Open | Task Dependency shall be defined. | In the GANT BAR depency are showed
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20