## Resolution Sheet
|  |  |  | PROJECT: | 17811-COM
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | VDS | 17811-01
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 1 | 0 | Closed | following documents were mentioned in the previous reversion and have now been removed, shall be added these documents 1-TIE IN POINT LIST 2-PIPING VALVE LIST 3-PIPING LINE LIST | Noted will be provided, will be added in new revision | NOTED
2 | Page 1 | 0 | Closed | Any changes shall be shown cloudy with revision mark. | Or Color, depending on the type of document | NOTED
3 | Page 1 | 0 | Closed | First issue date shall be specified | Noted will be provided, will be added in new revision | NOTED
4 | Page 1 | 0 | Closed | CLIENT COMMENTS: Refer to comments on next pages. Some doc MC/ Client class shall be changed as per attached excel file. | Noted will be updated | NOTED
5 | Page 1 | 0 | Closed | CLIENT COMMENTS: All related document for each tag no (such as PID, GA, datasheet, ....) shall be submitted separately as separate document. For example, please change the name of documents such as below pattern: - GA for Nitrogen Gas Booster Compressor - GA for Emergency Instrument Air Compressor | Noted will be updated | NOTED
6 | Page 2 | 0 | Closed | ME | Noted will be updated
7 | Page 2 | 0 | Closed | sectional | section drawings may not be availavle, however detailed drawings will be provided | CES REPLY : CLOSED. MC REPLY: CLOSED.
8 | Page 2 | 0 | Closed | LOGIC DRAWING | it is already mentioning logic drawing
9 | Page 2 | 01 | Open | INCL. UCP WIRING DIAGRAM AND BOM | This needs to be updated, one document is wiring diagram for UCP, LCP and JB other document is lay-out drawing | ITS OK .JUST ALSO BOM SHALL BE MENTION IN THE END OF "UCP/LCP/JB WIRING DIAGRAM" (ACCORDING TO COMMENT ON DOCUMENT). | BOM will not be included
10 | Page 2 | 01 | Closed | INCLUDING PERFORMANCE TEST PROCEDURE AND MECHANICAL RUNING TEST PROCEDURE | Noted | COMMENT HAS NOT IMPLEMENTED.SHALL BE MENTION IN REMARK: INCLUDING PERFORMANCE TEST PROCEDURE AND MECHANICAL RUNNING TEST PROCEDURE | Included
11 | Page 3 | 01 | Open | MC/Client Class | Noted will be updated | To be added. | Will be added
12 | Page 3 | 0 | Closed | ME | Noted will be updated | NOTED
13 | Page 3 | 0 | Closed | WIRING DIAGRAM INCLUDING JUNCTION BOX, LCP WIRING DIAGRAM AND TERMINAL DIAGRAM | This needs to be updated, one document is wiring diagram for UCP, LCP and JB other document is lay-out drawing | NOTED
14 | page 1 | 01 | Open | FOLLOWING DOCUMENTS SHALL BE ADDED: SIL report SIL verification report HAZOP report Bi-weekly report |  |  | Our SIL and FAT Report are one doucment and will be added as such progress report is not ad document and will not be added, it will be submitted thourgh E-mail.
15 | page 3 | 01 | Open | FOR NITROGEN GAS BOOSTER |  |  | Will be included
16 | page 3 | 01 | Open | EMERGENCY INSTRUMENT AIR COMPRESSOR |  |  | Will be changed