## Resolution Sheet
|  |  |  | PROJECT: | 17811-COM
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Inspection Test Plan (ITP) | 17811-08
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2 | AirPack's Reply #2
1 | page 1 | 0 | Open | Inspection and Test Plan (ITP) for Reciprocating Compressor-MEG-303 | common for both compressos, we will split them after approval of 1 document.
2 | page 1 | 0 | Open | ? | This is your format
3 | page 1 | 0 | Open | MEG | Noted will be updated
4 | Page 2 | 0 | Open | LOGO VENDOR | Noted will be updated
5 | Page 2 | 0 | Open | ?? | Noted will be updated
6 | Page 6 | 0 | Open | 20% | SW is 10% as per your format, will not be changed
7 | Page 9 | 0 | Open | Documents Review Procedures according to VPIS H RA R R | Noted will be updated |  |  |  |  | Open
8 | Page 9 | 0 | Open | H/R/H | Noted will be updated |  |  |  |  | Closed
9 | Page 10 | 0 | Open | mention procedures needed for each steps and other necessary references. this goes for Acceptance criteria | Noted will be updated
10 | Page 10 | 0 | Open | there are no "Q" in this project. Vendor is "H" in every steps | Noted will be updated
11 | Page 10 | 0 | Open | Why all actions are "R". Submit your ITP as min requirements of SOI | Not everything is R, however only Items that do not require witness are W. If any item you want to W please indicate with proper reference to specifcation instead of general comment
12 | Page 11 | 0 | Open | R | Noted will be updated
13 | Page 16 | 0 | Open | R | Noted will be updated
14 | Page 17 | 0 | Open | R | Noted will be updated
15 | Page 18 | 0 | Open | R | Noted will be updated
16 | Page 19 | 0 | Open | H/W/W/R | Noted will be updated
17 | Page 20 | 0 | Open | H/H/H/R | Noted will be updated
18 | Page 20 | 0 | Open | Final Data Book >>>>> index as reference and acceptance criteria with H/RA/RA/R actions | Noted will be updated
1 | Page 1 | 1 |  | Comment: 1.Inspections items for Vessels, Heat exchangers, UCP, Lube oil system and all related equipments (for example Electrical heaters and ...) and all another equipments based on approved drawing and project spec. shall be added. 2. Refer to text comments. | 1. electricacl heater is not an inspection item, it is only a few 100 watts, lubes oil system is part of compressor and has not inspectable parts. 2. Noted
2 | General | 1 |  | Logo vendor | Noted
3 | Page 5 | 1 |  | ?? | will be filled in
4 | Page 6 | 1 |  | 20 | SW is 10% as per your format, will not be changed
5 | Page 8 | 1 |  | API 618 (last edition) | With taken deviations and clarifications as per P.O.
6 | Page 9 | 1 |  | Contract/PO | Noted will be updated
7 | Page 9 | 1 |  | add ITP | Noted will be updated
8 | Page 9 | 1 |  | change to H | Noted will be updated
9 | Page 9 | 1 |  | To be devided into two row as "Engineering documents" and "Procedure Documents". procedure documents shall be mentioned in detail as per approved VPIS. | Noted will be updated
10 | Page 9 | 1 |  | Add WPS & PQR as separate row and Welding operator qualification certificate as follows: H\RA\RA\R | This is added per point of inspection
11 | Page 9 | 1 |  | Add a row as "NDT qualification certificate" in accordance with SNT-TC-1A with following actions: H\RA\RA\R | NDT will be outsourced to reputable company, this will not be provided as we do not know who will do the NDT
12 | Page 9 | 1 |  | Add "Type Test certificate (if any)" with following actions: H\RA\RA\R | Not applicable
13 | Page 10 | 1 |  | H /RA (*) | Only review on material certificates
14 | Page 10 | 1 |  | H | Only review of welding procedures
15 | Page 10 | 1 |  | SW | NDT only review of NDT certificates
16 | Page 10 | 1 |  | W | Dimension of the skid will be checked during FAT
17 | Page 10 | 1 |  | add app. project spec and datasheet | project spec. will not be added, datasheet and drawing will be added for reference
18 | Page 10 | 1 |  | add app. project spec and datasheet | project spec. will not be added, datasheet and drawing will be added for reference
19 | Page 10 | 1 |  | add EN10204 type 3.1 / Lab test report (Note 1) Note 1: If there is any doubt about the authenticity of the material test certificate, sampling and laboratory tests shall be done under supervision of TPI. | This will not be added, as discussussed in sales stage only 3.1 certificate is offered. No addiotional test are applicable.
20 | Page 10 | 1 |  | add visual and move this step before step of welding | Noted visual inspection will be added, visual inspection report will be added to the databook.
21 | Page 10 | 1 |  | change TPA to W for step of NDT | NDT only review of NDT certificates
22 | Page 10 | 1 |  | What about other welds? | No NDT on other weld
23 | Page 10 | 1 |  | change to VT report | what is VT report?
24 | Page 10 | 1 |  | change to VT report | what is VT report?
25 | Page 10 | 1 |  | Raw Material Check | Raw materials will not be checked, only 3.1 material certificate review.
26 | Page 11 | 1 |  | (*): Hold for sampling Review Approve for certificate of parts | Review of material certificates only
27 | Page 11 | 1 |  | Material Check and sampling | Review of material certificates only
28 | Page 11 | 1 |  | Material Check and sampling | Review of material certificates only
29 | Page 11 | 1 |  | and UT | No UT is foreseen
30 | Page 11 | 1 |  | and UT for all joints except for pipes less than 8 mm thick | No UT is foreseen
31 | Page 11 | 1 |  | As per Item c.1 comments. | See answer C.1
32 | Page 11 | 1 |  | add PT for fillet weld such as branch and socket welds (if any) | No PT is foreseen
33 | Page 11 | 1 |  | add step for "visual & dimensional (fitup)" before step of welding. | Noted will be added as H R R
34 | Page 11 | 1 |  | change to SW | Only review
35 | Page 11 | 1 |  | As per C.2 comments. | what is VT report?
36 | Page 11 | 1 |  | change to NDT report | Noted will be updated
37 | Page 11 | 1 |  | except the penalties | Not considered in ITP
38 | Page 12 | 1 |  | H | Noted Can be added as H point
39 | Page 12 | 1 |  | W | DFT check during FAT is W, painting is Review
40 | Page 12 | 1 |  | and API 618 | only pulsation study as per API 618 design aproach 1
41 | Page 12 | 1 |  | Material Check and sampling | Review of material certificates only
42 | Page 12 | 1 |  | H/RA (*) | Review of material certificates only
43 | Page 12 | 1 |  | (*): Hold for sampling Review Approve for certificate of parts | Review of material certificates only
44 | Page 12 | 1 |  | SW | Review only
45 | Page 12 | 1 |  | change to report | Noted will be updated
46 | Page 12 | 1 |  | As per C.1 comments | See answer C.1
47 | Page 12 | 1 |  | As per C.2 comments | what is VT report?
48 | Page 12 | 1 |  | add step for "visual & dimensional (fitup)" before step of welding. | Noted visual inspection will be added, visual inspection report will be added to the databook.
49 | Page 12 | 1 |  | NDT after welding is not considered? | Because ASME VIII may not require this based on the calculation
50 | Page 13 | 1 |  | H | Only R of hydrostatic test report
51 | Page 13 | 1 |  | W | DFT check during FAT is W, painting is Review
52 | Page 14 | 1 |  | Material Check and sampling | Review of material certificates only
53 | Page 14 | 1 |  | H/RA (*) | Review of material certificates only
54 | Page 14 | 1 |  | (*): Hold for sampling Review Approve for certificate of parts | Review of material certificates only
55 | Page 14 | 1 |  | SW | Review only
56 | Page 14 | 1 |  | and API 618 | Not required for Cooler
57 | Page 14 | 1 |  | change to report | Noted will be updated
58 | Page 14 | 1 |  | Section D comments shall be applied for this section | As per reply on section D comments
59 | Page 14 | 1 |  | H | Only R of hydrostatic test report
60 | Page 14 | 1 |  | W | DFT check during FAT is W, painting is Review
61 | Page 14 | 1 |  | Material Check and sampling of main parts | Review of material certificates only
62 | Page 14 | 1 |  | H/RA (*) | Review of material certificates only
63 | Page 14 | 1 |  | (*): Hold for sampling Review Approve for certificate of parts | Review of material certificates only
64 | Page 15 | 1 |  | W | Review onlt
65 | Page 15 | 1 |  | Below items shall be added: -Protection of machine surface -Welding for connections (if any) -NDT on main parts -Run-out check -Assembling | These inspections are not considered
66 | Page 15 | 1 |  | Hydrostatic test and Gas leakage test for cylinder and connections and pressure containing parts. | These inspections are not considered
67 | Page 16 | 1 |  | SW | Only review
68 | Page 16 | 1 |  | W | Only review
69 | Page 16 | 1 |  | According to comments from electrical Disciplines | Noted
70 | Page 16 | 1 |  | add test procedure. | No test procedure will be submitted as the test is according international standard
71 | Page 17 | 1 |  | RA | Noted will be upodated
72 | Page 17 | 1 |  | add VPIS | VPIS is not applicable for this point
73 | Page 17 | 1 |  | Add VPIS | VPIS is not applicable for this point
74 | Page 17 | 1 |  | add Relevante calibration procedure or standard | No releveant procedure applicable
75 | Page 17 | 1 |  | add Relevante calibration procedure or standard | No releveant procedure applicable
76 | Page 18 | 1 |  | and Visual | Noted will be updated
77 | Page 19 | 1 |  | API 618, Specification | Only FAT procedure
78 | Page 19 | 1 |  | Mechanical and performance Procedure | Only FAT procedure
79 | Page 19 | 1 |  | Mechanical and performance Procedure | Only FAT procedure
80 | Page 19 | 1 |  | Shall be added: -Strip Down test -Machine Monitoring System including Vibration monitoring system and Temperature Monitoring System -SAT | These inspections are not considered
81 | Page 20 | 1 |  | Clearance of all remained punches. | Noted will be updated
82 | Page 20 | 1 |  | add MR, data sheet | Noted will be updated
83 | Page 20 | 1 |  | for main parts and 2 year spare parts | Noted will be updated
84 | Page 21 | 1 |  | Add Name plate & Tag check. | Will be added to FAT
85 | Page 21 | 1 |  | add approved data sheet. | Datasheet has nothing to do with it
86 | Page 21 | 1 |  | add approved data sheet. | Datasheet has nothing to do with it
87 | Page 21 | 1 |  | Approve Packing List | Noted will be updated
88 | Page 21 | 1 |  | change to app. packing list | Noted will be updated
89 | Page 21 | 1 |  | add app. VPIS | Noted will be updated
90 | Page 21 | 1 |  | change to "Final book index, VPIS" | Noted will be updated
91 | Page 21 | 1 |  | add SAT (if it is required as per contract) | Not applicable in this ITP
| page 9 | aftermeeting |  | B.5 NDT qualification certificate | will add at every NDT item. NDT is outsourced.
| page 9 | aftermeeting |  | IECEx , IP, ATEX and SIL certificate | part of MRB and MRB index is a document for approval.
| page 17 | aftermeeting |  | performance routine test | as per spec motor is LV and only type test is needed.
| page 17 | aftermeeting |  | components | As per spec motor is LV and only name plate final inspection are witness points. This can be checked during the FAT
| page 17 | aftermeeting |  | painting | As per spec motor is LV and only name plate final inspection are witness points. This can be checked during the FAT
| page 18 | aftermeeting |  | leaktest | During FAT