## Resolution Sheet
|  |  |  | PROJECT: | 17811
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Datasheets & drawings for strainers | 17811-44
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
General | page 1 | 0 | Open | 1. Strainer drawing shall be added in next revision. | Will be added in revision after purchase.
1 | page 1 | 0 | Closed | 2. These data is checked by considering that 20-C1002 is not finalized. | Noted
2 | page 4 | 0 | Closed | 20-C-7080: 50 kg/hr | Will be incorporated in next revision
3 | page 4&5 | 0 | Closed | Please check gap size again and select suffiecient strainer | Will be incorporated in next revision
4 | page 5 | 0 | Closed | This item must be filled out. | Will be incorporated in next revision
5
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26