## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | XX | XXXXX-XX
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | PAGE1 | 00 | Closed | Prerequisite document such as I/O list shall be issued. | ok
2 | PAGE1 | 00 | Closed | This document is checked only for compressor 7080. New document should be generated for compressor 1002. | Will be separeted in two documents
3 | PAGE3 | 00 | Closed | refer to comments on instrument index. | Will be incorporated
4 | PAGE3 | 00 | Closed | Discrepancy with PID. On PID FAL is considered. | Wil be incorporated
5
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20