## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 05/Oct/2020 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: INSPECTION & TEST PLAN (ITP)
|  | Transmittal No.: APCES-V-00029 | Doc. No.: BU-20-VD-303-QC-ITP-0005
|  | Transmittal Date: 05/10/2021 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | this has been commented before to 20%. |  |  | Yes I know but it won't be changed as the 10% is your own format.
2 | Project Spec, Standards |  |  | Noted will be incorperated
3 | Eng Docs |  |  | Noted will be incorperated
4 | Approved Procedures |  |  | Noted will be incorperated
5 | Project Spec, Data Sheet, DWG |  |  | Noted will be incorperated
6 | add EN10204 type 3.1 / Lab test report (Note 1) Note 1: If there is any doubt about the authenticity of the material test certificate, sampling and laboratory tests shall be done under supervision of TPI. |  |  | Only 3.1 Material certificate, Lab test report is not considered
7 | H/H/R |  |  | As Per SOI provided this is not H point but RI
8 | change to VT report |  |  | VT Meaning visual inspection, then this is agreed
9 | W |  |  | As Per SOI provided this is not W point but RI
10 | W |  |  | Dimensions will be checked during the FAT of the package
11 | add visual and move this step before step of welding |  |  | see point 8, alread Visual inspection
12 | Raw material |  |  | Noted will be changed
13 | As per Item c.1 comments. |  |  | As per C.1 reply
14 | add PT for fillet weld such as branch and socket welds (if any) |  |  | As per ASME B31.3 only RT is required 5%
15 | and UT for all joints except for pipes less than 8 mm thick |  |  | As per ASME B31.3 only RT is required 5%
16 | NDT Report, Certificates |  |  | Noted will be changed
17 | Report |  |  | Noted will be changed
18 | SW |  |  | as per SOI only review of films
19 | As per C.1 comments |  |  | As per C.1 reply
20 | NDT Report |  |  | Noted will be changed
21 | Report |  |  | Noted will be changed
22 | H |  |  | Noted will be changed
23 | As per C.1 comments |  |  | As per C.1 reply
24 | report |  |  | Noted will be changed
25 | H |  |  | Noted will be changed
26 | As per C.1 comments |  |  | As per C.1 reply
27 | Visual and |  |  | Noted will be changed
28 | W |  |  | During FAT
29 | Add Test Procedure, DWG |  |  | Noted will be changed
30 | Add Test Procedure, DWG |  |  | Noted will be changed
31 | and Test Report |  |  | Noted will be changed
32 | SW |  |  | During FAT
33 | W |  |  | Not possible, due to the fact that mfr is WEG, motor is made in brasil and they do not allow inspections at this moment due to Covid-19
34 | DWG, Data Sheet, Project Spec |  |  | Noted will be changed
35 | RA |  |  | Noted will be changed
36 | Visual and |  |  | Noted will be changed
37 | API 618, Specification |  |  | Noted will be changed
38 | Mechanical and performance Procedure |  |  | FAT procedure, everything is mentioned there
39 | Mechanical and performance Procedure |  |  | FAT procedure, everything is mentioned there
40 | API 618, Specification |  |  | Noted will be changed
41 | For Main Parts and 2 Years Spare Parts |  |  | Noted as per P.O.
42 | Clearance of all remained punches. |  |  | Noted will be changed
43 | Packing and Marking Inspection |  |  | Packing and Marking Procedure, Data Sheet, MTO, DWG
44
45
46
47
48
49
50
51
52
53
54
55
56