## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 05/oct /2021 | Rev.: 00
|  | Comment Sheet Ref.No.: | Doc Description: Subvendor list
|  | Transmittal No.: APCES-V-00030 | Doc. No.: BU-20-VD-303-PE-LST-0002
|  | Transmittal Date: 05/10/2021 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Change new logo all pages |  |  | noted
2 | Issue For Approval |  |  | noted
3 | classs 1 |  |  | noted
4 | Phase P |  |  | noted
5 | Type of material and vendor is not in AVL of project |  |  | The block of the Airpack compressor is made by Mehrer.
6 | Vendors are in AVL but not related to the type of material Coolers |  |  | Water cooler is not part of the AVL. So Airpack standerd will be followed.
7 | Vendors are in AVL but not related to the type of material Filters |  |  | Airapck standerd AVL was provided. Filters not part of this package. Part removed.
8 | Vendors are in AVL but not related to the type of material motors |  |  | noted
9 | Repeated |  |  | changed in two groups. Flow transmitters and Temp and pressure transmistters
10 | Type of material is not in AVL |  |  | Airpack standerd will be followed
11 | More specfication needed |  |  | Airapck standerd AVL was provide. Heater not part of this package. Part removed.
12 | Vendors are in AVL but not related to the type of material heater |  |  | Airpack standerd will be followed
13 | Cable glands |  |  | Group material not part of the agreed AVL. Airpack standard will be followd.
14 | Gaskets |  |  | As per TCL Airapck will follow the most. In this catagoryy we will not folluw agreed AVL. Gaskets are a critical for proper working. Airpack will use there AVL to ensure garantue and working of the compressor.