## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 19/Oct/2021 | Rev.:00
|  | Comment Sheet Ref.No.: | Doc Description: MODBUS LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00037 | Doc. No.: BU-20-VD-303-IN-LST-0102
|  | Transmittal Date: 19/10/2021 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Prerequisite document such as I/O list shall be issued. This doc to be updated based on comments on index and also as per project PID (for interface signals between PLC and main system) |  |  | Noted. It will be incorporated.
2 | LOGO CES |  |  | Noted. It will be incorporated.