## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 05/Oct/2020 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: INSPECTION & TEST PLAN (ITP)
|  | Transmittal No.: APCES-V-00029 | Doc. No.: BU-20-VD-303-QC-ITP-0005
|  | Transmittal Date: 05/10/2021 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 |  |  |  | The document as per the PIM is mostly ok for us, except for below points marked yellow in the below documents.
2 |  |  |  | Welder qualification and NDT personnel qualification will be presented during inspection if requested by the inspector, no prior approval required.
3 |  |  |  | added 100%MT for lifting lugs
4 |  |  |  | added visual en paint inspection during FAT
5 |  |  |  | Added 5% RT according ASME b31.3 for piping
6 |  |  |  | as discussed we will club all inspections together, therefore we have deleted FIT-up inspection and have only visial en dimensional inspection
7 |  |  |  | NDT for ASME VIII equipment added "NDT as per ASME VIII if any"
8 |  |  |  | Gas leuk test of compressor during FAT
9 |  |  |  | NDT fro compressor removed, as per the submitted letter
10 |  |  |  | Removed wetted parts from compressor material certificates
11 |  |  |  | Final data book and certificates was mentioned 3 times, has been removed 2 times
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56