## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 30/Nov/2020 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: LOGIC DIAGRAMS-PROGRAM OF UCP - COMPRESSOR SHUTDOWN LOGIC DRAWING FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00057 | Doc. No.: BU-20-VD-303-IN-DIG-0035
|  | Transmittal Date: 30/Nov/2021 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Drawing shall be match the title of the project block |  |  | Noted. It will be incorporated.
2 | Prerequisite document such as cause & effect, control philosophy and I/O list shall be issued. |  |  | Noted. It will be incorporated.
3 | This document is checked only for compressor 7080. New document should be generated for compressor 1002. |  |  | Noted. It will be incorporated.
4 | tag names to be updated based on PID. All loops to be added to logic (FT/PCV/VT...) |  |  | Noted. It will be incorporated.
5 | to be updated based on PID |  |  | Noted. It will be incorporated.
6 | EL.01: It's not clear. one Emergency push button there is on LCP in accordance with standard drawings and philosophy. |  |  | This is stop button, not emergency shutdown button. For ESD pushbutton, please refer to Sheet 2.