## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 07/Dec/2021 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00064 | Doc. No.: BU-20-VD-303-ME-DSH-0022
|  | Transmittal Date: 07/Dec/2021 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | LEVELING SCREWS, SUB SOLE PLATES, CHOKE BLOCKS and shims are required. |  |  | Not required for mounting on a foundation, this will be mounted with anchor bolts, levelling is not required.
2 | With reference to clause 6.1.7 of API618 5th edition, allowable pressure drop along heat exchanger shall not exceed 1bar. Also with reference to clause 4.3.6 of BU-20-D-000-PR-SPC-101-06 pressure unit is bara. |  |  | pressure drop accros the cooler is as per pressure drop stated in the the information from client, additional pressure drop is created by a globe valve in the cooling water line to the cooler. Unit is bar(g) as per P&ID
3 | 1- ASTM material equivalent shall be added. |  |  | will not be added, as this are the materials used
4 | All remaining data to be completed |  |  | After completion of pulsation study, currently waiting for customer piping details
5 | All Notes shall be revised as per attached file. |  |  | This is what was provided in this format.