## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 09/Dec/2021 | Rev.: 02
|  | Comment Sheet Ref.No.: | Doc Description: MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00065 | Doc. No.: BU-20-VD-303-ME-DSH-0075
|  | Transmittal Date: 09/Dec/2021 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | With reference to following termodynamic formula T2/T1 = (P2/P1) (K-1/K), Discharge temperature is 148 C in adiabatic condition. |  |  | This comes from our calculation program for this type of compressor, I can’t change it CES reply: Closed.
2 | Mass flow rate does not match with compressor gas power. Gas power= H2 - H1 |  |  | It does as the actual flow is higher then the required flow CES reply: Closed.
3 | Pulsation dampener shall be equipped with moisture removal. |  |  | There will be a manual drain valve, but not automatic as the inlet air is dry CES reply: Closed. Please revie page 16.
4 | Insulation wherever is required, shall be done by AIRPACK. |  |  | Only PP CES reply: Please clarify what is PP?
5 | Perfomance required |  |  | these charts are not available CES reply: Closed.
6 | Remaining data shall be completed. |  |  | Rod packing not cooled CES reply: Selection of suitable material as per API618 is in vendor responsibility.
7 | PLAN D ????????? |  |  | What does this comment mean CES reply: Closed.
8 | ent and drain connection shall be considered by vendor. |  |  | Drain will be considerd CES reply: Closed.
9 | With reference to clause 6.1.7 of API618 5th edition, allowable pressure drop along heat exchanger shall not exceed 1bar. Also with reference to clause 4.3.6 of BU-20-D-000-PR-SPC-101-06 pressure unit is bara. |  |  | pressure drop accros the cooler is as per pressure drop stated in the the information from client, additional pressure drop is created by a globe valve in the cooling water line to the cooler. Unit is bar(g) as per P&ID
10 | 1- ASTM material equivalent shall be added. |  |  | will not be added, as this are the materials used
11 | All remaining data to be completed |  |  | After completion of pulsation study, currently waiting for customer piping details
12