## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 06/Jan/2022 | Rev.: 02
|  | Comment Sheet Ref.No.: | Doc Description: POWER CABLE SCHEDULE & LIST FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00075 | Doc. No.: BU-20-VD-303-EL-LST-0050
|  | Transmittal Date: 06/Jan/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
| EL: 1) Comment/Reply Sheet shall be submitted by vendor for each revision. 2) Any change or modification shall be specified by revision cloud. |  |  | 1)Noted. 2) The changes in the document will be shown in red.
1 | EL: Power Distribution Board (PD-C-1002-01) |  |  | Noted. It will be incorporated.
2 | EL: Unit Control Panel (UCP-C-1002-01) |  |  | Noted. It will be incorporated.
| EL: This column is duplicated |  |  | The first column shows the gland sizes from the first side of the cable, and the second column shows the other side.
| Power Distribution Board (PD-C-1002-01) |  |  | Noted. It will be incorporated.
| Nitrogen Gas Booster Compressor (20-C-1002-M) |  |  | Noted. It will be incorporated.
| Power Distribution Board (PD-C-1002-01) |  |  | Noted. It will be incorporated.
| EL: According to our "Cable List" document: "Substation Switchboard 20-MS-SWB3B-01" |  |  | Noted. It will be incorporated.
| EL: Oil Heater (20-C-1002-EC) |  |  | Oil Heater (LG-10151) according to the wiring diagram.
| EL: Please clarify this name. |  |  | LG-10151 according to wire diagram.
| EL: It seems, cable for Workstation (according to Electrical Load List) has been missed. It shall be clarified by vendor. |  |  | We don’t require and electrical cable, just an outlet for our power plug.
| EL: Following note shall be added according to vendor's "Electrical Load List" document. |  |  | Please comment on electrical load list seperately, as documents are made by different departments.