## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 06/Jan/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: COMPRESSOR MOTOR CURVE FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00077 | Doc. No.: BU-20-VD-303-EL-DIG-0100
|  | Transmittal Date: 06/Jan/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | EL: Color of this axis shall be changed into red, similat to next page. |  |  | These are standard curves from the motor supplier and therfore this cannot be changed
2 | EL: Color of this axis shall be changed into green, similat to next page. |  |  | These are standard curves from the motor supplier and therfore this cannot be changed
3 | EL: Add it: T / Tn |  |  | These are standard curves from the motor supplier and therfore this cannot be changed
4 | EL: Add it: I / In |  |  | These are standard curves from the motor supplier and therfore this cannot be changed
5 | EL: Conflict with data sheet. Vendor shall clarify them. Which one is true? |  |  | Data has been slighty modified after order stage of the motors, we have updated the motor datasheet accordingly and it will be submitted together with the new revision of these curves.
6 | EL: S = (Ws-Wr) / Ws Slip can change from 1 (at start) to 0 (at full load). It seems that this curve is not true. Please clarify it. |  |  | The curve is correct as it it based on percentage of rated current.
7 | EL: Please clarify this axis. |  |  | this is the percentage of the rated current.
8 | EL: Refer to comments on previous pages. |  |  | These are standard curves from the motor supplier and therfore this cannot be changed
9 | EL: Refer to comments on previous pages. |  |  | These are standard curves from the motor supplier and therfore this cannot be changed
10
11
12