## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 04/Nov/2021 | Rev.: 01
|  | Comment Sheet Ref.No.: | Doc Description: P&ID FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00045 | Doc. No.: BU-20-VD-303-PR-DWG-0013
|  | Transmittal Date: 04/11/2021 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CHCE Reply | Vendor Clarification
1 | Discharge |  |  | Noted and updated |  |  | Closed. | Updated
2 | With reference to clause M17 of TCL, three-step capacity control as well as spill back line for capacity control of compressor 20-C-1002 are required. |  |  | three step capacity control is not possible on this compressor, we can use spill back line for stepless control of capacity |  |  | Capacity control system shall be guaranteed by vendor | Updated with recylce / spill over valve
3 | 55. Please refer to clause M29 of TCL. |  |  | this was a type we want to confirm a 45kw Motor, as the absorbed power is only 37 kw 45 is more then sufficient. |  |  | Closed. | Noted
4 | 2nd |  |  | Noted and updated |  |  | Closed. | Updated
5 | Following items must be report: 1. Inlet T/Outlet T (oC) (Tube) 2. Inlet T/Outlet T (oC) (Shell) 3. Inlet T/Outlet P (barg) (Tube) 4.Inlet T/Outlet P (barg) (Shell) |  |  | the information at this time on the P&ID is sufficient, all other details can be found on the respective datasheet |  |  | Closed. | Noted
6 | Considering the fact that "Inter Cooler" is located in outlet of first stage and "After Cooler" is located in outlet of second stage, The condition of them are different. |  |  | will be corrected in next revision |  |  | Closed. | Updated
7 | With reference to clause M7 of TCL two PT shall be considered. |  |  | Noted and updated |  |  | Closed. | Updated
8 | 1 1/2" 150# |  |  | We will check wheter this is possible with this flow |  |  | Closed. | Updated
9 | With reference to clause M7 of TCL one TG shall be considered in discharge of package. |  |  | Noted and updated |  |  | Closed. | Updated
10 | To be deleted |  |  | Noted and updated |  |  | Closed. | Updated
11 | Hardware signal from compressor output to be connected to solenoid valve. if it is required to controlled by HMI hand switch it must be connected to interlock and also interlock to be described in the general notes. |  |  | This is already the case. Not handswitch is foreseen |  |  | Following symbol shall be deleted and PIC via hardware signal to be connected to the solenoid directly. | Updated
12 | With reference to clause M7 of TCL one PG shall be considered in discharge of package. |  |  | Noted and updated |  |  | Closed. | Updated
13 | Size of process connection to be specified. |  |  | Noted and updated |  |  | Closed. | Updated
14 | Solenoid valve tag to be specified. |  |  | Noted and updated |  |  | Schematic to be modified for field mounted. | Updated
15 | 1 1/2" 150# |  |  | We will check wheter this is possible with this flow |  |  | Closed. | Updated
16 | PLEASE CHECK INSTRUMENT AIR AND WASTE WATER REQUIREMENT LINES ACC. TO CLEINT PID. |  |  | This is from old flow, this is no longer valid |  |  | Closed. | Updated
17 | Pipe to be expanded to 4" for installation of TW on pipe. |  |  | Noted and updated |  |  | Closed. | Updated
18 | With reference to clause M7 of TCL three TT shall be considered at interstage line. Two TT for HIGH (H)signal and HIGH HIGH signal (HH) before inter cooler and One TT HIGH signal (H) after INTERCOOLER. |  |  | Noted and updated |  |  | Closed. | Updated
19 | With reference to clause M7 of TCL two PT (HIGH and HIGH HIGH) shall be considered at interstage line. |  |  | Noted and updated |  |  | Closed. | Updated
20 | Considering the fact that the pulsation damper is located in outlet of first stage, OP/DP must be revised to outlet pressure of first stage. |  |  | Noted and updated |  |  | Closed. | Updated
21 | Considering the fact that the pulsation damper is located in inlet of second stage, OP/DP must be revised to outlet pressure of first stage. |  |  | Noted and updated |  |  | Closed. | Updated
22 | Considering the fact that the pulsation damper is located in outlet of second stage, OP/DP must be revised to outlet pressure of second stage. |  |  | Noted and updated |  |  | Closed. | Updated
23 | Suction/Discharge pressure and temperature and design condition of each stage must be reported separately. |  |  | Not required in this P&Id this information can be found in the datasheet |  |  | Closed. | Updated
24 | Following signals shall be considered from ESD to UCP too : C-1002-MOS-1 HS-108-1R-1 |  |  | singals will not be added, MOS is not allowed on our compressor, also reset is not required as this is part on the UCP |  |  | Closed. | Updated
25 | Instrument and signals tag numbering shall be modify as per comment in previous page |  |  | Noted and updated |  |  | Closed. | Updated
26 | HS-108-SD-1 |  |  | Noted and updated |  |  | Closed. | Updated
27 | XCS-108 |  |  | Noted and updated |  |  | Closed. | Updated
28 | Please specify signals direction too |  |  | Noted and updated |  |  | Closed. | Updated
29 | This signal is not required |  |  | Noted will be removed |  |  | Closed. | Updated
30 | - Reply sheet shall be submitted by vendor. - Symbol, Legend and abbreviation shall be submitted by vendor. - All instruments tag no. procedure in nitrogen compressor shall be same as follow: PG-1015X → 5X your sequence number - Please clarify whether C-1002 and C-7080 have one UCP for both or each of them have a separate UCP. |  |  | - Noted - Not required as this is customer legend - Noted will be updated - Separate |  |  | Closed. | Updated
31
32