## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 21/Jan/2022 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: CONTROL PHILOSOPHY FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00087 | Doc. No.: BU-20-VD-303-PR-DPH-0046
|  | Transmittal Date: 21/Jan/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification
1 | considering the fact that many instrument tag numbers are modified yet the PID is not updated, the current document cannot be reviewed. the document will be reviewed after the PID. |  |  | This is unaceptable, the P&ID is on your side since 04-11-21 transmittal number 0045 CES REPLY (Jan.08,2021): See comment NO. CESAP-V-00057. P&ID is in Airpack side. Airpack Reply, P&ID has been resend
2 | Control philosophy of capacity control via unloaded valve shall be added. |  |  | updated CES REPLY (Jan.08,2021): Closed.