## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 10/Feb/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: Compressor FAT test procedure
|  | Transmittal No.: APCES-V-00094 | Doc. No.: BU-20-VD-303-QC-PRC-0009
|  | Transmittal Date: 10/Feb/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | Comments: 1.Lube oil filters shall be checked and replaced to new filters for shipment after Mechanical Running Test is completed. 2.The combined performance of the compressor and its driver under all operating conditions shall be the responsibility of the Vendor. The combined unit (or complete package, if applicable) shall perform as well on its permanent foundation as it did on the Manufacturer’s test stand. 3. All requirements of API 618 standard for mechanical running test and performance test shall be added. 4. Monitoring system conditions included gauges, Trans meters and etc shall be added. 5. How to calculate power and efficiency shall be added. The efficiency value shall not be less than specified value. The power consumption also shall be checked not to be more than 3% of rated value. 6.The API 618, requires that the reciprocating compressor manufacturer makes necessary calculations and provide the vibration limits. The vibration testing is done in 4 hour mechanical running test. 7.All job and shop equipments condition during FAT shall be cleared. |  |  | 1. lube oil filters will only be inspected, replacement is not required, they can be replaced after commissioning if required 2. Noted, however it will be tested under local condition, performance guarantee is part of warranty 3. Comment is not clear, what requirements are you talking about, please be more specific, all applicable items are already part of this procedure 4. all transmitter and gauges will be measured during the performance test. and recorded in attachment 4, which has been added in the new revision. 5. There are no provisions to calculate the efficiency, however we will measure the voltage and amps from which we calculate the absorbed power. 6. as we are only providing a frame vibration sensor, this is the only thing that will be measured during the running/performance test. 7. this comment is not clear, please specifiy.
2 | Following document shall be added to reference list: 1- Trip and alarm set point list 2- IO list 3- JB/UCP/LCP wiring diagram 4- JB/UCP/LCP drawing 4- Power distribution panel drawing 5- Power distribution panel wiring diagram 6- Modbus list |  |  | Noted and added
3 | Project document number shall be added |  |  | Noted and added
4 | and local MCC panel |  |  | Noted and added
5 | Acceptance criteria should be based on the 618 API standard |  |  | as we are only providing a frame vibration sensor, this is the only thing that will be measured during the running/performance test.
6 | vibration is measured in X, Y, and Z axises (Horizontal, Vertical, and Axial) |  |  | as we are only providing a frame vibration sensor, this is the only thing that will be measured during the running/performance test.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56