## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 10/Mar/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00111 | Doc. No.: BU-20-VD-303-ME-DSH-0027
|  | Transmittal Date: 10/Mar/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | Mechanical items will be checked after sending pulsation dampener calculation. |  |  | Noted, however please confirm datasheet is ok, calculation will be submitted soon CES reply: Closed.
2 | Following items shall be added to data sheet: 1- Dampener thickness. 2- RAL number of pulsation dampener. 3- Maximum Allowable Compressor Cylinder Flange Pressure Pulsation as per clause 7.9.4.2.5.2.1 of API618. 4- Maximum Allowable Pulsation Limits at and Beyond Line-side Nozzles of Pulsation Suppression Devices as per clause 7.9.4.2.5.2.2.1 of API 618. 5- Pulsation dampener design approach shall be added to document. 6- Maximum Allowable Pressure Drop as per clause 7.9.4.2.5.3.1 of API 618. 7- Capacity of pulsation dampener will be checked after specifying cylinder stroke and cylinder diameter. 8- DESIGN APPROACH STUDY SHALL BE ADDED. |  |  | 1.Noted and added CES reply: Closed. 2. Noted and added CES reply: Closed. 3. Noted and added CES reply: Closed. 4. Noted and added CES reply: Closed. 5. Noted and added CES reply: Closed. 6. Noted and added CES reply: Closed. 7. Noted CES reply: Closed. 8. Noted and added CES reply: Closed.
3 | Shall be specified in next revision. |  |  | updated CES reply: Closed.
4 | Exact material grade shall be added. |  |  | updated CES reply: Closed.
5 | 3 mm. |  |  | updated CES reply: Closed.
6 | Discrepancy with PID. |  |  | updated CES reply: Closed.
7 | Discrepancy with PID. On PID DP is reported 21 bara. |  |  | updated CES reply: Closed.
8 | Discrepancy with PID. On PID DP is reported 35.25 bara. |  |  | updated CES reply: Closed.
9 | Exact material grade shall be added. |  |  | updated CES reply: Closed.
10 | 1300#???? |  |  | updated CES reply: Closed.
11 | 3 mm. |  |  | updated CES reply: Closed.
12 | 1- Based on these data compressor data sheet shall be updated. 2- Percentage of allowable peak-peak pulse @ cylinder flange shall be added to document. |  |  | 1. Noted and will be updated 2. This was updated
13 | With reference to clause 4.5 of BU-20-D-000-PR-SPC-101 (ESS FOR AMBIENT, SITE CONDITION & UTILITY DATA), design temperature shall be at least 85C. |  |  | updated
14 | Test pressure shall be specified here clearly as a number. Also MAWP is not specified in this data sheet |  |  | This will be specified in calculation documents of pulsation dampers
15 | RAL color shall be deleted. Painting shall be as per APPROVED painting procedure. |  |  | updated
16 | Please check it again. |  |  | updated
17 | Please check the pressure with compressor data sheet. Discharge pressure of stage 1 is 14.5 barg. |  |  | updated
18 | Please check the capacity again. With reference to compressor data sheet, suction pressure is 7,8,9 bara and discharge of stage 1 is 15.5 bara. Therefor, capacity of pulsation dampener considering suction pressure 9 bara and discharge pressure 15.5 bara is almost 100 liter. Vd= 1.6x (Vs/r1/k) |  |  | based on simulation 80 Liters is sufficient
19 | With reference to latest comments on P&ID, PSV set pressure shall be at least 10% above operating pressure. Therefore, disign pressure shall be revised. |  |  | updated
19 | As per mechanical data sheet of compressor, design temperature is 210 C. |  |  | Mechanical datasheet will be updated
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19