## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 10/Mar/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00111 | Doc. No.: BU-20-VD-303-ME-DSH-0027
|  | Transmittal Date: 10/Mar/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | 1- Based on these data compressor data sheet shall be updated. 2- Percentage of allowable peak-peak pulse @ cylinder flange shall be added to document. |  |  | 1. Noted and will be updated 2. This was updated
2 | With reference to clause 4.5 of BU-20-D-000-PR-SPC-101 (ESS FOR AMBIENT, SITE CONDITION & UTILITY DATA), design temperature shall be at least 85C. |  |  | updated
3 | RAL color shall be deleted. Painting shall be as per APPROVED painting procedure. |  |  | updated
4 | Please check it again. |  |  | updated
5 | shall be move one row to upward |  |  | updated
6 | For this row, vessel dimensions shall be specified. |  |  | updated
7 | If standard pipe and cap used for body of vessel, please recheck thickness |  |  | updated
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
19
19
19
19
19
19
19
19
19
19
19
19
19