## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 25/Mar/2022 | Rev.: 04
|  | Comment Sheet Ref.No.: | Doc Description: CAUSE & EFFECT CHART LIST FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00117 | Doc. No.: BU-20-VD-303-PR-LST-0042
|  | Transmittal Date: 25/Mar/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | General comments: 1. Please be noted that the document must be followed a similar approach. For instance, some alarms ,such as TAH-10153, are reported, but High and Low alarms related to PIC-10158 are not reported. |  |  | everything is as per P&ID, the TAH 10153 is HH and is reported PIC-10158 H and L are not alarms but load and unload
2 | - Effects of following signals shall be specified: • PIT-10157 • PB-10159 • PB-10160 |  |  | PIT-1057 has been added PB-10159 is accept and is not part of cause and effect, this is part of the control philosophy PB-10160 is reset and is not part of cause and effect, this is part of the control philosophy
3 | There are some inconsistencies between the current document, vendor's PID and the project PID. (please refer to the attachment) |  |  | This is according to the current P&ID, where no comments were received on this, so will not be updated
4 | Not found in PID |  |  | deleted
5
6
7
8
9
10
11
12