## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 13/Apr/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL DATA SHEET FOR INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00123 | Doc. No.: BU-20-VD-303-ME-DSH-0028
|  | Transmittal Date: 13/Apr/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | 1- Based on these data compressor data sheet shall be updated. 2- Percentage of allowable peak-peak pulse @ cylinder flange shall be added to document. |  |  | 1. Noted and will be updated CES reply : Closed. 2. This was updated CES reply : Closed.
2 | With reference to clause 4.5 of BU-20-D-000-PR-SPC-101 (ESS FOR AMBIENT, SITE CONDITION & UTILITY DATA), design temperature shall be at least 85C. |  |  | updated CES reply : Closed.
3 | RAL color shall be deleted. Painting shall be as per APPROVED painting procedure. |  |  | updated CES reply : Closed.
4 | Please check it again. |  |  | updated CES reply : Closed.
5 | shall be move one row to upward |  |  | updated CES reply : Closed.
6 | For this row, vessel dimensions shall be specified. |  |  | updated CES reply : Closed.
7 | If standard pipe and cap used for body of vessel, please recheck thickness |  |  | updated CES reply : Closed.
8
9 | 3. 8.5 bara |  |  | Noted and updated
10 | 6. In AB revision of P&ID, P&ID shall be revised. |  |  | Please provide your comments so we can issue before AB
11 | 1.Please use same unit in the document. |  |  | Noted and updated
12 | Unit shall be same. |  |  | Noted and updated
13 | 2.Please double-check. In PID the design pressure is reported 25 bara while the set pressure of PVS on the downstream is 26 barg. |  |  | P&ID needs to be updated, please provide your comments there
14 | Same as pulsation dampener drawing, 26 barg shall be used. |  |  | Noted and updated
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
19
19
19
19
19
19
19
19
19
19
19
19
19